## Tasks
Tasks
Target (From): |  |  | Target (Thru): |  |  |  | Completed: |  |  |  | Completed (From): |  |  |  |  | Completed (Thru):
Protocol No.: |  | Staff Name: |  |  |  | Staff Role: |  |  |  | Institution: |  |  |  | NA: |  |  |  | Management Group: |  | CTSU - Ambulatory and
Task List | Task Name |  |  | Owner Type | Owner Name |  |  | Target Date | Days Overdue |  |  | Completed Date | NA |  | Protocol No |  | Institution |  | Mgmt Group
CTSU Pre-Award - 336-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2016-07-07 | 0 |  |  | 2016-07-07 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-01-17 | 0 |  |  | 2017-01-17 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-01-20 | 0 |  |  | 2017-01-20 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2017-01-20 | 0 |  |  | 2017-01-20 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-01-22 | 0 |  |  | 2017-01-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-01-23 | 0 |  |  | 2017-01-23 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-01-24 | 0 |  |  | 2017-01-24 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-01-24 | 2 |  |  | 2017-01-26 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-01-25 | 0 |  |  | 2017-01-25 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-01-27 | 138 |  |  | 2017-06-14 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-01-29 | 143 |  |  | 2017-06-21 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-01-29 | 143 |  |  | 2017-06-21 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-01-30 | 0 |  |  | 2017-01-30 | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-01-30 | 0 |  |  | 2017-01-30 | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-01-31 | 524 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-01-31 | 524 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-01 | 0 |  |  | 2017-02-01 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-01 | 0 |  |  | 2017-02-01 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-02-01 | 22 |  |  | 2017-02-23 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-02 | 0 |  |  | 2017-02-02 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-02 | 0 |  |  | 2017-02-02 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-03 | 0 |  |  | 2017-02-03 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-03 | 0 |  |  | 2017-02-03 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-03 | 0 |  |  | 2017-02-03 | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-03 | 0 |  |  | 2017-02-03 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-03 | 0 |  |  | 2017-02-03 | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-03 | 4 |  |  | 2017-02-07 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-02-03 | 7 |  |  | 2017-02-10 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-02-05 | 134 |  |  | 2017-06-19 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-02-05 | 1 |  |  | 2017-02-06 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-02-06 | 0 |  |  | 2017-02-06 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-06 | 0 |  |  | 2017-02-03 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | LaVasseur, Kristen |  |  | 2017-02-06 | 0 |  |  | 2017-02-06 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2017-02-06 | 128 |  |  | 2017-06-14 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-07 | 0 |  |  | 2017-01-19 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-07 | 0 |  |  | 2017-02-07 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-07 | 0 |  |  | 2017-02-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-07 | 517 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-07 | 0 |  |  | 2017-02-07 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-02-07 | 150 |  |  | 2017-07-07 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-02-07 | 143 |  |  | 2017-06-30 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-08 | 0 |  |  | 2017-02-08 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-08 | 0 |  |  | 2017-02-08 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-02-08 | 142 |  |  | 2017-06-30 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO |  |  | 2017-02-09 | 0 |  |  | 2017-02-09 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-09 | 0 |  |  | 2017-02-09 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-09 | 4 |  |  | 2017-02-13 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-09 | 0 |  |  | 2017-02-09 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-09 | 0 |  |  | 2017-02-09 | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-09 | 515 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-09 | 0 |  |  | 2017-01-30 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-09 | 515 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-02-09 | 515 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-02-09 | 515 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-02-09 | 148 |  |  | 2017-07-07 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-02-09 | 1 |  |  | 2017-02-10 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-02-10 | 0 |  |  | 2017-02-10 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO |  |  | 2017-02-10 | 0 |  |  | 2017-02-10 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-10 | 0 |  |  | 2017-01-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-02-10 | 0 |  |  | 2017-02-10 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-10 | 0 |  |  | 2017-02-10 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-02-10 | 0 |  |  | 2017-01-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-10 | 34 |  |  | 2017-03-16 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-11 | 34 |  |  | 2017-03-17 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-11 | 100 |  |  | 2017-05-22 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-02-11 | 25 |  |  | 2017-03-08 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO |  |  | 2017-02-12 | 0 |  |  | 2017-02-10 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-02-12 | 36 |  |  | 2017-03-20 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-02-13 | 0 |  |  | 2017-02-13 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-14 | 0 |  |  | 2017-01-19 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-14 | 0 |  |  | 2017-02-14 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-14 | 0 |  |  | 2017-02-14 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-14 | 0 |  |  | 2017-02-01 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-14 | 0 |  |  | 2017-02-14 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-14 | 0 |  |  | 2017-02-14 | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Nimblify Build is Complete & Ready for Import |  |  | Role | CRAO |  |  | 2017-02-15 | 5 |  |  | 2017-02-20 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-15 | 8 |  |  | 2017-02-23 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-02-15 | 33 |  |  | 2017-03-20 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-16 | 0 |  |  | 2017-01-26 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-16 | 5 |  |  | 2017-02-21 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-16 | 5 |  |  | 2017-02-21 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-16 | 0 |  |  | 2017-01-27 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-16 | 0 |  |  | 2017-01-24 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-02-16 | 5 |  |  | 2017-02-21 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Attach Build Notes ( as Protocol Doc ) |  |  | Role | CRAO |  |  | 2017-02-17 | 6 |  |  | 2017-02-23 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-17 | 0 |  |  | 2017-02-17 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-17 | 0 |  |  | 2017-02-17 | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-17 | 26 |  |  | 2017-03-15 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-17 | 26 |  |  | 2017-03-15 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-17 | 507 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-02-17 | 37 |  |  | 2017-03-26 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | LaVasseur, Kristen |  |  | 2017-02-17 | 6 |  |  | 2017-02-23 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-02-18 | 0 |  |  | 2017-02-01 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-19 | 37 |  |  | 2017-03-28 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-20 | 504 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-20 | 0 |  |  | 2017-01-30 | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-02-20 | 504 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-20 | 204 |  |  | 2017-09-12 | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-21 | 0 |  |  | 2017-02-21 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-21 | 0 |  |  | 2017-02-21 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-21 | 0 |  |  | 2017-02-21 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-21 | 0 |  |  | 2017-02-14 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-21 | 503 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-22 | 0 |  |  | 2017-02-03 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-02-22 | 61 |  |  | 2017-04-24 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-23 | 0 |  |  | 2017-02-06 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-23 | 0 |  |  | 2017-02-07 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-23 | 0 |  |  | 2017-02-23 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-23 | 0 |  |  | 2017-02-23 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-23 | 0 |  |  | 2017-02-23 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-23 | 0 |  |  | 2017-02-23 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-23 | 8 |  |  | 2017-03-03 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-23 | 39 |  |  | 2017-04-03 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-02-23 | 0 |  |  | 2017-02-23 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-24 | 403 |  |  | 2018-04-03 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-24 | 0 |  |  | 2017-02-23 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-24 | 500 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-24 | 174 |  |  | 2017-08-17 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-24 | 500 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 0 |  |  | 2017-02-07 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 0 |  |  | 2017-02-07 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 0 |  |  | 2017-02-24 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 500 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 0 |  |  | 2017-02-07 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 60 |  |  | 2017-04-25 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 31 |  |  | 2017-03-27 | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-24 | 0 |  |  | 2017-01-20 | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-24 | 0 |  |  | 2017-02-23 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-02-24 | 0 |  |  | 2017-02-01 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-02-24 | 19 |  |  | 2017-03-15 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-02-24 | 0 |  |  | 2017-02-01 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-02-24 | 500 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-25 | 5 |  |  | 2017-03-02 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-02-25 | 4 |  |  | 2017-03-01 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-25 | 0 |  |  | 2016-12-19 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-25 | 0 |  |  | 2017-01-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-02-25 | 0 |  |  | 2017-02-23 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-02-25 | 81 |  |  | 2017-05-17 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-02-26 | 95 |  |  | 2017-06-01 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-27 | 0 |  |  | 2017-02-08 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-02-27 | 497 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-02-27 | 80 |  |  | 2017-05-18 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-02-28 | 0 |  |  | 2017-02-14 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-02-28 | 0 |  |  | 2017-02-28 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-28 | 0 |  |  | 2017-02-28 | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-02-28 | 0 |  |  | 2017-02-28 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-28 | 0 |  |  | 2017-02-23 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-02-28 | 0 |  |  | 2017-02-17 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-28 | 8 |  |  | 2017-03-08 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-02-28 | 0 |  |  | 2017-02-24 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-02-28 | 496 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-01 | 0 |  |  | 2017-02-23 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-01 | 0 |  |  | 2017-02-13 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-01 | 0 |  |  | 2017-03-01 | N |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-01 | 495 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-01 | 495 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-03-01 | 495 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-01 | 495 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-02 | 0 |  |  | 2017-02-07 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-02 | 0 |  |  | 2017-02-23 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-02 | 0 |  |  | 2017-02-22 | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-02 | 0 |  |  | 2017-03-02 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-02 | 30 |  |  | 2017-04-01 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Feasibility Approval Notice Received |  |  | User | Hess, Aaron |  |  | 2017-03-02 | 14 |  |  | 2017-03-16 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Feasibility approved/CRAO Notified |  |  | User | Oliver, Amy |  |  | 2017-03-02 | 0 |  |  | 2017-03-02 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-03 | 493 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-03 | 132 |  |  | 2017-07-13 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-03 | 493 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-03 | 0 |  |  | 2017-03-03 | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-03 | 0 |  |  | 2017-02-01 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-03 | 0 |  |  | 2017-02-21 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-03 | 54 |  |  | 2017-04-26 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-03 | 493 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Final Budget |  |  | User | Henry, Robin |  |  | 2017-03-03 | 45 |  |  | 2017-04-17 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Care Designations completed |  |  | User | VanderElzen, Liz |  |  | 2017-03-03 | 12 |  |  | 2017-03-15 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-04 | 0 |  |  | 2017-02-23 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-04 | 0 |  |  | 2017-02-07 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-04 | 13 |  |  | 2017-03-17 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-04 | 0 |  |  | 2017-02-07 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-04 | 1 |  |  | 2017-03-05 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-03-04 | 4 |  |  | 2017-03-08 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-05 | 491 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-05 | 491 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 0 |  |  | 2017-02-21 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 32 |  |  | 2017-04-06 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 23 |  |  | 2017-03-28 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 29 |  |  | 2017-04-03 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-05 | 491 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | PAF routed |  |  | User | Henry, Robin |  |  | 2017-03-05 | 129 |  |  | 2017-07-12 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-06 | 0 |  |  | 2017-03-06 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-07 | 17 |  |  | 2017-03-24 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-07 | 489 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-07 | 0 |  |  | 2017-03-07 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-03-07 | 0 |  |  | 2017-02-22 | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-07 | 0 |  |  | 2017-02-21 | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-07 | 0 |  |  | 2017-03-01 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-07 | 13 |  |  | 2017-03-20 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-07 | 16 |  |  | 2017-03-23 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-07 | 0 |  |  | 2017-02-21 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-07 | 28 |  |  | 2017-04-04 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-08 | 0 |  |  | 2017-03-08 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-08 | 0 |  |  | 2017-03-08 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-09 | 0 |  |  | 2017-02-22 | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-09 | 0 |  |  | 2017-03-09 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-09 | 0 |  |  | 2017-03-09 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-09 | 18 |  |  | 2017-03-27 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-09 | 19 |  |  | 2017-03-28 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-09 | 487 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-10 | 10 |  |  | 2017-03-20 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-10 | 486 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-03-10 | 0 |  |  | 2017-03-10 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-03-10 | 59 |  |  | 2017-05-08 | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-10 | 59 |  |  | 2017-05-08 | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-10 | 0 |  |  | 2017-03-01 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-10 | 19 |  |  | 2017-03-29 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-10 | 0 |  |  | 2017-03-10 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-03-10 | 89 |  |  | 2017-06-07 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Planning Meeting Request Sent |  |  | Role | CTSU Administrator |  |  | 2017-03-11 | 0 |  |  | 2017-03-02 | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-11 | 0 |  |  | 2017-02-23 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 32 |  |  | 2017-04-13 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 0 |  |  | 2017-03-02 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 18 |  |  | 2017-03-30 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 61 |  |  | 2017-05-12 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 0 |  |  | 2017-03-10 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 4 |  |  | 2017-03-16 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-12 | 0 |  |  | 2017-02-01 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-13 | 0 |  |  | 2017-03-13 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-13 | 0 |  |  | 2017-03-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-03-13 | 483 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-13 | 483 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-13 | 483 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-13 | 483 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-03-13 | 0 |  |  | 2017-03-13 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-03-13 | 114 |  |  | 2017-07-05 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-14 | 13 |  |  | 2017-03-27 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-14 | 64 |  |  | 2017-05-17 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-14 | 482 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-03-14 | 0 |  |  | 2017-03-14 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-03-14 | 62 |  |  | 2017-05-15 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-14 | 9 |  |  | 2017-03-23 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-14 | 0 |  |  | 2017-03-14 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-14 | 15 |  |  | 2017-03-29 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Planning Meeting Request Sent |  |  | Role | CTSU Finance |  |  | 2017-03-15 | 481 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Planning Meeting Request Sent |  |  | Role | CTSU Finance |  |  | 2017-03-15 | 8 |  |  | 2017-03-23 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-03-15 | 14 |  |  | 2017-03-29 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-03-15 | 127 |  |  | 2017-07-20 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-03-15 | 5 |  |  | 2017-03-20 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-16 | 0 |  |  | 2017-03-01 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-16 | 7 |  |  | 2017-03-23 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-16 | 480 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 0 |  |  | 2017-03-16 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 0 |  |  | 2017-02-23 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 26 |  |  | 2017-04-11 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 18 |  |  | 2017-04-03 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 21 |  |  | 2017-04-06 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 13 |  |  | 2017-03-29 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 480 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 480 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 480 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-16 | 480 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-03-16 | 0 |  |  | 2017-03-16 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-03-16 | 0 |  |  | 2017-02-16 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-17 | 0 |  |  | 2017-03-02 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-17 | 479 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-17 | 13 |  |  | 2017-03-30 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-17 | 479 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-17 | 479 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-18 | 10 |  |  | 2017-03-28 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-19 | 477 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 65 |  |  | 2017-05-23 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 0 |  |  | 2017-02-21 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 17 |  |  | 2017-04-05 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 24 |  |  | 2017-04-12 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 59 |  |  | 2017-05-17 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 26 |  |  | 2017-04-14 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 477 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 477 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 477 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-19 | 477 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-03-19 | 263 |  |  | 2017-12-07 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-03-19 | 37 |  |  | 2017-04-25 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-20 | 476 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-20 | 476 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-20 | 476 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-21 | 0 |  |  | 2017-03-21 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-21 | 475 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-21 | 123 |  |  | 2017-07-22 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-03-21 | 114 |  |  | 2017-07-13 | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-21 | 0 |  |  | 2017-03-13 | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-03-21 | 0 |  |  | 2017-02-28 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-21 | 0 |  |  | 2017-02-28 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-03-21 | 0 |  |  | 2017-02-27 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-21 | 22 |  |  | 2017-04-12 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-21 | 27 |  |  | 2017-04-17 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-03-21 | 15 |  |  | 2017-04-05 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-03-21 | 475 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-03-21 | 35 |  |  | 2017-04-25 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-03-21 | 35 |  |  | 2017-04-25 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-22 | 0 |  |  | 2017-03-22 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-22 | 0 |  |  | 2017-02-17 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-23 | 0 |  |  | 2017-03-22 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 0 |  |  | 2017-02-22 | N |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 4 |  |  | 2017-03-27 | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 33 |  |  | 2017-04-25 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 9 |  |  | 2017-04-01 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 19 |  |  | 2017-04-11 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 25 |  |  | 2017-04-17 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-23 | 473 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Intake Form Completed |  |  | User | Henry, Robin |  |  | 2017-03-23 | 0 |  |  | 2017-03-23 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-03-23 | 34 |  |  | 2017-04-26 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-03-23 | 4 |  |  | 2017-03-27 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-24 | 472 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-03-24 | 472 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-24 | 472 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-24 | 25 |  |  | 2017-04-18 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-24 | 472 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-24 | 472 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-03-24 | 472 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-25 | 4 |  |  | 2017-03-29 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-25 | 0 |  |  | 2017-02-21 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-25 | 471 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-26 | 37 |  |  | 2017-05-02 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-03-26 | 0 |  |  | 2017-03-13 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-03-26 | 23 |  |  | 2017-04-18 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-03-26 | 57 |  |  | 2017-05-22 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-26 | 8 |  |  | 2017-04-03 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-27 | 74 |  |  | 2017-06-09 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-03-27 | 0 |  |  | 2017-03-27 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-27 | 0 |  |  | 2017-03-27 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-27 | 0 |  |  | 2017-03-27 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-27 | 3 |  |  | 2017-03-30 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-27 | 469 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-27 | 3 |  |  | 2017-03-30 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-27 | 469 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-27 | 469 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-03-27 | 469 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-03-28 | 0 |  |  | 2017-03-28 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO |  |  | 2017-03-28 | 16 |  |  | 2017-04-13 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-28 | 468 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-28 | 43 |  |  | 2017-05-10 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-03-28 | 0 |  |  | 2017-03-24 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-03-28 | 36 |  |  | 2017-05-03 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-28 | 13 |  |  | 2017-04-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-28 | 6 |  |  | 2017-04-03 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-28 | 468 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-03-28 | 55 |  |  | 2017-05-22 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-29 | 0 |  |  | 2017-03-13 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-29 | 0 |  |  | 2017-03-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-29 | 0 |  |  | 2017-03-29 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-29 | 467 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-03-29 | 467 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-03-29 | 280 |  |  | 2018-01-03 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-03-30 | 19 |  |  | 2017-04-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-03-30 | 0 |  |  | 2017-03-30 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-03-30 | 466 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-30 | 0 |  |  | 2017-03-09 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-03-30 | 0 |  |  | 2017-03-30 | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-30 | 0 |  |  | 2017-02-01 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-30 | 26 |  |  | 2017-04-25 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-03-30 | 466 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-03-30 | 466 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-03-30 | 466 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-03-31 | 465 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-31 | 0 |  |  | 2017-02-01 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-03-31 | 465 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-03-31 | 10 |  |  | 2017-04-10 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-03-31 | 465 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-03-31 | 28 |  |  | 2017-04-28 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-01 | 0 |  |  | 2017-02-07 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00122254 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-04-01 | 131 |  |  | 2017-08-10 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00122254 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-04-01 | 131 |  |  | 2017-08-10 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-02 | 463 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-04-02 | 463 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-04-02 | 463 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-04-02 | 463 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-04-02 | 98 |  |  | 2017-07-09 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-02 | 138 |  |  | 2017-08-18 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-04-02 | 26 |  |  | 2017-04-28 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-04-02 | 31 |  |  | 2017-05-03 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-03 | 0 |  |  | 2017-04-03 | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-03 | 0 |  |  | 2017-02-13 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-03 | 462 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-04-03 | 462 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-03 | 137 |  |  | 2017-08-18 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-04-03 | 7 |  |  | 2017-04-10 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-04 | 66 |  |  | 2017-06-09 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-04 | 0 |  |  | 2017-03-14 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-04 | 31 |  |  | 2017-05-05 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-04 | 31 |  |  | 2017-05-05 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-04 | 1 |  |  | 2017-04-05 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-04-04 | 461 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-04 | 461 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-04-04 | 0 |  |  | 2017-03-29 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-04 | 119 |  |  | 2017-08-01 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-04-04 | 161 |  |  | 2017-09-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-06 | 238 |  |  | 2017-11-30 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-06 | 36 |  |  | 2017-05-12 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-06 | 459 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-06 | 41 |  |  | 2017-05-17 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-06 | 0 |  |  | 2017-03-30 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-06 | 200 |  |  | 2017-10-23 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-07 | 0 |  |  | 2017-04-07 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-07 | 0 |  |  | 2017-04-07 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-07 | 0 |  |  | 2017-04-05 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-07 | 458 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-04-07 | 6 |  |  | 2017-04-13 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-07 | 458 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-04-07 | 458 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-07 | 0 |  |  | 2017-04-07 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-08 | 457 |  |  |  | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-08 | 457 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-08 | 2 |  |  | 2017-04-10 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-08 | 457 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-09 | 2 |  |  | 2017-04-11 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-09 | 456 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-04-09 | 53 |  |  | 2017-06-01 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-09 | 17 |  |  | 2017-04-26 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-09 | 17 |  |  | 2017-04-26 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-10 | 10 |  |  | 2017-04-20 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-10 | 455 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-10 | 455 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-04-10 | 455 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-04-11 | 454 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-11 | 0 |  |  | 2017-04-11 | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-11 | 0 |  |  | 2017-04-11 | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-04-11 | 0 |  |  | 2017-04-07 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-11 | 0 |  |  | 2017-04-06 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-04-11 | 454 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-04-11 | 86 |  |  | 2017-07-06 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-11 | 63 |  |  | 2017-06-13 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-11 | 150 |  |  | 2017-09-08 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-04-11 | 100 |  |  | 2017-07-20 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-11 | 454 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-04-11 | 59 |  |  | 2017-06-09 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-04-11 | 51 |  |  | 2017-06-01 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Assign to Analyst |  |  | Role | CRAO |  |  | 2017-04-12 | 0 |  |  | 2017-04-12 | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-12 | 1 |  |  | 2017-04-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-12 | 0 |  |  | 2017-04-12 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-12 | 0 |  |  | 2017-04-12 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-12 | 16 |  |  | 2017-04-28 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-12 | 453 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-12 | 453 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-12 | 453 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-12 | 453 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-12 | 1 |  |  | 2017-04-13 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-12 | 128 |  |  | 2017-08-18 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-04-13 | 60 |  |  | 2017-06-12 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-04-13 | 88 |  |  | 2017-07-10 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-13 | 127 |  |  | 2017-08-18 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-04-13 | 103 |  |  | 2017-07-25 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-14 | 0 |  |  | 2017-04-14 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-14 | 0 |  |  | 2017-04-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-14 | 451 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-14 | 5 |  |  | 2017-04-19 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-04-14 | 451 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-14 | 451 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-04-14 | 451 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-15 | 450 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-15 | 6 |  |  | 2017-04-21 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Complete Calendar ( ie. Flag as Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-15 | 6 |  |  | 2017-04-21 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-15 | 0 |  |  | 2017-04-13 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-15 | 6 |  |  | 2017-04-21 | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Complete Calendar ( ie. Flag as Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-15 | 6 |  |  | 2017-04-21 | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-15 | 6 |  |  | 2017-04-21 | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-16 | 262 |  |  | 2018-01-03 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-16 | 5 |  |  | 2017-04-21 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-17 | 0 |  |  | 2017-04-17 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-17 | 39 |  |  | 2017-05-26 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-17 | 23 |  |  | 2017-05-10 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-17 | 0 |  |  | 2017-04-17 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-17 | 448 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-04-17 | 0 |  |  | 2017-04-17 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-17 | 0 |  |  | 2017-03-27 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-04-17 | 4 |  |  | 2017-04-21 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-04-17 | 448 |  |  |  | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-17 | 0 |  |  | 2017-02-21 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-04-17 | 448 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Feasibility Approval Notice Received |  |  | User | Hess, Aaron |  |  | 2017-04-17 | 0 |  |  | 2017-04-17 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-18 | 0 |  |  | 2017-04-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-18 | 447 |  |  |  | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-04-18 | 447 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-18 | 447 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-04-18 | 1 |  |  | 2017-04-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Submit Calendar Build Request and Docs to Nimblify 04/18/17 |  |  | User | Hess, Aaron |  |  | 2017-04-18 | 0 |  |  | 2017-04-18 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2017-04-18 | 0 |  |  | 2017-04-18 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-18 | 231 |  |  | 2017-12-05 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Feasibility Approval Notice Received |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-18 | 1 |  |  | 2017-04-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-18 | 44 |  |  | 2017-06-01 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-19 | 43 |  |  | 2017-06-01 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-19 | 5 |  |  | 2017-04-24 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-19 | 0 |  |  | 2017-04-19 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-19 | 0 |  |  | 2017-04-19 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-04-19 | 0 |  |  | 2017-04-19 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-19 | 0 |  |  | 2017-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-04-19 | 446 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-04-19 | 0 |  |  | 2017-04-18 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2017-04-19 | 5 |  |  | 2017-04-24 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda |  |  | 2017-04-19 | 0 |  |  | 2017-04-18 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-19 | 68 |  |  | 2017-06-26 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-19 | 0 |  |  | 2017-04-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-19 | 0 |  |  | 2017-04-18 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-04-19 | 0 |  |  | 2017-04-17 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-20 | 445 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-20 | 11 |  |  | 2017-05-01 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-20 | 0 |  |  | 2017-04-20 | N |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-20 | 0 |  |  | 2017-04-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-20 | 68 |  |  | 2017-06-27 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-20 | 54 |  |  | 2017-06-13 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-04-20 | 14 |  |  | 2017-05-04 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-20 | 95 |  |  | 2017-07-24 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Nimblify Build is Complete & Ready for Import |  |  | Role | CRAO |  |  | 2017-04-21 | 4 |  |  | 2017-04-25 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Nimblify Build is Complete & Ready for Import |  |  | Role | CRAO |  |  | 2017-04-21 | 0 |  |  | 2017-04-21 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-04-21 | 0 |  |  | 2017-04-21 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-21 | 444 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-04-21 | 444 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda |  |  | 2017-04-21 | 0 |  |  | 2017-04-18 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-21 | 111 |  |  | 2017-08-10 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-21 | 5 |  |  | 2017-04-26 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-22 | 443 |  |  |  | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-22 | 443 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-22 | 443 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-22 | 16 |  |  | 2017-05-08 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-22 | 0 |  |  | 2017-04-20 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-22 | 0 |  |  | 2017-04-20 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-22 | 0 |  |  | 2017-04-19 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-22 | 3 |  |  | 2017-04-25 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-04-22 | 55 |  |  | 2017-06-16 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-23 | 0 |  |  | 2017-04-16 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-23 | 442 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-23 | 442 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-23 | 10 |  |  | 2017-05-03 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-23 | 10 |  |  | 2017-05-03 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-23 | 4 |  |  | 2017-04-27 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-23 | 4 |  |  | 2017-04-27 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-24 | 441 |  |  |  | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-24 | 179 |  |  | 2017-10-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-24 | 441 |  |  |  | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-24 | 441 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-04-24 | 154 |  |  | 2017-09-25 | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-24 | 148 |  |  | 2017-09-19 | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-24 | 441 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-04-24 | 441 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-04-24 | 441 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - MENEES-1 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-24 | 441 |  |  |  | N |  | MENEES-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-24 | 1 |  |  | 2017-04-25 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-24 | 1 |  |  | 2017-04-25 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-24 | 1 |  |  | 2017-04-25 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-04-24 | 64 |  |  | 2017-06-27 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-25 | 24 |  |  | 2017-05-19 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-25 | 0 |  |  | 2017-04-25 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-04-25 | 22 |  |  | 2017-05-17 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-04-25 | 0 |  |  | 2017-04-25 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-25 | 0 |  |  | 2017-04-17 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-25 | 440 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-25 | 0 |  |  | 2017-04-25 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Feasibility Approval Notice Received |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-25 | 0 |  |  | 2017-04-25 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-25 | 41 |  |  | 2017-06-05 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-04-25 | 48 |  |  | 2017-06-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-26 | 190 |  |  | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-04-26 | 0 |  |  | 2017-04-25 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-04-26 | 439 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-04-26 | 439 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-04-26 | 42 |  |  | 2017-06-07 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-26 | 48 |  |  | 2017-06-13 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-26 | 71 |  |  | 2017-07-06 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-04-26 | 61 |  |  | 2017-06-26 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-26 | 0 |  |  | 2017-04-25 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Complete SVS & Pricing List ( Built & Coded ) |  |  | Role | CRAO |  |  | 2017-04-27 | 0 |  |  | 2017-04-07 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-04-27 | 22 |  |  | 2017-05-19 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-27 | 438 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-27 | 5 |  |  | 2017-05-02 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-04-27 | 0 |  |  | 2017-04-27 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-04-27 | 13 |  |  | 2017-05-10 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-04-27 | 147 |  |  | 2017-09-21 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Request MCRU Budget |  |  | User | Oliver, Amy |  |  | 2017-04-27 | 13 |  |  | 2017-05-10 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-27 | 0 |  |  | 2017-04-25 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-27 | 0 |  |  | 2017-04-25 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-27 | 26 |  |  | 2017-05-23 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-27 | 26 |  |  | 2017-05-23 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-27 | 0 |  |  | 2017-04-25 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-27 | 0 |  |  | 2017-04-25 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Assign to Analyst |  |  | User | Zahs, Brian |  |  | 2017-04-27 | 54 |  |  | 2017-06-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-04-28 | 2 |  |  | 2017-04-30 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-04-28 | 2 |  |  | 2017-04-30 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-28 | 0 |  |  | 2017-04-28 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-04-28 | 0 |  |  | 2017-04-28 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-28 | 77 |  |  | 2017-07-14 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-04-28 | 21 |  |  | 2017-05-19 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-28 | 0 |  |  | 2017-04-28 | N |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-28 | 0 |  |  | 2017-04-28 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-28 | 0 |  |  | 2017-04-07 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-04-28 | 0 |  |  | 2017-04-28 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-04-28 | 0 |  |  | 2017-04-08 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2017-04-28 | 0 |  |  | 2017-04-28 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-04-28 | 5 |  |  | 2017-05-03 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-04-28 | 437 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-04-28 | 437 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-04-28 | 437 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda |  |  | 2017-04-28 | 0 |  |  | 2017-04-25 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2017-04-28 | 0 |  |  | 2017-03-16 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-28 | 46 |  |  | 2017-06-13 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-28 | 46 |  |  | 2017-06-13 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-28 | 0 |  |  | 2017-04-25 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-29 | 76 |  |  | 2017-07-14 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-04-29 | 131 |  |  | 2017-09-07 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-29 | 0 |  |  | 2017-04-18 | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-04-29 | 39 |  |  | 2017-06-07 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-04-29 | 436 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-04-29 | 436 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-04-29 | 436 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-29 | 0 |  |  | 2017-04-29 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-29 | 0 |  |  | 2017-04-26 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-29 | 0 |  |  | 2017-04-25 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-29 | 0 |  |  | 2017-04-25 | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-30 | 5 |  |  | 2017-05-05 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-04-30 | 5 |  |  | 2017-05-05 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-04-30 | 0 |  |  | 2017-04-30 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-04-30 | 46 |  |  | 2017-06-15 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-04-30 | 200 |  |  | 2017-11-16 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-04-30 | 295 |  |  | 2018-02-19 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-04-30 | 50 |  |  | 2017-06-19 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-04-30 | 61 |  |  | 2017-06-30 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-04-30 | 32 |  |  | 2017-06-01 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2017-04-30 | 1 |  |  | 2017-05-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-30 | 0 |  |  | 2017-04-30 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-30 | 0 |  |  | 2017-04-30 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-30 | 1 |  |  | 2017-05-01 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-30 | 0 |  |  | 2017-04-26 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-04-30 | 0 |  |  | 2017-04-28 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-04-30 | 117 |  |  | 2017-08-25 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-04-30 | 0 |  |  | 2017-04-28 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-04-30 | 0 |  |  | 2017-03-31 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-01 | 74 |  |  | 2017-07-14 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-01 | 220 |  |  | 2017-12-07 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-01 | 434 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-05-01 | 0 |  |  | 2017-05-01 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-05-01 | 1 |  |  | 2017-05-02 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-01 | 0 |  |  | 2017-05-01 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-05-01 | 4 |  |  | 2017-05-05 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-05-01 | 4 |  |  | 2017-05-05 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2017-05-01 | 31 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-05-01 | 31 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne |  |  | 2017-05-01 | 31 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2017-05-01 | 25 |  |  | 2017-05-26 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-02 | 433 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-02 | 433 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-02 | 0 |  |  | 2017-05-02 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-02 | 55 |  |  | 2017-06-26 | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-05-02 | 433 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-02 | 0 |  |  | 2017-04-16 | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-02 | 34 |  |  | 2017-06-05 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-05-02 | 34 |  |  | 2017-06-05 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-05-02 | 30 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-02 | 129 |  |  | 2017-09-08 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-02 | 48 |  |  | 2017-06-19 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-02 | 0 |  |  | 2017-05-01 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-02 | 0 |  |  | 2017-05-01 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-02 | 113 |  |  | 2017-08-23 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-03 | 23 |  |  | 2017-05-26 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-03 | 0 |  |  | 2017-04-17 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-05-03 | 15 |  |  | 2017-05-18 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-03 | 0 |  |  | 2017-04-12 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-03 | 0 |  |  | 2017-05-03 | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-03 | 0 |  |  | 2017-05-03 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-03 | 432 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-05-03 | 432 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-05-03 | 432 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-05-03 | 432 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-03 | 13 |  |  | 2017-05-16 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-03 | 112 |  |  | 2017-08-23 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-05-03 | 57 |  |  | 2017-06-29 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Other |  |  | User | Przykucki, Anne |  |  | 2017-05-03 | 29 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne |  |  | 2017-05-03 | 29 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne |  |  | 2017-05-03 | 29 |  |  | 2017-06-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2017-05-03 | 30 |  |  | 2017-06-02 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2017-05-03 | 30 |  |  | 2017-06-02 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-03 | 5 |  |  | 2017-05-08 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-03 | 5 |  |  | 2017-05-08 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-03 | 0 |  |  | 2017-05-03 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-03 | 0 |  |  | 2017-05-03 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-03 | 0 |  |  | 2017-05-03 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-04 | 0 |  |  | 2017-05-04 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-04 | 8 |  |  | 2017-05-12 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-04 | 6 |  |  | 2017-05-10 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-05-04 | 130 |  |  | 2017-09-11 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-05-04 | 48 |  |  | 2017-06-21 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Care Designations completed |  |  | User | VanderElzen, Liz |  |  | 2017-05-04 | 40 |  |  | 2017-06-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-04 | 33 |  |  | 2017-06-06 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-04 | 32 |  |  | 2017-06-05 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Complete Calendar ( ie. Ready for Financials ) |  |  | Role | CRAO |  |  | 2017-05-05 | 0 |  |  | 2017-05-05 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-05 | 0 |  |  | 2017-04-28 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-05 | 0 |  |  | 2017-04-28 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-05-05 | 0 |  |  | 2017-05-04 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-05 | 52 |  |  | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-05 | 41 |  |  | 2017-06-15 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-05-05 | 112 |  |  | 2017-08-25 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-05-05 | 0 |  |  | 2017-05-01 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 96-BESIRLI | CRAO Approval Issue & Documented |  |  | Role | CRAO |  |  | 2017-05-06 | 1 |  |  | 2017-05-07 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-06 | 208 |  |  | 2017-11-30 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-06 | 10 |  |  | 2017-05-16 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-06 | 10 |  |  | 2017-05-16 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-05-06 | 429 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-06 | 6 |  |  | 2017-05-12 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-06 | 6 |  |  | 2017-05-12 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-05-07 | 428 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-05-07 | 428 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-05-07 | 297 |  |  | 2018-02-28 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-08 | 339 |  |  | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-08 | 49 |  |  | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-08 | 0 |  |  | 2016-07-07 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Initial contact with sponsor |  |  | Role | CTSU Coordinator |  |  | 2017-05-08 | 0 |  |  | 2017-05-08 | N |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2017-05-08 | 25 |  |  | 2017-06-02 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-05-08 | 427 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-05-08 | 12 |  |  | 2017-05-20 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-05-08 | 8 |  |  | 2017-05-16 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-05-08 | 192 |  |  | 2017-11-16 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-08 | 427 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-08 | 427 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-05-08 | 39 |  |  | 2017-06-16 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-09 | 426 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-09 | 426 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-09 | 0 |  |  | 2017-05-09 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-05-09 | 28 |  |  | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-05-09 | 426 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-05-09 | 426 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-05-09 | 22 |  |  | 2017-05-31 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-05-09 | 13 |  |  | 2017-05-22 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-05-09 | 6 |  |  | 2017-05-15 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-05-10 | 0 |  |  | 2017-05-10 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-10 | 48 |  |  | 2017-06-27 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-10 | 61 |  |  | 2017-07-10 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-10 | 0 |  |  | 2017-04-25 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-10 | 75 |  |  | 2017-07-24 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-10 | 0 |  |  | 2017-05-10 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-05-10 | 0 |  |  | 2017-05-10 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-05-10 | 425 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-05-10 | 425 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2017-05-10 | 23 |  |  | 2017-06-02 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-10 | 26 |  |  | 2017-06-05 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-10 | 425 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-11 | 57 |  |  | 2017-07-07 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-11 | 0 |  |  | 2017-04-20 | N |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-05-11 | 56 |  |  | 2017-07-06 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-11 | 50 |  |  | 2017-06-30 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-11 | 0 |  |  | 2017-05-11 | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-11 | 424 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-11 | 424 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 97 |  |  | 2017-08-16 | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-05-11 | 424 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-05-11 | 0 |  |  | 2017-05-11 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-05-11 | 0 |  |  | 2017-05-11 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-11 | 33 |  |  | 2017-06-13 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-11 | 424 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-11 | 25 |  |  | 2017-06-05 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-11 | 21 |  |  | 2017-06-01 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-05-11 | 36 |  |  | 2017-06-16 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-11 | 68 |  |  | 2017-07-18 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-11 | 91 |  |  | 2017-08-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-12 | 0 |  |  | 2017-05-12 | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-12 | 0 |  |  | 2017-05-07 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-05-12 | 423 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-05-12 | 423 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-05-12 | 423 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-05-12 | 423 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-05-12 | 0 |  |  | 2017-05-11 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-05-12 | 0 |  |  | 2017-05-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-12 | 75 |  |  | 2017-07-26 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-12 | 90 |  |  | 2017-08-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-05-12 | 48 |  |  | 2017-06-29 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-05-12 | 32 |  |  | 2017-06-13 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-05-12 | 0 |  |  | 2017-03-31 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 2 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-05-12 | 80 |  |  | 2017-07-31 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-05-13 | 422 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-05-13 | 422 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-05-13 | 31 |  |  | 2017-06-13 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-05-13 | 88 |  |  | 2017-08-09 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-05-13 | 88 |  |  | 2017-08-09 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Budget Negotiations |  |  | User | VanderElzen, Liz |  |  | 2017-05-13 | 34 |  |  | 2017-06-16 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-14 | 30 |  |  | 2017-06-13 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-14 | 421 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-05-14 | 421 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-05-14 | 0 |  |  | 2017-04-17 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-05-14 | 57 |  |  | 2017-07-10 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-05-14 | 51 |  |  | 2017-07-04 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-05-14 | 5 |  |  | 2017-05-19 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-05-14 | 0 |  |  | 2017-05-14 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-15 | 399 |  |  | 2018-06-18 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-15 | 17 |  |  | 2017-06-01 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-05-15 | 0 |  |  | 2017-05-15 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-15 | 0 |  |  | 2017-05-15 | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-15 | 420 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-05-15 | 91 |  |  | 2017-08-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-15 | 108 |  |  | 2017-08-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-15 | 108 |  |  | 2017-08-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-05-15 | 86 |  |  | 2017-08-09 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-15 | 91 |  |  | 2017-08-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-05-15 | 91 |  |  | 2017-08-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-16 | 54 |  |  | 2017-07-09 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-16 | 419 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-16 | 419 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-16 | 419 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-16 | 0 |  |  | 2017-05-16 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-16 | 0 |  |  | 2017-04-24 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2017-05-16 | 0 |  |  | 2017-05-16 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-05-16 | 0 |  |  | 2017-05-14 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-05-16 | 77 |  |  | 2017-08-01 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-05-16 | 77 |  |  | 2017-08-01 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-05-16 | 0 |  |  | 2017-05-16 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-05-16 | 3 |  |  | 2017-05-19 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-17 | 397 |  |  | 2018-06-18 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-05-17 | 0 |  |  | 2017-04-24 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-05-17 | 2 |  |  | 2017-05-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-05-17 | 117 |  |  | 2017-09-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-05-17 | 90 |  |  | 2017-08-15 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-17 | 21 |  |  | 2017-06-07 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-18 | 417 |  |  |  | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-18 | 417 |  |  |  | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-18 | 0 |  |  | 2017-05-18 | N |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-18 | 0 |  |  | 2017-05-18 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-05-18 | 417 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-05-18 | 417 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-18 | 34 |  |  | 2017-06-21 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2017-05-18 | 7 |  |  | 2017-05-25 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Footnote Edits |  |  | Role | CRAO |  |  | 2017-05-19 | 17 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | Role | CRAO |  |  | 2017-05-19 | 17 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Visit Tolerance Edits |  |  | Role | CRAO |  |  | 2017-05-19 | 17 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-05-19 | 31 |  |  | 2017-06-19 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-19 | 59 |  |  | 2017-07-17 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-05-19 | 11 |  |  | 2017-05-30 | N |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-19 | 0 |  |  | 2017-05-01 | N |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-19 | 0 |  |  | 2017-05-03 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-05-19 | 416 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-05-19 | 416 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-05-19 | 180 |  |  | 2017-11-15 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-05-19 | 81 |  |  | 2017-08-08 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2017-05-19 | 17 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2017-05-19 | 0 |  |  | 2017-05-19 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | Role | CRAO |  |  | 2017-05-20 | 16 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-05-20 | 0 |  |  | 2017-05-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-05-20 | 0 |  |  | 2017-05-19 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Other |  |  | Role | CRAO |  |  | 2017-05-21 | 15 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Update RSH Source in MBECT |  |  | Role | CRAO |  |  | 2017-05-21 | 15 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-21 | 43 |  |  | 2017-07-03 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-21 | 5 |  |  | 2017-05-26 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-05-21 | 1 |  |  | 2017-05-22 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-05-21 | 414 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-05-21 | 1 |  |  | 2017-05-22 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-05-21 | 12 |  |  | 2017-06-02 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-05-21 | 15 |  |  | 2017-06-05 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-05-21 | 12 |  |  | 2017-06-02 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-05-21 | 79 |  |  | 2017-08-08 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-05-22 | 46 |  |  | 2017-07-07 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-22 | 0 |  |  | 2017-05-22 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-05-22 | 2 |  |  | 2017-05-24 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-05-22 | 413 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-05-22 | 177 |  |  | 2017-11-15 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Complete MCA / QCT |  |  | User | LaVasseur, Kristen |  |  | 2017-05-22 | 0 |  |  | 2017-05-22 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-05-22 | 17 |  |  | 2017-06-08 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-22 | 413 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-22 | 66 |  |  | 2017-07-27 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-05-22 | 0 |  |  | 2017-05-22 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-05-22 | 1 |  |  | 2017-05-23 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-05-22 | 18 |  |  | 2017-06-09 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-23 | 86 |  |  | 2017-08-17 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-23 | 66 |  |  | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-05-23 | 412 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-05-23 | 412 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-05-23 | 412 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-05-23 | 412 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-23 | 412 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-23 | 412 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-05-23 | 57 |  |  | 2017-07-19 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-23 | 87 |  |  | 2017-08-18 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-05-23 | 412 |  |  |  | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-23 | 9 |  |  | 2017-06-01 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-24 | 0 |  |  | 2017-05-24 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-24 | 411 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-24 | 2 |  |  | 2017-05-26 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-05-24 | 0 |  |  | 2017-05-24 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-05-24 | 411 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-24 | 0 |  |  | 2017-05-09 | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-05-24 | 0 |  |  | 2017-05-22 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-05-24 | 8 |  |  | 2017-06-01 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-05-24 | 411 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-05-24 | 176 |  |  | 2017-11-16 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-05-24 | 19 |  |  | 2017-06-12 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Budget Negotiations |  |  | User | VanderElzen, Liz |  |  | 2017-05-24 | 15 |  |  | 2017-06-08 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-05-24 | 15 |  |  | 2017-06-08 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-05-24 | 16 |  |  | 2017-06-09 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-05-24 | 16 |  |  | 2017-06-09 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-05-25 | 410 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-05-25 | 67 |  |  | 2017-07-31 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-05-25 | 67 |  |  | 2017-07-31 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-26 | 409 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-26 | 0 |  |  | 2017-05-26 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-26 | 140 |  |  | 2017-10-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-05-26 | 0 |  |  | 2017-05-26 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-26 | 0 |  |  | 2017-05-26 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-05-26 | 409 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-05-26 | 409 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-05-26 | 409 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-05-26 | 409 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-05-26 | 0 |  |  | 2017-05-26 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Feasibility Approval Notice Received |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-26 | 0 |  |  | 2017-05-26 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-27 | 5 |  |  | 2017-06-01 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-27 | 408 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-05-27 | 408 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-05-27 | 408 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-05-27 | 79 |  |  | 2017-08-14 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-05-27 | 53 |  |  | 2017-07-19 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-05-27 | 20 |  |  | 2017-06-16 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Complete Calendar and Document Approval |  |  | Role | CRAO |  |  | 2017-05-28 | 8 |  |  | 2017-06-05 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-28 | 407 |  |  |  | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-28 | 199 |  |  | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Planning Meeting Request Sent |  |  | User | Huffman, Kate |  |  | 2017-05-28 | 2 |  |  | 2017-05-30 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-05-28 | 88 |  |  | 2017-08-24 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-05-28 | 3 |  |  | 2017-05-31 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Request MCRU Budget |  |  | User | VanderElzen, Liz |  |  | 2017-05-28 | 33 |  |  | 2017-06-30 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Request Research Pharmacy Budget |  |  | User | VanderElzen, Liz |  |  | 2017-05-28 | 3 |  |  | 2017-05-31 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-29 | 8 |  |  | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-05-29 | 406 |  |  |  | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-05-29 | 11 |  |  | 2017-06-09 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-05-29 | 4 |  |  | 2017-06-02 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-29 | 2 |  |  | 2017-05-31 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-05-29 | 32 |  |  | 2017-06-30 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-05-30 | 405 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-05-30 | 0 |  |  | 2017-05-18 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-30 | 0 |  |  | 2017-05-09 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-05-30 | 405 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-05-30 | 405 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-05-30 | 0 |  |  | 2017-05-02 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Assign to Analyst |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-30 | 1 |  |  | 2017-05-31 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-05-30 | 87 |  |  | 2017-08-25 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-05-30 | 0 |  |  | 2017-05-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-05-30 | 62 |  |  | 2017-07-31 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-05-30 | 27 |  |  | 2017-06-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-05-31 | 404 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-05-31 | 0 |  |  | 2017-05-31 | N |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-05-31 | 14 |  |  | 2017-06-14 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-31 | 2 |  |  | 2017-06-02 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-05-31 | 7 |  |  | 2017-06-07 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-05-31 | 47 |  |  | 2017-07-17 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-05-31 | 27 |  |  | 2017-06-27 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-05-31 | 75 |  |  | 2017-08-14 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Budget Finalized |  |  | Role | CTSU Administrator |  |  | 2017-06-01 | 0 |  |  | 2017-06-01 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Contract Executed |  |  | Role | CTSU Administrator |  |  | 2017-06-01 | 39 |  |  | 2017-07-10 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-06-01 | 403 |  |  |  | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-06-01 | 0 |  |  | 2017-02-13 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2017-06-01 | 4 |  |  | 2017-06-05 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-02 | 402 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 402 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 402 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 402 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Intake Form Completed |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 0 |  |  | 2017-05-30 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 402 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-06-02 | 402 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-06-02 | 11 |  |  | 2017-06-13 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-02 | 4 |  |  | 2017-06-06 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Assign to Analyst |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-02 | 28 |  |  | 2017-06-30 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-06-02 | 21 |  |  | 2017-06-23 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-06-02 | 21 |  |  | 2017-06-23 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-06-02 | 48 |  |  | 2017-07-20 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-06-02 | 48 |  |  | 2017-07-20 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2017-06-02 | 0 |  |  | 2017-06-02 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-03 | 401 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-06-03 | 44 |  |  | 2017-07-17 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | Assign to Analyst |  |  | User | LaVasseur, Kristen |  |  | 2017-06-03 | 6 |  |  | 2017-06-09 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-06-03 | 95 |  |  | 2017-09-06 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-04 | 0 |  |  | 2017-06-02 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-04 | 0 |  |  | 2017-06-02 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-04 | 0 |  |  | 2017-06-04 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-06-04 | 33 |  |  | 2017-07-07 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-06-04 | 400 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-06-04 | 400 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-06-04 | 64 |  |  | 2017-08-07 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-06-04 | 1 |  |  | 2017-06-05 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-06-04 | 3 |  |  | 2017-06-07 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-06-04 | 1 |  |  | 2017-06-05 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-04 | 32 |  |  | 2017-07-06 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-04 | 50 |  |  | 2017-07-24 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-06-04 | 95 |  |  | 2017-09-07 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-05 | 2 |  |  | 2017-06-07 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-05 | 399 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-06-05 | 142 |  |  | 2017-10-25 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-05 | 0 |  |  | 2017-06-05 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-05 | 0 |  |  | 2017-06-05 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-05 | 0 |  |  | 2017-06-05 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-05 | 0 |  |  | 2017-06-05 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-05 | 0 |  |  | 2017-06-01 | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-05 | 0 |  |  | 2017-05-15 | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-05 | 0 |  |  | 2017-06-05 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-05 | 0 |  |  | 2017-03-30 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-06-05 | 7 |  |  | 2017-06-12 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-06-05 | 42 |  |  | 2017-07-17 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-06-05 | 9 |  |  | 2017-06-14 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-05 | 11 |  |  | 2017-06-16 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-05 | 11 |  |  | 2017-06-16 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-05 | 15 |  |  | 2017-06-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-06-05 | 108 |  |  | 2017-09-21 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-05 | 0 |  |  | 2017-06-05 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-05 | 11 |  |  | 2017-06-16 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Billing Calendar Received |  |  | User | VanderElzen, Liz |  |  | 2017-06-05 | 15 |  |  | 2017-06-20 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-06-05 | 1 |  |  | 2017-06-06 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-06-05 | 1 |  |  | 2017-06-06 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-06-05 | 4 |  |  | 2017-06-09 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-06 | 1 |  |  | 2017-06-07 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-06 | 1 |  |  | 2017-06-07 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-06 | 0 |  |  | 2017-06-06 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-06 | 23 |  |  | 2017-06-29 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-06 | 0 |  |  | 2017-06-06 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-06 | 0 |  |  | 2017-05-26 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-06 | 0 |  |  | 2017-05-16 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-06-06 | 398 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-06 | 0 |  |  | 2017-06-06 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-07 | 0 |  |  | 2017-06-05 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-06-07 | 5 |  |  | 2017-06-12 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Final Budget |  |  | User | Henry, Robin |  |  | 2017-06-07 | 190 |  |  | 2017-12-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Assign to Analyst |  |  | User | Hess, Aaron |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-07 | 13 |  |  | 2017-06-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-07 | 15 |  |  | 2017-06-22 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-06-07 | 96 |  |  | 2017-09-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-06-07 | 2 |  |  | 2017-06-09 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-07 | 13 |  |  | 2017-06-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-07 | 13 |  |  | 2017-06-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-06-07 | 16 |  |  | 2017-06-23 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-06-07 | 1 |  |  | 2017-06-08 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Planning Meeting Completed |  |  | User | VanderElzen, Liz |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Yunk, Jason |  |  | 2017-06-07 | 0 |  |  | 2017-06-07 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-06-07 | 2 |  |  | 2017-06-09 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-06-07 | 2 |  |  | 2017-06-09 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Project Award Notice (PAN) Received |  |  | Role | CTSU Administrator |  |  | 2017-06-08 | 134 |  |  | 2017-10-20 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 0 |  |  | 2017-06-06 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 7 |  |  | 2017-06-15 | N |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 7 |  |  | 2017-06-15 | N |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 0 |  |  | 2017-06-07 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-08 | 0 |  |  | 2017-06-06 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-06-08 | 396 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | Make Update(s) |  |  | User | LaVasseur, Kristen |  |  | 2017-06-08 | 1 |  |  | 2017-06-09 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | Re-Complete Calendar |  |  | User | LaVasseur, Kristen |  |  | 2017-06-08 | 1 |  |  | 2017-06-09 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-06-08 | 0 |  |  | 2017-06-06 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-06-08 | 0 |  |  | 2017-06-06 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-08 | 0 |  |  | 2017-06-06 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-08 | 0 |  |  | 2017-06-06 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Planning Meeting Completed |  |  | User | VanderElzen, Liz |  |  | 2017-06-08 | 0 |  |  | 2017-06-08 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-09 | 0 |  |  | 2017-06-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Administrator |  |  | 2017-06-09 | 42 |  |  | 2017-07-21 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-09 | 73 |  |  | 2017-08-21 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-09 | 0 |  |  | 2017-06-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-09 | 0 |  |  | 2017-06-09 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-09 | 0 |  |  | 2017-06-09 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-09 | 5 |  |  | 2017-06-14 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-09 | 4 |  |  | 2017-06-13 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-09 | 0 |  |  | 2017-06-09 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-06-09 | 395 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | PAF routed |  |  | User | Henry, Robin |  |  | 2017-06-09 | 188 |  |  | 2017-12-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-06-09 | 45 |  |  | 2017-07-24 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-06-09 | 20 |  |  | 2017-06-29 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2017-06-09 | 11 |  |  | 2017-06-20 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-09 | 21 |  |  | 2017-06-30 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-06-09 | 95 |  |  | 2017-09-12 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-06-09 | 0 |  |  | 2017-06-08 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 132 |  |  | 2017-10-20 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 135 |  |  | 2017-10-23 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | MiChart Verifications |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 132 |  |  | 2017-10-20 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Provisions for Support and Services Finalized |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 41 |  |  | 2017-07-21 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 135 |  |  | 2017-10-23 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Study Files Established |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 41 |  |  | 2017-07-21 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-10 | 394 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | Other Personnel Notified |  |  | Role | CTSU Coordinator |  |  | 2017-06-10 | 41 |  |  | 2017-07-21 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-10 | 0 |  |  | 2017-06-09 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Complete SVS & Pricing List ( Built & Coded ) |  |  | Role | CTSU Finance |  |  | 2017-06-10 | 0 |  |  | 2017-06-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-06-10 | 394 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-06-10 | 394 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-06-10 | 394 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-06-10 | 2 |  |  | 2017-06-12 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2017-06-10 | 11 |  |  | 2017-06-21 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2017-06-10 | 0 |  |  | 2017-06-08 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-10 | 0 |  |  | 2017-06-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-10 | 4 |  |  | 2017-06-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-10 | 0 |  |  | 2017-06-09 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-06-10 | 2 |  |  | 2017-06-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-06-10 | 0 |  |  | 2017-06-09 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-06-10 | 0 |  |  | 2017-06-08 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-06-10 | 6 |  |  | 2017-06-16 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-11 | 5 |  |  | 2017-06-16 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-06-11 | 0 |  |  | 2017-04-25 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-06-11 | 1 |  |  | 2017-06-12 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2017-06-11 | 9 |  |  | 2017-06-20 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2017-06-11 | 10 |  |  | 2017-06-21 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-06-11 | 89 |  |  | 2017-09-08 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2017-06-11 | 0 |  |  | 2017-06-09 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2017-06-11 | 0 |  |  | 2017-06-09 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-11 | 0 |  |  | 2017-06-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-06-11 | 25 |  |  | 2017-07-06 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-12 | 392 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-12 | 0 |  |  | 2017-05-12 | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-06-12 | 392 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-06-12 | 0 |  |  | 2017-06-12 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-06-12 | 74 |  |  | 2017-08-25 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-06-12 | 10 |  |  | 2017-06-22 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-06-12 | 0 |  |  | 2017-06-09 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-06-12 | 17 |  |  | 2017-06-29 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-12 | 134 |  |  | 2017-10-24 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-06-12 | 0 |  |  | 2017-06-09 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-12 | 2 |  |  | 2017-06-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-12 | 2 |  |  | 2017-06-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Care Designations completed |  |  | User | VanderElzen, Liz |  |  | 2017-06-12 | 18 |  |  | 2017-06-30 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-06-12 | 4 |  |  | 2017-06-16 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-06-12 | 4 |  |  | 2017-06-16 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-06-13 | 391 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-06-13 | 9 |  |  | 2017-06-22 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-13 | 174 |  |  | 2017-12-04 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Other |  |  | User | Przykucki, Anne |  |  | 2017-06-13 | 0 |  |  | 2017-06-09 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2017-06-13 | 0 |  |  | 2017-06-09 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-13 | 0 |  |  | 2017-06-13 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-13 | 0 |  |  | 2017-06-13 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Complete SVS & Pricing List ( Built & Coded ) |  |  | Role | CRAO |  |  | 2017-06-14 | 0 |  |  | 2017-06-14 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-14 | 390 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-14 | 26 |  |  | 2017-07-10 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-06-14 | 390 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-06-14 | 390 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-06-14 | 390 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-06-14 | 390 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-06-14 | 23 |  |  | 2017-07-07 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-06-14 | 75 |  |  | 2017-08-28 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-06-14 | 5 |  |  | 2017-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-06-14 | 1 |  |  | 2017-06-15 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-06-14 | 15 |  |  | 2017-06-29 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-06-14 | 8 |  |  | 2017-06-22 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-06-14 | 37 |  |  | 2017-07-21 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-06-14 | 16 |  |  | 2017-06-30 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-06-14 | 29 |  |  | 2017-07-13 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-14 | 0 |  |  | 2017-06-13 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-06-14 | 37 |  |  | 2017-07-21 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-06-14 | 0 |  |  | 2017-06-08 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-06-14 | 0 |  |  | 2017-06-14 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-06-14 | 0 |  |  | 2017-06-14 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-06-14 | 8 |  |  | 2017-06-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-06-15 | 389 |  |  |  | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-15 | 0 |  |  | 2017-06-15 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-06-15 | 6 |  |  | 2017-06-21 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-06-15 | 11 |  |  | 2017-06-26 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-06-15 | 11 |  |  | 2017-06-26 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-15 | 389 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-06-15 | 6 |  |  | 2017-06-21 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2017-06-15 | 0 |  |  | 2017-06-14 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2017-06-15 | 0 |  |  | 2017-06-14 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2017-06-15 | 15 |  |  | 2017-06-30 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-06-15 | 1 |  |  | 2017-06-16 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-06-15 | 96 |  |  | 2017-09-19 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-06-15 | 39 |  |  | 2017-07-24 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-06-15 | 33 |  |  | 2017-07-18 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-16 | 0 |  |  | 2017-06-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Contract Executed |  |  | Role | CTSU Coordinator |  |  | 2017-06-16 | 0 |  |  | 2017-06-16 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-16 | 0 |  |  | 2017-06-16 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-06-16 | 0 |  |  | 2017-06-15 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-06-16 | 0 |  |  | 2017-06-15 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-06-16 | 4 |  |  | 2017-06-20 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2017-06-16 | 12 |  |  | 2017-06-28 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-06-16 | 11 |  |  | 2017-06-27 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-06-16 | 13 |  |  | 2017-06-29 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-16 | 33 |  |  | 2017-07-19 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-06-16 | 4 |  |  | 2017-06-20 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-16 | 19 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-16 | 54 |  |  | 2017-08-09 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-16 | 54 |  |  | 2017-08-09 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Billing Calendar Received |  |  | User | VanderElzen, Liz |  |  | 2017-06-16 | 0 |  |  | 2017-06-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-06-16 | 40 |  |  | 2017-07-26 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-06-16 | 40 |  |  | 2017-07-26 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-06-17 | 387 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2017-06-17 | 13 |  |  | 2017-06-30 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2017-06-17 | 46 |  |  | 2017-08-02 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-17 | 18 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-17 | 18 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-17 | 18 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-17 | 18 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-06-17 | 38 |  |  | 2017-07-25 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-06-17 | 37 |  |  | 2017-07-24 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-06-18 | 386 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-06-18 | 386 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-06-18 | 0 |  |  | 2017-05-02 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-06-18 | 33 |  |  | 2017-07-21 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-06-18 | 8 |  |  | 2017-06-26 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-06-18 | 31 |  |  | 2017-07-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-18 | 51 |  |  | 2017-08-08 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-18 | 17 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-06-18 | 59 |  |  | 2017-08-16 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-06-18 | 3 |  |  | 2017-06-21 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-19 | 0 |  |  | 2017-06-19 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-06-19 | 16 |  |  | 2017-07-05 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-06-19 | 7 |  |  | 2017-06-26 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-06-19 | 43 |  |  | 2017-08-01 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-06-19 | 4 |  |  | 2017-06-23 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-06-19 | 0 |  |  | 2017-06-13 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-06-19 | 316 |  |  | 2018-05-01 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-19 | 16 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-19 | 16 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Request Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-19 | 16 |  |  | 2017-07-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-06-19 | 45 |  |  | 2017-08-03 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-06-20 | 384 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-06-20 | 384 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-20 | 55 |  |  | 2017-08-14 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-06-20 | 55 |  |  | 2017-08-14 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-06-20 | 384 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-06-20 | 6 |  |  | 2017-06-26 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2017-06-20 | 0 |  |  | 2017-06-09 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Budget Negotiations |  |  | User | VanderElzen, Liz |  |  | 2017-06-20 | 1 |  |  | 2017-06-21 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-21 | 27 |  |  | 2017-07-18 | N |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-21 | 27 |  |  | 2017-07-18 | N |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-21 | 0 |  |  | 2017-06-21 | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Budget Finalized |  |  | Role | CTSU Finance |  |  | 2017-06-21 | 0 |  |  | 2017-06-21 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-06-21 | 383 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-06-21 | 314 |  |  | 2018-05-01 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-06-21 | 127 |  |  | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-21 | 127 |  |  | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-21 | 41 |  |  | 2017-08-01 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-21 | 41 |  |  | 2017-08-01 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-06-21 | 47 |  |  | 2017-08-07 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-06-21 | 47 |  |  | 2017-08-07 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-22 | 0 |  |  | 2017-06-16 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-06-22 | 21 |  |  | 2017-07-13 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-06-22 | 382 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-06-22 | 382 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-06-22 | 0 |  |  | 2017-06-20 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-06-22 | 13 |  |  | 2017-07-05 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Assign to Analyst |  |  | User | Hess, Aaron |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Feasibility Approval Notice Received |  |  | User | Hess, Aaron |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-06-22 | 0 |  |  | 2017-06-22 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-22 | 70 |  |  | 2017-08-31 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-22 | 53 |  |  | 2017-08-14 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-06-22 | 32 |  |  | 2017-07-24 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-06-22 | 42 |  |  | 2017-08-03 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-06-22 | 53 |  |  | 2017-08-14 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-22 | 21 |  |  | 2017-07-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-23 | 381 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-23 | 0 |  |  | 2017-06-23 | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-23 | 118 |  |  | 2017-10-19 | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-23 | 0 |  |  | 2017-06-21 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-06-23 | 14 |  |  | 2017-07-07 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-06-23 | 19 |  |  | 2017-07-12 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-23 | 39 |  |  | 2017-08-01 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-23 | 220 |  |  | 2018-01-29 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-23 | 76 |  |  | 2017-09-07 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-06-23 | 356 |  |  | 2018-06-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-06-23 | 41 |  |  | 2017-08-03 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-06-23 | 55 |  |  | 2017-08-17 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-06-23 | 54 |  |  | 2017-08-16 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Care Designations completed |  |  | User | VanderElzen, Liz |  |  | 2017-06-23 | 39 |  |  | 2017-08-01 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-06-24 | 0 |  |  | 2017-06-19 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-06-24 | 380 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-06-24 | 6 |  |  | 2017-06-30 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-06-24 | 45 |  |  | 2017-08-08 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-06-24 | 0 |  |  | 2017-05-31 | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-24 | 23 |  |  | 2017-07-17 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-24 | 23 |  |  | 2017-07-17 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-06-24 | 62 |  |  | 2017-08-25 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-06-24 | 4 |  |  | 2017-06-28 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2017-06-24 | 37 |  |  | 2017-07-31 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-25 | 0 |  |  | 2017-06-20 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-06-25 | 0 |  |  | 2017-05-02 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-06-25 | 17 |  |  | 2017-07-12 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2017-06-25 | 5 |  |  | 2017-06-30 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-25 | 11 |  |  | 2017-07-06 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-25 | 11 |  |  | 2017-07-06 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-25 | 22 |  |  | 2017-07-17 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-25 | 102 |  |  | 2017-10-05 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-25 | 102 |  |  | 2017-10-05 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-06-25 | 86 |  |  | 2017-09-19 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-06-25 | 22 |  |  | 2017-07-17 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-06-25 | 26 |  |  | 2017-07-21 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-26 | 28 |  |  | 2017-07-24 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-26 | 0 |  |  | 2017-06-26 | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-26 | 3 |  |  | 2017-06-29 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-06-26 | 28 |  |  | 2017-07-24 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-06-26 | 378 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-06-26 | 378 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-06-26 | 378 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-06-26 | 28 |  |  | 2017-07-24 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-06-26 | 31 |  |  | 2017-07-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-06-26 | 22 |  |  | 2017-07-18 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-06-26 | 44 |  |  | 2017-08-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-06-26 | 10 |  |  | 2017-07-06 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2017-06-26 | 44 |  |  | 2017-08-09 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-26 | 44 |  |  | 2017-08-09 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-06-26 | 56 |  |  | 2017-08-21 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-06-26 | 63 |  |  | 2017-08-28 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-06-26 | 63 |  |  | 2017-08-28 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-06-27 | 64 |  |  | 2017-08-30 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2017-06-27 | 9 |  |  | 2017-07-06 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2017-06-27 | 21 |  |  | 2017-07-18 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-06-27 | 9 |  |  | 2017-07-06 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-06-27 | 44 |  |  | 2017-08-10 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-06-27 | 377 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-06-27 | 37 |  |  | 2017-08-03 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-27 | 20 |  |  | 2017-07-17 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-06-27 | 20 |  |  | 2017-07-17 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-06-27 | 106 |  |  | 2017-10-11 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-06-27 | 28 |  |  | 2017-07-25 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-06-27 | 28 |  |  | 2017-07-25 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-28 | 13 |  |  | 2017-07-11 | N |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-28 | 13 |  |  | 2017-07-11 | N |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-06-28 | 0 |  |  | 2017-05-02 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-06-28 | 27 |  |  | 2017-07-25 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-06-28 | 29 |  |  | 2017-07-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Final Budget |  |  | User | Henry, Robin |  |  | 2017-06-28 | 33 |  |  | 2017-07-31 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-28 | 48 |  |  | 2017-08-15 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-06-28 | 47 |  |  | 2017-08-14 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-06-28 | 63 |  |  | 2017-08-30 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-06-28 | 69 |  |  | 2017-09-05 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-29 | 0 |  |  | 2017-06-29 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-29 | 375 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator |  |  | 2017-06-29 | 0 |  |  | 2017-06-29 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-29 | 15 |  |  | 2017-07-14 | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-29 | 15 |  |  | 2017-07-14 | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-06-29 | 375 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-06-29 | 7 |  |  | 2017-07-06 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-06-29 | 40 |  |  | 2017-08-08 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-06-29 | 57 |  |  | 2017-08-25 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | OnCore Budget Build |  |  | User | Oliver, Amy |  |  | 2017-06-29 | 375 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-06-29 | 28 |  |  | 2017-07-27 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-06-30 | 112 |  |  | 2017-10-20 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-06-30 | 374 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-06-30 | 83 |  |  | 2017-09-21 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-30 | 0 |  |  | 2017-06-30 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator |  |  | 2017-06-30 | 11 |  |  | 2017-07-11 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-06-30 | 130 |  |  | 2017-11-07 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-06-30 | 0 |  |  | 2017-06-14 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-06-30 | 0 |  |  | 2017-06-13 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2017-06-30 | 0 |  |  | 2017-06-30 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-06-30 | 0 |  |  | 2017-05-03 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | PAF routed |  |  | User | Henry, Robin |  |  | 2017-06-30 | 32 |  |  | 2017-08-01 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-06-30 | 0 |  |  | 2017-06-30 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-06-30 | 35 |  |  | 2017-08-04 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-06-30 | 374 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-01 | 111 |  |  | 2017-10-20 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-01 | 5 |  |  | 2017-07-06 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-01 | 5 |  |  | 2017-07-06 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-01 | 4 |  |  | 2017-07-05 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-07-01 | 6 |  |  | 2017-07-07 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-07-01 | 373 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-07-01 | 26 |  |  | 2017-07-27 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-02 | 166 |  |  | 2017-12-15 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-02 | 372 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-07-02 | 372 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-07-02 | 372 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-07-02 | 372 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-07-02 | 16 |  |  | 2017-07-18 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-07-02 | 10 |  |  | 2017-07-12 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-07-02 | 15 |  |  | 2017-07-17 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-07-02 | 33 |  |  | 2017-08-04 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-02 | 3 |  |  | 2017-07-05 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Billing Calendar Received |  |  | User | VanderElzen, Liz |  |  | 2017-07-02 | 23 |  |  | 2017-07-25 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-03 | 371 |  |  |  | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-03 | 0 |  |  | 2017-07-03 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-03 | 371 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-03 | 0 |  |  | 2017-07-03 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-03 | 0 |  |  | 2017-07-03 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | MiChart Verifications |  |  | Role | CTSU Coordinator |  |  | 2017-07-03 | 0 |  |  | 2017-07-03 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-07-03 | 371 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-07-03 | 32 |  |  | 2017-08-04 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Feasibility Approval Notice Received |  |  | User | Hess, Aaron |  |  | 2017-07-03 | 0 |  |  | 2017-07-03 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-07-03 | 20 |  |  | 2017-07-23 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-03 | 4 |  |  | 2017-07-07 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-03 | 4 |  |  | 2017-07-07 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-07-04 | 114 |  |  | 2017-10-26 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-07-04 | 35 |  |  | 2017-08-08 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-07-04 | 370 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-07-04 | 370 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-07-04 | 71 |  |  | 2017-09-13 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-07-04 | 28 |  |  | 2017-08-01 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-07-04 | 34 |  |  | 2017-08-07 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-07-04 | 370 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-04 | 3 |  |  | 2017-07-07 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-07-04 | 14 |  |  | 2017-07-18 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-05 | 369 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-05 | 0 |  |  | 2017-07-05 | N |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-05 | 0 |  |  | 2017-07-05 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-05 | 0 |  |  | 2017-07-05 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-05 | 1 |  |  | 2017-07-06 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-05 | 5 |  |  | 2017-07-10 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Request MCRU Budget |  |  | User | Henry, Robin |  |  | 2017-07-05 | 202 |  |  | 2018-01-23 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-05 | 5 |  |  | 2017-07-10 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-07-05 | 1 |  |  | 2017-07-06 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-05 | 78 |  |  | 2017-09-21 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-07-05 | 369 |  |  |  | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-05 | 2 |  |  | 2017-07-07 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Request Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-05 | 2 |  |  | 2017-07-07 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-05 | 1 |  |  | 2017-07-06 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-07-05 | 43 |  |  | 2017-08-17 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian |  |  | 2017-07-05 | 0 |  |  | 2017-07-05 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-06 | 368 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-06 | 0 |  |  | 2017-06-27 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-07-06 | 0 |  |  | 2017-06-15 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-06 | 14 |  |  | 2017-07-20 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-07-06 | 368 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-07-06 | 368 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-07-06 | 27 |  |  | 2017-08-02 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-07-06 | 37 |  |  | 2017-08-12 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-07-06 | 368 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-07-06 | 17 |  |  | 2017-07-23 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-06 | 43 |  |  | 2017-08-18 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-07-06 | 0 |  |  | 2017-07-06 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-07-06 | 19 |  |  | 2017-07-25 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Planning Meeting Completed |  |  | User | VanderElzen, Liz |  |  | 2017-07-06 | 0 |  |  | 2017-06-26 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-07-06 | 34 |  |  | 2017-08-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-07-06 | 34 |  |  | 2017-08-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-07-06 | 43 |  |  | 2017-08-18 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-07-06 | 43 |  |  | 2017-08-18 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-07 | 95 |  |  | 2017-10-10 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-07 | 0 |  |  | 2017-06-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-07-07 | 367 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-07-07 | 75 |  |  | 2017-09-20 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-07-07 | 166 |  |  | 2017-12-20 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-07-07 | 6 |  |  | 2017-07-13 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-07-07 | 220 |  |  | 2018-02-12 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-07-07 | 0 |  |  | 2017-07-07 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-07-07 | 0 |  |  | 2017-07-06 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-08 | 94 |  |  | 2017-10-10 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-08 | 366 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-07-08 | 366 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-07-08 | 366 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-07-08 | 366 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-07-08 | 366 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-07-08 | 48 |  |  | 2017-08-25 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-07-08 | 37 |  |  | 2017-08-14 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron |  |  | 2017-07-08 | 54 |  |  | 2017-08-31 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-08 | 201 |  |  | 2018-01-25 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-08 | 45 |  |  | 2017-08-22 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-08 | 219 |  |  | 2018-02-12 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-07-08 | 60 |  |  | 2017-09-06 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-08 | 0 |  |  | 2017-07-07 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-08 | 0 |  |  | 2017-07-07 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Nimblify Build is Complete & Ready for Import |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-08 | 5 |  |  | 2017-07-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-07-08 | 38 |  |  | 2017-08-15 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-09 | 79 |  |  | 2017-09-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-09 | 93 |  |  | 2017-10-10 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-07-09 | 0 |  |  | 2017-07-07 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-07-09 | 16 |  |  | 2017-07-25 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-07-09 | 122 |  |  | 2017-11-08 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-07-09 | 365 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Care Designations completed |  |  | User | VanderElzen, Liz |  |  | 2017-07-09 | 25 |  |  | 2017-08-03 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-10 | 122 |  |  | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-10 | 364 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-10 | 0 |  |  | 2017-07-10 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-07-10 | 364 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-07-10 | 364 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-07-10 | 364 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-07-10 | 98 |  |  | 2017-10-16 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-10 | 7 |  |  | 2017-07-17 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-10 | 7 |  |  | 2017-07-17 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2017-07-10 | 22 |  |  | 2017-08-01 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-07-10 | 0 |  |  | 2017-07-07 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-11 | 195 |  |  | 2018-01-22 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-11 | 66 |  |  | 2017-09-15 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-11 | 315 |  |  | 2018-05-22 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-11 | 107 |  |  | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-07-11 | 363 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-11 | 0 |  |  | 2017-07-11 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-12 | 362 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-12 | 362 |  |  |  | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-12 | 0 |  |  | 2017-07-12 | N |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-07-12 | 0 |  |  | 2017-07-10 | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-12 | 0 |  |  | 2017-07-10 | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-07-12 | 362 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Final Budget |  |  | User | Henry, Robin |  |  | 2017-07-12 | 26 |  |  | 2017-08-07 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Final Budget |  |  | User | Henry, Robin |  |  | 2017-07-12 | 44 |  |  | 2017-08-25 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Intake Form Completed |  |  | User | Oliver, Amy |  |  | 2017-07-12 | 0 |  |  | 2017-07-12 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-07-12 | 97 |  |  | 2017-10-17 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-12 | 41 |  |  | 2017-08-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-07-12 | 0 |  |  | 2017-07-07 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-07-12 | 0 |  |  | 2017-07-07 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-07-13 | 1 |  |  | 2017-07-14 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO |  |  | 2017-07-13 | 1 |  |  | 2017-07-14 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | IRB Approval |  |  | Role | CTSU Administrator |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-13 | 202 |  |  | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-13 | 64 |  |  | 2017-09-15 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-13 | 361 |  |  |  | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-07-13 | 4 |  |  | 2017-07-17 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-07-13 | 4 |  |  | 2017-07-17 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2017-07-13 | 0 |  |  | 2017-07-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-07-13 | 0 |  |  | 2017-06-26 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-14 | 360 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-14 | 0 |  |  | 2017-07-14 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-14 | 0 |  |  | 2017-07-14 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-07-14 | 0 |  |  | 2017-05-08 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-14 | 0 |  |  | 2017-07-14 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | PAF routed |  |  | User | Henry, Robin |  |  | 2017-07-14 | 45 |  |  | 2017-08-28 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | PAF routed |  |  | User | Henry, Robin |  |  | 2017-07-14 | 43 |  |  | 2017-08-26 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-07-14 | 102 |  |  | 2017-10-24 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-07-14 | 56 |  |  | 2017-09-08 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-15 | 0 |  |  | 2017-07-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-15 | 12 |  |  | 2017-07-27 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-07-15 | 359 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-15 | 3 |  |  | 2017-07-18 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-15 | 25 |  |  | 2017-08-09 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-07-15 | 90 |  |  | 2017-10-13 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-07-15 | 52 |  |  | 2017-09-05 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Request Research Pharmacy Budget |  |  | User | VanderElzen, Liz |  |  | 2017-07-15 | 4 |  |  | 2017-07-19 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-16 | 358 |  |  |  | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-07-16 | 358 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-07-16 | 358 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-07-16 | 9 |  |  | 2017-07-25 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-16 | 85 |  |  | 2017-10-09 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-16 | 2 |  |  | 2017-07-18 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-16 | 2 |  |  | 2017-07-18 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-07-16 | 75 |  |  | 2017-09-29 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-07-16 | 0 |  |  | 2017-06-29 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-07-16 | 4 |  |  | 2017-07-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-17 | 357 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-07-17 | 38 |  |  | 2017-08-24 | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-17 | 38 |  |  | 2017-08-24 | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-17 | 43 |  |  | 2017-08-29 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-07-17 | 357 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-07-17 | 35 |  |  | 2017-08-21 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-07-17 | 10 |  |  | 2017-07-27 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-07-17 | 357 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-07-17 | 108 |  |  | 2017-11-02 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-07-17 | 3 |  |  | 2017-07-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-07-17 | 3 |  |  | 2017-07-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-18 | 0 |  |  | 2017-07-18 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-18 | 79 |  |  | 2017-10-05 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-07-18 | 356 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-07-18 | 356 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-07-18 | 356 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-07-18 | 0 |  |  | 2017-07-12 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-18 | 0 |  |  | 2017-07-18 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-18 | 2 |  |  | 2017-07-20 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-07-18 | 77 |  |  | 2017-10-03 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Budget Negotiations |  |  | User | VanderElzen, Liz |  |  | 2017-07-18 | 0 |  |  | 2017-06-29 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Yunk, Jason |  |  | 2017-07-18 | 0 |  |  | 2017-07-18 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | ** Structural Edits |  |  | User | Yunk, Jason |  |  | 2017-07-18 | 0 |  |  | 2017-07-18 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2017-07-18 | 0 |  |  | 2017-07-18 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-07-18 | 2 |  |  | 2017-07-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-07-18 | 2 |  |  | 2017-07-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-19 | 0 |  |  | 2017-07-19 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-19 | 355 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-07-19 | 355 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-07-19 | 355 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-07-19 | 1 |  |  | 2017-07-20 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-07-19 | 6 |  |  | 2017-07-25 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | OnCore Budget Build |  |  | User | Oliver, Amy |  |  | 2017-07-19 | 355 |  |  |  | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-19 | 34 |  |  | 2017-08-22 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-20 | 0 |  |  | 2017-07-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-07-20 | 354 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-07-20 | 354 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-20 | 0 |  |  | 2017-07-20 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-20 | 0 |  |  | 2017-07-20 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-07-20 | 14 |  |  | 2017-08-03 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-07-20 | 21 |  |  | 2017-08-10 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-07-20 | 19 |  |  | 2017-08-08 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-07-20 | 354 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-20 | 354 |  |  |  | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-20 | 5 |  |  | 2017-07-25 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | PAN Released |  |  | User | VanderElzen, Liz |  |  | 2017-07-20 | 354 |  |  |  | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-07-21 | 3 |  |  | 2017-07-24 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2017-07-21 | 3 |  |  | 2017-07-24 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-21 | 19 |  |  | 2017-08-09 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-21 | 0 |  |  | 2017-07-20 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-21 | 353 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-07-21 | 353 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-07-21 | 353 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-07-21 | 353 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-21 | 0 |  |  | 2017-07-21 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-21 | 3 |  |  | 2017-07-24 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-21 | 3 |  |  | 2017-07-24 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-21 | 3 |  |  | 2017-07-24 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-21 | 0 |  |  | 2017-07-14 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-21 | 10 |  |  | 2017-07-31 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-07-21 | 35 |  |  | 2017-08-25 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-07-21 | 25 |  |  | 2017-08-15 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-07-21 | 10 |  |  | 2017-07-31 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-22 | 352 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-22 | 352 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-22 | 0 |  |  | 2017-07-13 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-07-22 | 352 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-07-22 | 26 |  |  | 2017-08-17 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-22 | 11 |  |  | 2017-08-02 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-22 | 9 |  |  | 2017-07-31 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Final Budget |  |  | User | Henry, Robin |  |  | 2017-07-22 | 68 |  |  | 2017-09-28 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-07-22 | 352 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-07-22 | 54 |  |  | 2017-09-14 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-07-23 | 351 |  |  |  | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-23 | 4 |  |  | 2017-07-27 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-23 | 4 |  |  | 2017-07-27 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-23 | 0 |  |  | 2017-07-21 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Planning Meeting Scheduled |  |  | Role | CTSU Coordinator |  |  | 2017-07-23 | 86 |  |  | 2017-10-17 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-07-23 | 16 |  |  | 2017-08-08 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-07-23 | 351 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-07-23 | 351 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-07-23 | 0 |  |  | 2017-07-20 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-07-23 | 24 |  |  | 2017-08-16 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-07-23 | 16 |  |  | 2017-08-08 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-07-23 | 4 |  |  | 2017-07-27 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-07-23 | 30 |  |  | 2017-08-22 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-07-23 | 30 |  |  | 2017-08-22 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-07-23 | 1 |  |  | 2017-07-24 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-07-23 | 1 |  |  | 2017-07-24 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Billing Calendar Received |  |  | User | VanderElzen, Liz |  |  | 2017-07-23 | 0 |  |  | 2017-07-20 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-07-23 | 3 |  |  | 2017-07-26 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-07-23 | 3 |  |  | 2017-07-26 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-07-23 | 15 |  |  | 2017-08-07 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-24 | 350 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-24 | 28 |  |  | 2017-08-21 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-24 | 28 |  |  | 2017-08-21 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-24 | 350 |  |  |  | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-24 | 350 |  |  |  | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-24 | 0 |  |  | 2017-07-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-07-24 | 350 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-24 | 0 |  |  | 2017-07-24 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-07-24 | 0 |  |  | 2017-07-24 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-07-24 | 15 |  |  | 2017-08-08 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | PAF routed |  |  | User | Henry, Robin |  |  | 2017-07-24 | 66 |  |  | 2017-09-28 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2017-07-24 | 10 |  |  | 2017-08-03 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2017-07-24 | 1 |  |  | 2017-07-25 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2017-07-24 | 1 |  |  | 2017-07-25 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2017-07-24 | 1 |  |  | 2017-07-25 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-24 | 2 |  |  | 2017-07-26 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-24 | 7 |  |  | 2017-07-31 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-07-24 | 350 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-07-24 | 65 |  |  | 2017-09-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-07-24 | 14 |  |  | 2017-08-07 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-07-24 | 3 |  |  | 2017-07-27 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-07-24 | 11 |  |  | 2017-08-04 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-07-25 | 349 |  |  |  | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-07-25 | 0 |  |  | 2017-07-24 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-07-25 | 15 |  |  | 2017-08-09 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-07-25 | 9 |  |  | 2017-08-03 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-07-25 | 1 |  |  | 2017-07-26 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-25 | 0 |  |  | 2017-07-25 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2017-07-25 | 1 |  |  | 2017-07-26 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-07-25 | 43 |  |  | 2017-09-06 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-07-25 | 13 |  |  | 2017-08-07 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-07-25 | 17 |  |  | 2017-08-11 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-26 | 33 |  |  | 2017-08-28 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-26 | 348 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-07-26 | 12 |  |  | 2017-08-07 | N |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-26 | 12 |  |  | 2017-08-07 | N |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-07-26 | 0 |  |  | 2017-07-20 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-26 | 0 |  |  | 2017-07-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-07-26 | 348 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-07-26 | 348 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-07-26 | 348 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-07-26 | 348 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-07-26 | 348 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-07-26 | 84 |  |  | 2017-10-18 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | ** Structural Edits |  |  | User | Yunk, Jason |  |  | 2017-07-26 | 0 |  |  | 2017-07-26 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-07-26 | 9 |  |  | 2017-08-04 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-07-26 | 16 |  |  | 2017-08-11 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-27 | 29 |  |  | 2017-08-25 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-27 | 0 |  |  | 2017-07-25 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-07-27 | 13 |  |  | 2017-08-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-27 | 0 |  |  | 2017-07-25 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-27 | 0 |  |  | 2017-06-01 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-07-27 | 7 |  |  | 2017-08-03 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-07-27 | 0 |  |  | 2017-07-26 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-07-27 | 1 |  |  | 2017-07-28 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-27 | 13 |  |  | 2017-08-09 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-27 | 0 |  |  | 2017-07-26 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Planning Meeting Completed |  |  | User | VanderElzen, Liz |  |  | 2017-07-27 | 6 |  |  | 2017-08-02 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-07-27 | 0 |  |  | 2017-07-26 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128531 | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian |  |  | 2017-07-27 | 0 |  |  | 2017-07-27 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-07-27 | 42 |  |  | 2017-09-07 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-07-27 | 42 |  |  | 2017-09-07 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-07-28 | 346 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-07-28 | 0 |  |  | 2017-05-09 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-07-28 | 33 |  |  | 2017-08-30 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | PAN Released |  |  | User | Henry, Robin |  |  | 2017-07-28 | 95 |  |  | 2017-10-31 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-07-28 | 103 |  |  | 2017-11-08 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-07-28 | 95 |  |  | 2017-10-31 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-07-28 | 6 |  |  | 2017-08-03 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-07-28 | 3 |  |  | 2017-07-31 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-07-28 | 3 |  |  | 2017-07-31 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-29 | 0 |  |  | 2017-07-27 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-07-29 | 0 |  |  | 2017-07-27 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-07-29 | 345 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-07-29 | 13 |  |  | 2017-08-11 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-07-29 | 16 |  |  | 2017-08-14 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-07-29 | 9 |  |  | 2017-08-07 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-07-29 | 0 |  |  | 2017-06-05 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-07-29 | 16 |  |  | 2017-08-14 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-29 | 0 |  |  | 2017-07-26 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-29 | 17 |  |  | 2017-08-15 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-07-29 | 3 |  |  | 2017-08-01 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-29 | 32 |  |  | 2017-08-30 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-07-29 | 166 |  |  | 2018-01-11 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-07-30 | 15 |  |  | 2017-08-14 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-07-30 | 10 |  |  | 2017-08-09 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-30 | 37 |  |  | 2017-09-05 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-30 | 19 |  |  | 2017-08-18 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-07-30 | 4 |  |  | 2017-08-03 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-07-30 | 165 |  |  | 2018-01-11 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-07-30 | 344 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Care Designations completed |  |  | User | VanderElzen, Liz |  |  | 2017-07-30 | 38 |  |  | 2017-09-06 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-07-30 | 51 |  |  | 2017-09-19 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-07-30 | 2 |  |  | 2017-08-01 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-07-30 | 2 |  |  | 2017-08-01 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-07-30 | 1 |  |  | 2017-07-31 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-07-30 | 3 |  |  | 2017-08-02 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-07-31 | 0 |  |  | 2017-07-17 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Contract Executed |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-05-15 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | MiChart Verifications |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 1 |  |  | 2017-08-01 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Other Personnel Notified |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-06-30 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Study Files Established |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | Budget Finalized |  |  | Role | CTSU Finance |  |  | 2017-07-31 | 0 |  |  | 2017-05-15 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | PAN Released |  |  | User | Farmer, Amber |  |  | 2017-07-31 | 210 |  |  | 2018-02-26 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-07-31 | 21 |  |  | 2017-08-21 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-07-31 | 15 |  |  | 2017-08-15 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-07-31 | 0 |  |  | 2017-07-28 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-07-31 | 11 |  |  | 2017-08-11 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-07-31 | 0 |  |  | 2017-07-31 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-01 | 31 |  |  | 2017-09-01 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-01 | 2 |  |  | 2017-08-03 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-01 | 1 |  |  | 2017-08-02 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-01 | 1 |  |  | 2017-08-02 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-01 | 2 |  |  | 2017-08-03 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-01 | 1 |  |  | 2017-08-02 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-01 | 1 |  |  | 2017-08-02 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-08-01 | 14 |  |  | 2017-08-15 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Adequate Equipment and Supplies Available |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Budget Finalized |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 0 |  |  | 2017-03-29 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Contract Executed |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 0 |  |  | 2017-03-29 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | IRB Approval |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 0 |  |  | 2017-06-29 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Investigational Drug/Device Supplies Available |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | MiChart Verifications |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Other Personnel Notified |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Project Award Notice (PAN) Received |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 0 |  |  | 2017-08-01 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Provisions for Support and Services Finalized |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Study Files Established |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | Study Team Roles/Responsibilities Finalized |  |  | User | Huffman, Kate |  |  | 2017-08-01 | 71 |  |  | 2017-10-11 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-01 | 13 |  |  | 2017-08-14 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-01 | 17 |  |  | 2017-08-18 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-01 | 141 |  |  | 2017-12-20 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-08-01 | 0 |  |  | 2017-07-25 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-08-01 | 13 |  |  | 2017-08-14 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-08-01 | 1 |  |  | 2017-08-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | Make Update(s) |  |  | User | Zahs, Brian |  |  | 2017-08-01 | 2 |  |  | 2017-08-03 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | Re-Complete Calendar |  |  | User | Zahs, Brian |  |  | 2017-08-01 | 3 |  |  | 2017-08-04 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-02 | 27 |  |  | 2017-08-29 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-02 | 170 |  |  | 2018-01-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-02 | 21 |  |  | 2017-08-23 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-02 | 0 |  |  | 2017-07-26 | N |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-02 | 0 |  |  | 2017-07-26 | N |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-02 | 0 |  |  | 2017-08-02 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-02 | 341 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-02 | 0 |  |  | 2017-08-02 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-08-02 | 22 |  |  | 2017-08-24 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-08-02 | 341 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-02 | 0 |  |  | 2017-08-01 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2017-08-02 | 0 |  |  | 2017-08-01 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-08-02 | 341 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-03 | 340 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-03 | 55 |  |  | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-03 | 0 |  |  | 2017-08-02 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-03 | 0 |  |  | 2017-08-02 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-03 | 340 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-03 | 340 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-03 | 0 |  |  | 2017-08-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-08-03 | 340 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-08-03 | 340 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-08-03 | 1 |  |  | 2017-08-04 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-03 | 22 |  |  | 2017-08-25 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-03 | 0 |  |  | 2017-07-13 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-03 | 0 |  |  | 2017-07-13 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-03 | 0 |  |  | 2017-07-17 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-03 | 0 |  |  | 2017-08-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda |  |  | 2017-08-03 | 0 |  |  | 2017-08-02 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-08-03 | 5 |  |  | 2017-08-08 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-08-03 | 0 |  |  | 2017-05-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-03 | 8 |  |  | 2017-08-11 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-08-03 | 0 |  |  | 2017-07-28 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-08-03 | 0 |  |  | 2017-07-26 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-08-03 | 34 |  |  | 2017-09-06 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-03 | 15 |  |  | 2017-08-18 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-03 | 12 |  |  | 2017-08-15 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-03 | 12 |  |  | 2017-08-15 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-04 | 0 |  |  | 2017-07-21 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-04 | 0 |  |  | 2017-07-21 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-04 | 217 |  |  | 2018-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-04 | 25 |  |  | 2017-08-29 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-04 | 14 |  |  | 2017-08-18 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-04 | 35 |  |  | 2017-09-08 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-08-04 | 7 |  |  | 2017-08-11 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-04 | 32 |  |  | 2017-09-05 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-08-04 | 32 |  |  | 2017-09-05 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-04 | 0 |  |  | 2017-08-02 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-08-04 | 7 |  |  | 2017-08-11 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-04 | 14 |  |  | 2017-08-18 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-08-04 | 7 |  |  | 2017-08-11 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-08-04 | 339 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-04 | 14 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-08-04 | 54 |  |  | 2017-09-27 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-08-04 | 6 |  |  | 2017-08-10 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-08-04 | 5 |  |  | 2017-08-09 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 20 |  |  | 2017-08-24 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 20 |  |  | 2017-08-24 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 3 |  |  | 2017-08-07 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 0 |  |  | 2017-08-04 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 5 |  |  | 2017-08-09 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 3 |  |  | 2017-08-07 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 0 |  |  | 2017-08-04 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-04 | 3 |  |  | 2017-08-07 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-08-05 | 338 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-08-05 | 338 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-05 | 23 |  |  | 2017-08-28 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-05 | 10 |  |  | 2017-08-15 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-08-05 | 32 |  |  | 2017-09-06 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | PAN Released |  |  | User | Henry, Robin |  |  | 2017-08-05 | 13 |  |  | 2017-08-18 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-05 | 338 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-08-05 | 47 |  |  | 2017-09-21 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-05 | 13 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-05 | 19 |  |  | 2017-08-24 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-08-06 | 4 |  |  | 2017-08-10 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-06 | 15 |  |  | 2017-08-21 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-06 | 18 |  |  | 2017-08-24 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-08-06 | 0 |  |  | 2017-08-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-08-06 | 52 |  |  | 2017-09-27 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-08-06 | 0 |  |  | 2017-08-03 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-08-06 | 4 |  |  | 2017-08-10 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-08-06 | 4 |  |  | 2017-08-10 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-06 | 3 |  |  | 2017-08-09 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-06 | 3 |  |  | 2017-08-09 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-06 | 1 |  |  | 2017-08-07 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-06 | 1 |  |  | 2017-08-07 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-07 | 336 |  |  |  | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-07 | 336 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-08-07 | 336 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-08-07 | 336 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-07 | 21 |  |  | 2017-08-28 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 17 |  |  | 2017-08-24 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 4 |  |  | 2017-08-11 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00122254 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00124920 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125566 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127136 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127505 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128325 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128531 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128743 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 0 |  |  | 2017-08-07 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 17 |  |  | 2017-08-24 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | OnCore Budget Build |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 336 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 129 |  |  | 2017-12-14 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-07 | 126 |  |  | 2017-12-11 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-08 | 17 |  |  | 2017-08-25 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-08 | 30 |  |  | 2017-09-07 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-08 | 0 |  |  | 2017-08-02 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-08 | 0 |  |  | 2017-08-02 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-08-08 | 15 |  |  | 2017-08-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Final Budget |  |  | User | Henry, Robin |  |  | 2017-08-08 | 65 |  |  | 2017-10-12 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-08 | 0 |  |  | 2017-07-27 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-08 | 335 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-08 | 3 |  |  | 2017-08-11 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Budget Negotiations |  |  | User | VanderElzen, Liz |  |  | 2017-08-08 | 15 |  |  | 2017-08-23 | N |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00122254 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-07 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00122254 | Questions |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 1 |  |  | 2017-08-09 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00124920 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-07 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125566 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127136 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127505 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128325 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128325 | Questions |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 1 |  |  | 2017-08-09 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128531 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128531 | Questions |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128743 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-08 | 0 |  |  | 2017-08-08 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-08 | 2 |  |  | 2017-08-10 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-08 | 2 |  |  | 2017-08-10 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-09 | 46 |  |  | 2017-09-24 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-09 | 334 |  |  |  | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-09 | 0 |  |  | 2017-08-09 | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-08-09 | 334 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-08-09 | 334 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-09 | 0 |  |  | 2017-08-07 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-08-09 | 27 |  |  | 2017-09-05 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-10 | 333 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-10 | 91 |  |  | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-08-10 | 333 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-08-10 | 0 |  |  | 2017-08-10 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-08-10 | 333 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-10 | 1 |  |  | 2017-08-11 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-08-10 | 14 |  |  | 2017-08-24 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-10 | 0 |  |  | 2017-08-08 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | PAF routed |  |  | User | Henry, Robin |  |  | 2017-08-10 | 63 |  |  | 2017-10-12 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-10 | 0 |  |  | 2017-07-21 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-10 | 21 |  |  | 2017-08-31 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-10 | 21 |  |  | 2017-08-31 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127505 | Questions |  |  | User | Oliver, Amy |  |  | 2017-08-10 | 0 |  |  | 2017-08-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-08-10 | 0 |  |  | 2017-08-09 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2017-08-10 | 333 |  |  |  | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-08-10 | 4 |  |  | 2017-08-14 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-08-10 | 4 |  |  | 2017-08-14 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-11 | 332 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-11 | 0 |  |  | 2017-08-11 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-08-11 | 0 |  |  | 2017-07-20 | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-08-11 | 38 |  |  | 2017-09-18 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-08-11 | 332 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-11 | 76 |  |  | 2017-10-26 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-11 | 0 |  |  | 2017-08-09 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-11 | 0 |  |  | 2017-08-07 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-11 | 0 |  |  | 2017-08-08 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2017-08-11 | 3 |  |  | 2017-08-14 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 10 |  |  | 2017-08-21 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 6 |  |  | 2017-08-17 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00124920 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00124920 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125566 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125566 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127136 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127136 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127505 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127505 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128325 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128325 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128531 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128531 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128743 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128743 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-08-10 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 14 |  |  | 2017-08-25 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 159 |  |  | 2018-01-17 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 159 |  |  | 2018-01-17 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-11 | 0 |  |  | 2017-06-30 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-12 | 331 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-08-12 | 331 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-08-12 | 331 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-08-12 | 331 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-08-12 | 331 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-12 | 31 |  |  | 2017-09-12 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-12 | 9 |  |  | 2017-08-21 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-08-12 | 19 |  |  | 2017-08-31 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Final Budget |  |  | User | Henry, Robin |  |  | 2017-08-12 | 9 |  |  | 2017-08-21 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-12 | 81 |  |  | 2017-11-01 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-12 | 40 |  |  | 2017-09-21 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-08-12 | 11 |  |  | 2017-08-23 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-12 | 0 |  |  | 2017-06-06 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-13 | 330 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-13 | 330 |  |  |  | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-08-13 | 330 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-08-13 | 4 |  |  | 2017-08-17 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-13 | 10 |  |  | 2017-08-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-13 | 0 |  |  | 2017-08-03 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-08-13 | 0 |  |  | 2017-08-11 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-13 | 15 |  |  | 2017-08-28 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-13 | 15 |  |  | 2017-08-28 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-08-13 | 2 |  |  | 2017-08-15 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-07-20 | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 329 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129652 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129716 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129820 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130575 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131837 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131953 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133290 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - PLT-INF24-001 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 0 |  |  | 2017-08-14 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-08-14 | 329 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-14 | 129 |  |  | 2017-12-21 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-14 | 7 |  |  | 2017-08-21 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | PAF routed |  |  | User | Henry, Robin |  |  | 2017-08-14 | 7 |  |  | 2017-08-21 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-08-14 | 9 |  |  | 2017-08-23 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-08-14 | 10 |  |  | 2017-08-24 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-08-14 | 17 |  |  | 2017-08-31 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-15 | 328 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-15 | 328 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-15 | 328 |  |  |  | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-15 | 76 |  |  | 2017-10-30 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-15 | 76 |  |  | 2017-10-30 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-15 | 83 |  |  | 2017-11-06 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-15 | 76 |  |  | 2017-10-30 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-15 | 0 |  |  | 2017-08-02 | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-15 | 0 |  |  | 2017-08-01 | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-15 | 0 |  |  | 2017-08-02 | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-15 | 0 |  |  | 2017-08-02 | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-15 | 21 |  |  | 2017-09-05 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-15 | 72 |  |  | 2017-10-26 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-15 | 0 |  |  | 2017-08-14 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-15 | 0 |  |  | 2017-08-14 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-15 | 0 |  |  | 2017-08-03 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-15 | 0 |  |  | 2017-08-07 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-15 | 0 |  |  | 2017-08-08 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-15 | 157 |  |  | 2018-01-19 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-15 | 0 |  |  | 2017-07-06 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129652 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 1 |  |  | 2017-08-16 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129716 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 1 |  |  | 2017-08-16 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129820 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 1 |  |  | 2017-08-16 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130575 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 1 |  |  | 2017-08-16 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131837 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 2 |  |  | 2017-08-17 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131953 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 3 |  |  | 2017-08-18 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133290 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 1 |  |  | 2017-08-16 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - PLT-INF24-001 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-15 | 1 |  |  | 2017-08-16 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-08-15 | 23 |  |  | 2017-09-07 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-08-15 | 23 |  |  | 2017-09-07 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 282-POP-BUSUI | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian |  |  | 2017-08-15 | 328 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-15 | 28 |  |  | 2017-09-12 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-15 | 15 |  |  | 2017-08-30 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-15 | 28 |  |  | 2017-09-12 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-15 | 15 |  |  | 2017-08-30 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-16 | 0 |  |  | 2017-08-16 | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-08-16 | 14 |  |  | 2017-08-30 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-08-16 | 14 |  |  | 2017-08-30 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-08-16 | 16 |  |  | 2017-09-01 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-16 | 37 |  |  | 2017-09-22 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-16 | 77 |  |  | 2017-11-01 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-17 | 0 |  |  | 2017-08-17 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-17 | 0 |  |  | 2017-08-17 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-17 | 0 |  |  | 2017-08-17 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-17 | 75 |  |  | 2017-10-31 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-17 | 75 |  |  | 2017-10-31 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-17 | 0 |  |  | 2017-08-08 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-17 | 22 |  |  | 2017-09-08 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-17 | 0 |  |  | 2017-08-17 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-08-17 | 326 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125425 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-17 | 0 |  |  | 2017-08-17 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132020 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-17 | 0 |  |  | 2017-08-17 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-08-17 | 119 |  |  | 2017-12-14 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-08-17 | 29 |  |  | 2017-09-15 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-17 | 0 |  |  | 2017-08-14 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | Make Update(s) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-17 | 14 |  |  | 2017-08-31 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 19 |  |  | 2017-09-05 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Request MCRU Budget |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 32 |  |  | 2017-09-18 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 21 |  |  | 2017-09-07 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 182 |  |  | 2018-02-15 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 0 |  |  | 2017-08-10 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 96 |  |  | 2017-11-21 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Oliver, Amy |  |  | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-08-17 | 75 |  |  | 2017-10-31 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-08-17 | 55 |  |  | 2017-10-11 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-17 | 19 |  |  | 2017-09-05 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Submit Update Request(s) | [6 empty] | 2017-08-17 | 1 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-18 | 214 |  |  | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-18 | 24 |  |  | 2017-09-11 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-18 | 3 |  |  | 2017-08-21 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-18 | 3 |  |  | 2017-08-21 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-18 | 3 |  |  | 2017-08-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-18 | 3 |  |  | 2017-08-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-18 | 3 |  |  | 2017-08-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-18 | 21 |  |  | 2017-09-08 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-18 | 10 |  |  | 2017-08-28 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-18 | 10 |  |  | 2017-08-28 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-18 | 0 |  |  | 2017-08-17 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-18 | 0 |  |  | 2017-08-07 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129652 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129652 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129716 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129716 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129820 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129820 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130575 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130575 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131837 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131837 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131953 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131953 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133290 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133290 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - PLT-INF24-001 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - PLT-INF24-001 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 0 |  |  | 2017-08-10 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-08-18 | 325 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125425 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132020 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132020 | Questions |  |  | User | Yunk, Jason |  |  | 2017-08-18 | 0 |  |  | 2017-08-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-19 | 55 |  |  | 2017-10-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-19 | 151 |  |  | 2018-01-17 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-19 | 0 |  |  | 2017-08-18 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-19 | 0 |  |  | 2017-08-18 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-19 | 0 |  |  | 2017-08-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-08-19 | 324 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | PAN Released |  |  | Role | CTSU Finance |  |  | 2017-08-19 | 324 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-08-19 | 30 |  |  | 2017-09-18 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-08-19 | 55 |  |  | 2017-10-13 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-19 | 72 |  |  | 2017-10-30 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-19 | 72 |  |  | 2017-10-30 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-19 | 2 |  |  | 2017-08-21 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-08-19 | 9 |  |  | 2017-08-28 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Assign to Analyst |  |  | User | LaVasseur, Kristen |  |  | 2017-08-19 | 0 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-08-19 | 18 |  |  | 2017-09-06 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-19 | 2 |  |  | 2017-08-21 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-20 | 212 |  |  | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-20 | 25 |  |  | 2017-09-14 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-20 | 4 |  |  | 2017-08-24 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-20 | 0 |  |  | 2017-08-11 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-08-20 | 323 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-20 | 0 |  |  | 2017-08-16 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-20 | 3 |  |  | 2017-08-23 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-08-20 | 0 |  |  | 2017-08-14 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-20 | 0 |  |  | 2017-08-08 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-20 | 32 |  |  | 2017-09-21 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-08-20 | 0 |  |  | 2017-08-11 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-08-20 | 323 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 4 |  |  | 2017-08-24 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 2 |  |  | 2017-08-22 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 4 |  |  | 2017-08-24 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 4 |  |  | 2017-08-24 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 2 |  |  | 2017-08-22 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 12 |  |  | 2017-09-01 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 4 |  |  | 2017-08-24 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 2 |  |  | 2017-08-22 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-20 | 11 |  |  | 2017-08-31 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-21 | 322 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-21 | 0 |  |  | 2017-08-16 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-21 | 141 |  |  | 2018-01-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-21 | 211 |  |  | 2018-03-20 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-21 | 10 |  |  | 2017-08-31 | N |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-21 | 11 |  |  | 2017-09-01 | N |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-21 | 0 |  |  | 2017-08-07 | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-21 | 0 |  |  | 2017-08-04 | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00108880 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125022 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00126010 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131329 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132200 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-08-21 | 322 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-21 | 122 |  |  | 2017-12-21 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-08-21 | 60 |  |  | 2017-10-20 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | 15 |  |  | 2017-09-05 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | 15 |  |  | 2017-09-05 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | 8 |  |  | 2017-08-29 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | 161 |  |  | 2018-01-29 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | 9 |  |  | 2017-08-30 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | 14 |  |  | 2017-09-04 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128157 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | ** Structural Edits |  |  | User | Yunk, Jason |  |  | 2017-08-21 | 0 |  |  | 2017-08-21 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-21 | 248 |  |  | 2018-04-26 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-21 | 3 |  |  | 2017-08-24 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-21 | 3 |  |  | 2017-08-24 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-21 | 16 |  |  | 2017-09-06 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-22 | 321 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-22 | 321 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-08-22 | 321 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-22 | 66 |  |  | 2017-10-27 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128157 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-22 | 8 |  |  | 2017-08-30 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-22 | 6 |  |  | 2017-08-28 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-22 | 6 |  |  | 2017-08-28 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-22 | 0 |  |  | 2017-08-17 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-22 | 2 |  |  | 2017-08-24 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128157 | Questions |  |  | User | Oliver, Amy |  |  | 2017-08-22 | 2 |  |  | 2017-08-24 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-08-22 | 0 |  |  | 2017-08-15 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-22 | 248 |  |  | 2018-04-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-22 | 119 |  |  | 2017-12-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00108880 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-22 | 0 |  |  | 2017-08-21 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125022 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-22 | 0 |  |  | 2017-08-21 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00126010 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-22 | 0 |  |  | 2017-08-21 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131329 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-22 | 0 |  |  | 2017-08-22 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132200 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-22 | 0 |  |  | 2017-08-21 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132200 | Questions |  |  | User | Yunk, Jason |  |  | 2017-08-22 | 0 |  |  | 2017-08-22 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-22 | 2 |  |  | 2017-08-24 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-22 | 2 |  |  | 2017-08-24 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-22 | 10 |  |  | 2017-09-01 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-22 | 10 |  |  | 2017-09-01 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-22 | 9 |  |  | 2017-08-31 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-22 | 9 |  |  | 2017-08-31 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-23 | 34 |  |  | 2017-09-26 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-23 | 10 |  |  | 2017-09-02 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-23 | 0 |  |  | 2017-08-23 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-23 | 0 |  |  | 2017-08-23 | N |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101092 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-23 | 0 |  |  | 2017-08-23 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107927 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-23 | 0 |  |  | 2017-08-23 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111185 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-23 | 0 |  |  | 2017-08-23 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-23 | 14 |  |  | 2017-09-06 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-23 | 14 |  |  | 2017-09-06 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-23 | 16 |  |  | 2017-09-08 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-08-23 | 16 |  |  | 2017-09-08 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-08-23 | 70 |  |  | 2017-11-01 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-08-23 | 54 |  |  | 2017-10-16 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-23 | 14 |  |  | 2017-09-06 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-23 | 19 |  |  | 2017-09-11 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | CRAO Approval Issue & Documented |  |  | Role | CRAO |  |  | 2017-08-24 | 0 |  |  | 2017-08-24 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-24 | 319 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-24 | 319 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-24 | 319 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-08-24 | 319 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-08-24 | 319 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Request MCRU Budget |  |  | Role | CTSU Finance |  |  | 2017-08-24 | 319 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-08-24 | 319 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-08-24 | 319 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-08-24 | 319 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107927 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-24 | 0 |  |  | 2017-08-23 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107927 | Questions |  |  | User | Farmer, Amber |  |  | 2017-08-24 | 7 |  |  | 2017-08-31 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111185 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-24 | 0 |  |  | 2017-08-23 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111185 | Questions |  |  | User | Farmer, Amber |  |  | 2017-08-24 | 6 |  |  | 2017-08-30 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2017-08-24 | 0 |  |  | 2017-08-24 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Make Updates |  |  | User | Hodges, Lynda |  |  | 2017-08-24 | 0 |  |  | 2017-08-24 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Make Update(s) |  |  | User | LaVasseur, Kristen |  |  | 2017-08-24 | 0 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Re-Complete Calendar |  |  | User | LaVasseur, Kristen |  |  | 2017-08-24 | 0 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-24 | 111 |  |  | 2017-12-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101092 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-08-24 | 0 |  |  | 2017-08-23 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 318 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 102 |  |  | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 220 |  |  | 2018-04-02 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-25 | 133 |  |  | 2018-01-05 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-08-25 | 38 |  |  | 2017-10-02 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-25 | 3 |  |  | 2017-08-28 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-25 | 3 |  |  | 2017-08-28 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 27 |  |  | 2017-09-21 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00108880 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00108880 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-24 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125022 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125022 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-23 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125425 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-18 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125425 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-18 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00126010 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00126010 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-22 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128157 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 5 |  |  | 2017-08-30 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131329 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131329 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-23 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132200 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-25 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132200 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-25 | 0 |  |  | 2017-08-23 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-08-26 | 0 |  |  | 2017-01-12 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-08-26 | 0 |  |  | 2017-08-25 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-08-26 | 0 |  |  | 2017-08-18 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-27 | 316 |  |  |  | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-27 | 316 |  |  |  | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-27 | 296 |  |  | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-27 | 1 |  |  | 2017-08-28 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-27 | 1 |  |  | 2017-08-28 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-27 | 1 |  |  | 2017-08-28 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-08-27 | 316 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-27 | 18 |  |  | 2017-09-14 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-27 | 22 |  |  | 2017-09-18 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-08-27 | 22 |  |  | 2017-09-18 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-27 | 22 |  |  | 2017-09-18 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-08-27 | 22 |  |  | 2017-09-18 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-27 | 2 |  |  | 2017-08-29 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-27 | 2 |  |  | 2017-08-29 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-27 | 5 |  |  | 2017-09-01 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-27 | 4 |  |  | 2017-08-31 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-27 | 0 |  |  | 2017-08-24 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-08-27 | 22 |  |  | 2017-09-18 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-08-27 | 22 |  |  | 2017-09-18 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-27 | 0 |  |  | 2017-08-25 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101092 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 0 |  |  | 2017-08-25 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101092 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 0 |  |  | 2017-08-23 | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107927 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 5 |  |  | 2017-09-01 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107927 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 4 |  |  | 2017-08-31 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111185 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 5 |  |  | 2017-09-01 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111185 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 4 |  |  | 2017-08-31 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-27 | 316 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-28 | 182 |  |  | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-08-28 | 315 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-28 | 315 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-28 | 0 |  |  | 2017-08-14 | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-28 | 0 |  |  | 2017-08-14 | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-28 | 0 |  |  | 2017-08-07 | N |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-28 | 0 |  |  | 2017-08-28 | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00066077 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-28 | 0 |  |  | 2017-08-28 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00082356 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-28 | 0 |  |  | 2017-08-28 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00089260 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-28 | 0 |  |  | 2017-08-28 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101426 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-28 | 0 |  |  | 2017-08-28 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130757 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-08-28 | 0 |  |  | 2017-08-28 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-08-28 | 315 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-08-28 | 43 |  |  | 2017-10-10 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Final Budget |  |  | User | Henry, Robin |  |  | 2017-08-28 | 0 |  |  | 2017-08-21 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-28 | 15 |  |  | 2017-09-12 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-08-28 | 15 |  |  | 2017-09-12 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | PAN Released |  |  | User | Henry, Robin |  |  | 2017-08-28 | 55 |  |  | 2017-10-22 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2017-08-28 | 10 |  |  | 2017-09-07 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2017-08-28 | 1 |  |  | 2017-08-29 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-08-28 | 10 |  |  | 2017-09-07 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 23-GUPTA | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2017-08-28 | 0 |  |  | 2017-08-25 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-08-28 | 9 |  |  | 2017-09-06 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-08-28 | 59 |  |  | 2017-10-26 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | ** Request for Clarification |  |  | User | Yunk, Jason |  |  | 2017-08-28 | 315 |  |  |  | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-08-28 | 38 |  |  | 2017-10-05 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-08-28 | 11 |  |  | 2017-09-08 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-08-28 | 8 |  |  | 2017-09-05 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-08-28 | 1 |  |  | 2017-08-29 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-08-28 | 1 |  |  | 2017-08-29 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-08-28 | 10 |  |  | 2017-09-07 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-29 | 0 |  |  | 2017-08-17 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-29 | 0 |  |  | 2017-08-17 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00066077 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 2 |  |  | 2017-08-31 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00066077 | Questions |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 2 |  |  | 2017-08-31 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00082356 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 1 |  |  | 2017-08-30 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00089260 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 0 |  |  | 2017-08-29 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101426 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 1 |  |  | 2017-08-30 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101426 | Questions |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 0 |  |  | 2017-08-28 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130757 | Initiate Updates |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 1 |  |  | 2017-08-30 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130757 | Questions |  |  | User | Farmer, Amber |  |  | 2017-08-29 | 0 |  |  | 2017-08-25 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-08-29 | 0 |  |  | 2017-08-29 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-08-29 | 0 |  |  | 2017-08-29 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-08-29 | 0 |  |  | 2017-08-29 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Final Budget |  |  | User | Henry, Robin |  |  | 2017-08-29 | 30 |  |  | 2017-09-28 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-08-29 | 0 |  |  | 2017-08-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-29 | 20 |  |  | 2017-09-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-29 | 29 |  |  | 2017-09-27 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-08-29 | 29 |  |  | 2017-09-27 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-08-30 | 313 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-08-30 | 313 |  |  |  | N |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-08-30 | 313 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-08-30 | 0 |  |  | 2017-08-17 | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-08-30 | 0 |  |  | 2017-08-03 | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-08-30 | 313 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-08-30 | 313 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-08-30 | 313 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-08-30 | 41 |  |  | 2017-10-10 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | PAF routed |  |  | User | Henry, Robin |  |  | 2017-08-30 | 0 |  |  | 2017-08-22 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-08-30 | 36 |  |  | 2017-10-05 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-08-30 | 22 |  |  | 2017-09-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-08-30 | 8 |  |  | 2017-09-07 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-08-30 | 8 |  |  | 2017-09-07 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-08-30 | 23 |  |  | 2017-09-22 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-08-30 | 23 |  |  | 2017-09-22 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-08-30 | 55 |  |  | 2017-10-24 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-08-30 | 49 |  |  | 2017-10-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-08-30 | 9 |  |  | 2017-09-08 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-08-30 | 9 |  |  | 2017-09-08 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-08-30 | 8 |  |  | 2017-09-07 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-08-30 | 8 |  |  | 2017-09-07 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-31 | 20 |  |  | 2017-09-20 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Planning Meeting Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-31 | 19 |  |  | 2017-09-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-31 | 64 |  |  | 2017-11-03 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-08-31 | 64 |  |  | 2017-11-03 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-08-31 | 0 |  |  | 2017-08-31 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-08-31 | 312 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-08-31 | 312 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-31 | 7 |  |  | 2017-09-07 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | ** Structural Edits |  |  | User | Farmer, Amber |  |  | 2017-08-31 | 0 |  |  | 2017-08-31 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2017-08-31 | 0 |  |  | 2017-08-31 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-08-31 | 112 |  |  | 2017-12-21 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | PAF routed |  |  | User | Henry, Robin |  |  | 2017-08-31 | 111 |  |  | 2017-12-20 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-31 | 0 |  |  | 2017-08-30 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-31 | 0 |  |  | 2017-08-30 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-08-31 | 0 |  |  | 2017-08-30 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-08-31 | 0 |  |  | 2017-08-17 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-08-31 | 312 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-08-31 | 312 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-31 | 18 |  |  | 2017-09-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-31 | 18 |  |  | 2017-09-18 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-31 | 32 |  |  | 2017-10-02 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-31 | 32 |  |  | 2017-10-02 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-08-31 | 32 |  |  | 2017-10-02 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-08-31 | 32 |  |  | 2017-10-02 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-01 | 27 |  |  | 2017-09-28 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-09-01 | 0 |  |  | 2017-08-03 | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-01 | 311 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-01 | 311 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-09-01 | 4 |  |  | 2017-09-05 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-09-01 | 0 |  |  | 2017-08-29 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Complete MCA / QCT |  |  | User | Hess, Aaron |  |  | 2017-09-01 | 13 |  |  | 2017-09-14 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2017-09-01 | 0 |  |  | 2017-08-30 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2017-09-01 | 11 |  |  | 2017-09-12 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-01 | 59 |  |  | 2017-10-30 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-01 | 59 |  |  | 2017-10-30 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-01 | 49 |  |  | 2017-10-20 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 88 |  |  | 2017-11-28 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 39 |  |  | 2017-10-10 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 45 |  |  | 2017-10-16 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 24 |  |  | 2017-09-25 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 32 |  |  | 2017-10-03 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00066077 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00066077 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-08-31 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00082356 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00082356 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-08-31 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00089260 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00089260 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-08-29 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101426 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-09-01 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101426 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-08-30 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130757 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-08-31 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130757 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 0 |  |  | 2017-08-30 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 137 |  |  | 2018-01-16 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 49 |  |  | 2017-10-20 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-01 | 311 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-01 | 237 |  |  | 2018-04-26 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-09-01 | 25 |  |  | 2017-09-26 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-09-01 | 25 |  |  | 2017-09-26 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-09-02 | 310 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-09-02 | 310 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-02 | 237 |  |  | 2018-04-27 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-02 | 5 |  |  | 2017-09-07 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-09-02 | 25 |  |  | 2017-09-27 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-09-02 | 39 |  |  | 2017-10-11 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-09-02 | 39 |  |  | 2017-10-11 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-02 | 310 |  |  |  | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-02 | 140 |  |  | 2018-01-20 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-02 | 109 |  |  | 2017-12-20 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-09-03 | 309 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-09-03 | 309 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-03 | 37 |  |  | 2017-10-10 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-03 | 24 |  |  | 2017-09-27 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-03 | 24 |  |  | 2017-09-27 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-09-03 | 47 |  |  | 2017-10-20 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-09-03 | 24 |  |  | 2017-09-27 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-03 | 24 |  |  | 2017-09-27 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-03 | 0 |  |  | 2017-08-17 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2017-09-03 | 9 |  |  | 2017-09-12 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2017-09-03 | 9 |  |  | 2017-09-12 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-03 | 309 |  |  |  | N |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-03 | 139 |  |  | 2018-01-20 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-03 | 130 |  |  | 2018-01-11 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-09-03 | 60 |  |  | 2017-11-02 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-03 | 309 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-04 | 154 |  |  | 2018-02-05 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-04 | 308 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-04 | 308 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-04 | 308 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-09-04 | 308 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-09-04 | 10 |  |  | 2017-09-14 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Initiate Post-Award Task List |  |  | User | Henry, Robin |  |  | 2017-09-04 | 58 |  |  | 2017-11-01 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-04 | 17 |  |  | 2017-09-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-04 | 31 |  |  | 2017-10-05 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-09-04 | 8 |  |  | 2017-09-12 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-04 | 134 |  |  | 2018-01-16 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-09-04 | 59 |  |  | 2017-11-02 | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-05 | 251 |  |  | 2018-05-14 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-05 | 307 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-05 | 307 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-05 | 0 |  |  | 2017-09-05 | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-09-05 | 307 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-05 | 307 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-05 | 307 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119175 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-05 | 0 |  |  | 2017-09-05 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119399 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-05 | 1 |  |  | 2017-09-06 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-05 | 10 |  |  | 2017-09-15 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-05 | 0 |  |  | 2017-08-21 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-09-05 | 36 |  |  | 2017-10-11 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-05 | 307 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 152 |  |  | 2018-02-05 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 44 |  |  | 2017-10-20 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 44 |  |  | 2017-10-20 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 306 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 306 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 306 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 306 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 298-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-06 | 306 |  |  |  | N |  | 298-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-06 | 306 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 306 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 306 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111923 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113391 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113496 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123231 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123861 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-09-06 | 34 |  |  | 2017-10-10 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-09-06 | 34 |  |  | 2017-10-10 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-09-06 | 34 |  |  | 2017-10-10 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-06 | 306 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119175 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119399 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-06 | 0 |  |  | 2017-09-06 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-07 | 305 |  |  |  | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-07 | 11 |  |  | 2017-09-18 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-07 | 305 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-09-07 | 147 |  |  | 2018-02-01 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-09-07 | 1 |  |  | 2017-09-08 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-09-07 | 1 |  |  | 2017-09-08 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-09-07 | 1 |  |  | 2017-09-08 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-07 | 7 |  |  | 2017-09-14 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-07 | 7 |  |  | 2017-09-14 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-07 | 7 |  |  | 2017-09-14 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-07 | 8 |  |  | 2017-09-15 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-09-07 | 22 |  |  | 2017-09-29 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-09-07 | 35 |  |  | 2017-10-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111923 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-07 | 0 |  |  | 2017-09-06 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113391 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-07 | 0 |  |  | 2017-09-06 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113496 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-07 | 0 |  |  | 2017-09-06 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123231 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-07 | 0 |  |  | 2017-09-06 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123861 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-07 | 0 |  |  | 2017-09-06 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-09-07 | 0 |  |  | 2017-09-07 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-08 | 304 |  |  |  | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-08 | 304 |  |  |  | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-08 | 304 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-08 | 304 |  |  |  | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-08 | 80 |  |  | 2017-11-27 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-08 | 81 |  |  | 2017-11-28 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-08 | 304 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-08 | 7 |  |  | 2017-09-15 | N |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-08 | 32 |  |  | 2017-10-10 | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-09-08 | 304 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-09-08 | 304 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-09-08 | 304 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-09-08 | 304 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-09-08 | 7 |  |  | 2017-09-15 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-09-08 | 7 |  |  | 2017-09-15 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-08 | 11 |  |  | 2017-09-19 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-08 | 27 |  |  | 2017-10-05 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-09-08 | 7 |  |  | 2017-09-15 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-09-08 | 304 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-08 | 269 |  |  | 2018-06-04 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-09-08 | 41 |  |  | 2017-10-19 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-09-08 | 41 |  |  | 2017-10-19 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-09-08 | 34 |  |  | 2017-10-12 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-09-08 | 34 |  |  | 2017-10-12 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-09 | 303 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-09-09 | 0 |  |  | 2017-09-08 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-09-09 | 0 |  |  | 2017-09-08 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119175 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-09 | 6 |  |  | 2017-09-15 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119175 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-09 | 6 |  |  | 2017-09-15 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119399 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-09 | 6 |  |  | 2017-09-15 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119399 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-09 | 6 |  |  | 2017-09-15 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-10 | 18 |  |  | 2017-09-28 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-10 | 10 |  |  | 2017-09-20 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-10 | 10 |  |  | 2017-09-20 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-09-10 | 32 |  |  | 2017-10-12 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-09-10 | 40 |  |  | 2017-10-20 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-09-10 | 8 |  |  | 2017-09-18 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-10 | 10 |  |  | 2017-09-20 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-10 | 3 |  |  | 2017-09-13 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 23 |  |  | 2017-10-03 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111923 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111923 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113391 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113391 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113496 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113496 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123231 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123231 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123861 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123861 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-10 | 0 |  |  | 2017-09-08 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-10 | 302 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-09-10 | 5 |  |  | 2017-09-15 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-09-10 | 11 |  |  | 2017-09-21 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-11 | 301 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-11 | 301 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-11 | 212 |  |  | 2018-04-11 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-11 | 301 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-11 | 301 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 301 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107954 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00118570 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125786 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127537 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129851 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133286 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133684 | Received calendar from Niyati |  |  | Role | CTSU Finance |  |  | 2017-09-11 | 0 |  |  | 2017-09-11 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-11 | 29 |  |  | 2017-10-10 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-11 | 8 |  |  | 2017-09-19 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-11 | 24 |  |  | 2017-10-05 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-09-11 | 29 |  |  | 2017-10-10 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-09-11 | 301 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-11 | 301 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-11 | 0 |  |  | 2017-09-08 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-09-12 | 300 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-09-12 | 300 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107954 | Initiate Updates |  |  | Role | CTSU Finance |  |  | 2017-09-12 | 1 |  |  | 2017-09-13 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125786 | Initiate Updates |  |  | Role | CTSU Finance |  |  | 2017-09-12 | 1 |  |  | 2017-09-13 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127537 | Initiate Updates |  |  | Role | CTSU Finance |  |  | 2017-09-12 | 1 |  |  | 2017-09-13 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129851 | Initiate Updates |  |  | Role | CTSU Finance |  |  | 2017-09-12 | 1 |  |  | 2017-09-13 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-12 | 99 |  |  | 2017-12-20 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-12 | 15 |  |  | 2017-09-27 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-12 | 15 |  |  | 2017-09-27 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-12 | 15 |  |  | 2017-09-27 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-12 | 1 |  |  | 2017-09-13 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2017-09-12 | 7 |  |  | 2017-09-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Make Updates |  |  | User | Hess, Aaron |  |  | 2017-09-12 | 7 |  |  | 2017-09-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-09-12 | 21 |  |  | 2017-10-03 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-09-12 | 9 |  |  | 2017-09-21 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-09-12 | 9 |  |  | 2017-09-21 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-13 | 299 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-13 | 35 |  |  | 2017-10-18 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-13 | 264 |  |  | 2018-06-04 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-13 | 0 |  |  | 2017-08-31 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-13 | 0 |  |  | 2017-08-30 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-13 | 0 |  |  | 2017-09-05 | N |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-13 | 0 |  |  | 2017-09-01 | N |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-13 | 0 |  |  | 2017-09-13 | N |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-13 | 0 |  |  | 2017-09-13 | N |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Initial Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-09-13 | 79 |  |  | 2017-12-01 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-13 | 64 |  |  | 2017-11-16 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-13 | 8 |  |  | 2017-09-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-13 | 22 |  |  | 2017-10-05 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-13 | 79 |  |  | 2017-12-01 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Budget Negotiations |  |  | User | Oliver, Amy |  |  | 2017-09-13 | 299 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-13 | 197 |  |  | 2018-03-29 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-14 | 11 |  |  | 2017-09-25 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-14 | 0 |  |  | 2017-09-14 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-14 | 0 |  |  | 2017-09-14 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | PI Signoff in OnCore |  |  | Role | CTSU Coordinator |  |  | 2017-09-14 | 298 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-09-14 | 298 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-14 | 298 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-09-14 | 230 |  |  | 2018-05-02 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-09-14 | 6 |  |  | 2017-09-20 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-14 | 230 |  |  | 2018-05-02 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-14 | 208 |  |  | 2018-04-10 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-14 | 26 |  |  | 2017-10-10 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-15 | 297 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Intake Form Completed |  |  | Role | CTSU Administrator |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 90 |  |  | 2017-12-14 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 118 |  |  | 2018-01-11 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 297 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 297 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107954 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107954 | Review & Release Calendar |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125786 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125786 | Review & Release Calendar |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127537 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127537 | Review & Release Calendar |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129851 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129851 | Review & Release Calendar |  |  | Role | CTSU Finance |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-15 | 14 |  |  | 2017-09-29 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-15 | 14 |  |  | 2017-09-29 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-15 | 80 |  |  | 2017-12-04 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-09-15 | 14 |  |  | 2017-09-29 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-15 | 90 |  |  | 2017-12-14 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-15 | 91 |  |  | 2017-12-15 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-15 | 123 |  |  | 2018-01-16 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-09-15 | 0 |  |  | 2017-09-15 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-16 | 296 |  |  |  | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-16 | 9 |  |  | 2017-09-25 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-16 | 296 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-09-16 | 96 |  |  | 2017-12-21 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-09-16 | 47 |  |  | 2017-11-02 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-17 | 239 |  |  | 2018-05-14 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-17 | 295 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-09-17 | 125 |  |  | 2018-01-20 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-09-17 | 295 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-09-17 | 295 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-09-17 | 295 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-09-17 | 295 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-17 | 121 |  |  | 2018-01-16 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-17 | 124 |  |  | 2018-01-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-17 | 1 |  |  | 2017-09-18 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-17 | 295 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-18 | 294 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-18 | 294 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-09-18 | 294 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-09-18 | 294 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-18 | 294 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-18 | 11 |  |  | 2017-09-29 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-18 | 11 |  |  | 2017-09-29 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-09-18 | 11 |  |  | 2017-09-29 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 313-CONJEEVARAM | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 294 |  |  |  | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128173 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129427 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130793 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133341 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00134035 | Received calendar from Niyati |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-18 | 294 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-18 | 1 |  |  | 2017-09-19 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00132700 | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian |  |  | 2017-09-18 | 0 |  |  | 2017-09-18 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-19 | 293 |  |  |  | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-19 | 0 |  |  | 2017-09-19 | N |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-09-19 | 293 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-19 | 2 |  |  | 2017-09-21 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-19 | 0 |  |  | 2017-09-08 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-19 | 0 |  |  | 2017-09-19 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | VanderElzen, Liz |  |  | 2017-09-19 | 6 |  |  | 2017-09-25 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128173 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-19 | 0 |  |  | 2017-09-18 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129427 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-19 | 0 |  |  | 2017-09-18 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130793 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-19 | 0 |  |  | 2017-09-18 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133341 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-19 | 0 |  |  | 2017-09-18 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00134035 | Initiate Updates |  |  | User | Yunk, Jason |  |  | 2017-09-19 | 0 |  |  | 2017-09-18 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-09-19 | 0 |  |  | 2017-09-19 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-20 | 30 |  |  | 2017-10-20 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-20 | 0 |  |  | 2017-09-20 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | PI Signoff in OnCore |  |  | Role | CTSU Coordinator |  |  | 2017-09-20 | 126 |  |  | 2018-01-24 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-20 | 292 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-20 | 0 |  |  | 2017-09-11 | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-20 | 292 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-09-20 | 1 |  |  | 2017-09-21 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-09-20 | 1 |  |  | 2017-09-21 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-09-20 | 1 |  |  | 2017-09-21 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-20 | 12 |  |  | 2017-10-02 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-20 | 12 |  |  | 2017-10-02 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-09-20 | 12 |  |  | 2017-10-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2017-09-20 | 0 |  |  | 2017-09-19 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Assign to Analyst |  |  | User | Zahs, Brian |  |  | 2017-09-20 | 0 |  |  | 2017-09-20 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-21 | 0 |  |  | 2017-09-15 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-21 | 0 |  |  | 2017-08-31 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | PI Signoff in OnCore |  |  | Role | CTSU Coordinator |  |  | 2017-09-21 | 291 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-09-21 | 291 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-09-21 | 291 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-09-21 | 291 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-21 | 75 |  |  | 2017-12-05 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-21 | 120 |  |  | 2018-01-19 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-09-21 | 0 |  |  | 2017-09-21 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2017-09-21 | 181 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-09-21 | 181 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-09-21 | 88 |  |  | 2017-12-18 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Yunk, Jason |  |  | 2017-09-21 | 167 |  |  | 2018-03-07 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-09-21 | 0 |  |  | 2017-09-21 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-09-21 | 5 |  |  | 2017-09-26 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Make Updates |  |  | User | Zahs, Brian |  |  | 2017-09-21 | 5 |  |  | 2017-09-26 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-22 | 290 |  |  |  | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-22 | 33 |  |  | 2017-10-25 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-09-22 | 0 |  |  | 2017-09-21 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-09-22 | 175 |  |  | 2018-03-16 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-09-22 | 52 |  |  | 2017-11-13 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128173 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 290 |  |  |  | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128173 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 290 |  |  |  | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129427 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129427 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-21 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130793 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130793 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133341 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133341 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00134035 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00134035 | Review & Release Calendar |  |  | User | Oliver, Amy |  |  | 2017-09-22 | 0 |  |  | 2017-09-21 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-09-22 | 180 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-22 | 290 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Footnote Edits |  |  | User | Zahs, Brian |  |  | 2017-09-22 | 18 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Zahs, Brian |  |  | 2017-09-22 | 18 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Visit Tolerance Edits |  |  | User | Zahs, Brian |  |  | 2017-09-22 | 18 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Zahs, Brian |  |  | 2017-09-22 | 0 |  |  | 2017-09-22 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-23 | 289 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-09-23 | 289 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-09-23 | 289 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-23 | 34 |  |  | 2017-10-27 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-23 | 2 |  |  | 2017-09-25 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-23 | 30 |  |  | 2017-10-23 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-23 | 289 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-09-23 | 289 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2017-09-23 | 179 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2017-09-23 | 179 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | Acknowledge |  |  | User | VanderElzen, Liz |  |  | 2017-09-23 | 6 |  |  | 2017-09-29 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Zahs, Brian |  |  | 2017-09-23 | 17 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-09-24 | 2 |  |  | 2017-09-26 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-24 | 0 |  |  | 2017-09-24 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-24 | 4 |  |  | 2017-09-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Zahs, Brian |  |  | 2017-09-24 | 16 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Zahs, Brian |  |  | 2017-09-24 | 16 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Request Care Designations |  |  | User | Zahs, Brian |  |  | 2017-09-24 | 16 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | MiChart Verifications |  |  | Role | CTSU Coordinator |  |  | 2017-09-25 | 0 |  |  | 2017-09-25 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-09-25 | 287 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-09-25 | 287 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-09-25 | 0 |  |  | 2017-09-25 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-09-25 | 0 |  |  | 2017-09-25 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-09-25 | 0 |  |  | 2017-09-25 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-25 | 32 |  |  | 2017-10-27 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-25 | 32 |  |  | 2017-10-27 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-09-26 | 286 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-26 | 286 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-26 | 0 |  |  | 2017-09-14 | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-26 | 0 |  |  | 2017-09-14 | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-09-26 | 286 |  |  |  | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-09-26 | 1 |  |  | 2017-09-27 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-09-26 | 1 |  |  | 2017-09-27 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-09-26 | 1 |  |  | 2017-09-27 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-09-26 | 2 |  |  | 2017-09-28 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Planning Meeting Request Sent |  |  | User | Henry, Robin |  |  | 2017-09-26 | 1 |  |  | 2017-09-27 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-09-26 | 1 |  |  | 2017-09-27 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-26 | 44 |  |  | 2017-11-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-26 | 44 |  |  | 2017-11-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-26 | 44 |  |  | 2017-11-09 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | PAN Released |  |  | User | Henry, Robin |  |  | 2017-09-26 | 27 |  |  | 2017-10-23 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-09-26 | 286 |  |  |  | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-09-26 | 7 |  |  | 2017-10-03 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-27 | 285 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-27 | 285 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-09-27 | 285 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-27 | 0 |  |  | 2017-09-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Final Budget |  |  | User | Henry, Robin |  |  | 2017-09-27 | 50 |  |  | 2017-11-16 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-09-27 | 285 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-09-27 | 0 |  |  | 2017-09-19 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-09-28 | 284 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-28 | 284 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-28 | 0 |  |  | 2017-09-13 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-09-28 | 109 |  |  | 2018-01-15 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-28 | 47 |  |  | 2017-11-14 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-28 | 0 |  |  | 2017-09-13 | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-09-28 | 0 |  |  | 2017-09-12 | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-09-28 | 0 |  |  | 2017-09-07 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-09-28 | 284 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-28 | 18 |  |  | 2017-10-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-09-28 | 0 |  |  | 2017-09-07 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-28 | 42 |  |  | 2017-11-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-28 | 42 |  |  | 2017-11-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-28 | 42 |  |  | 2017-11-09 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2017-09-28 | 0 |  |  | 2017-09-28 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-28 | 49 |  |  | 2017-11-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-28 | 1 |  |  | 2017-09-29 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-28 | 0 |  |  | 2017-09-27 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-09-28 | 11 |  |  | 2017-10-09 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2017-09-28 | 174 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-09-29 | 283 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-09-29 | 283 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-09-29 | 38 |  |  | 2017-11-06 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | PAF routed |  |  | User | Henry, Robin |  |  | 2017-09-29 | 48 |  |  | 2017-11-16 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2017-09-29 | 6 |  |  | 2017-10-05 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2017-09-29 | 0 |  |  | 2017-09-28 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-09-29 | 10 |  |  | 2017-10-09 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-09-29 | 283 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-29 | 31 |  |  | 2017-10-30 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-29 | 126 |  |  | 2018-02-02 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-29 | 133 |  |  | 2018-02-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-29 | 81 |  |  | 2017-12-19 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2017-09-29 | 206 |  |  | 2018-04-23 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-09-29 | 0 |  |  | 2017-09-20 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-09-30 | 282 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-09-30 | 282 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-09-30 | 104 |  |  | 2018-01-12 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-09-30 | 52 |  |  | 2017-11-21 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-09-30 | 33 |  |  | 2017-11-02 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-30 | 0 |  |  | 2017-09-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-09-30 | 0 |  |  | 2017-09-29 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-30 | 125 |  |  | 2018-02-02 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-30 | 132 |  |  | 2018-02-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-30 | 192 |  |  | 2018-04-10 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-09-30 | 282 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-09-30 | 101 |  |  | 2018-01-09 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2017-09-30 | 173 |  |  | 2018-03-22 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-09-30 | 282 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-01 | 281 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-01 | 281 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-01 | 15 |  |  | 2017-10-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-01 | 281 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-01 | 131 |  |  | 2018-02-09 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-10-01 | 204 |  |  | 2018-04-23 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-02 | 280 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-02 | 28 |  |  | 2017-10-30 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-10-02 | 0 |  |  | 2017-09-14 | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-02 | 0 |  |  | 2017-09-14 | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-10-02 | 1 |  |  | 2017-10-03 | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-02 | 1 |  |  | 2017-10-03 | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-02 | 0 |  |  | 2017-10-02 | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-02 | 0 |  |  | 2017-10-02 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-10-02 | 280 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-02 | 280 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-10-02 | 31 |  |  | 2017-11-02 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Planning Meeting Completed |  |  | User | VanderElzen, Liz |  |  | 2017-10-02 | 0 |  |  | 2017-09-19 | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-10-02 | 185 |  |  | 2018-04-05 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-03 | 176 |  |  | 2018-03-28 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-03 | 181 |  |  | 2018-04-02 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-03 | 181 |  |  | 2018-04-02 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-03 | 279 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-03 | 106 |  |  | 2018-01-17 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-03 | 27 |  |  | 2017-10-30 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-03 | 0 |  |  | 2017-10-03 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-10-03 | 279 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-10-03 | 279 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-10-03 | 1 |  |  | 2017-10-04 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-10-03 | 202 |  |  | 2018-04-23 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-03 | 0 |  |  | 2017-09-01 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-04 | 278 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-04 | 79 |  |  | 2017-12-22 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-04 | 278 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-04 | 27 |  |  | 2017-10-31 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-04 | 278 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-04 | 125 |  |  | 2018-02-06 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-04 | 6 |  |  | 2017-10-10 | N |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-04 | 0 |  |  | 2017-09-27 | N |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-10-04 | 40 |  |  | 2017-11-13 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-10-04 | 40 |  |  | 2017-11-13 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-10-04 | 8 |  |  | 2017-10-12 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-10-04 | 0 |  |  | 2017-09-28 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2017-10-04 | 40 |  |  | 2017-11-13 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-04 | 30 |  |  | 2017-11-03 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-10-04 | 0 |  |  | 2017-09-20 | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-04 | 0 |  |  | 2017-09-21 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-04 | 278 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-04 | 278 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-05 | 174 |  |  | 2018-03-28 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-05 | 179 |  |  | 2018-04-02 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-05 | 187 |  |  | 2018-04-10 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-05 | 277 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-05 | 277 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-05 | 277 |  |  |  | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-05 | 277 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-05 | 0 |  |  | 2017-09-27 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-05 | 277 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-10-05 | 0 |  |  | 2017-09-21 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-10-05 | 277 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-10-05 | 277 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-10-05 | 99 |  |  | 2018-01-12 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-05 | 277 |  |  |  | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-05 | 277 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-05 | 277 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-05 | 76 |  |  | 2017-12-20 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-06 | 276 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-06 | 276 |  |  |  | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-06 | 171 |  |  | 2018-03-26 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-06 | 0 |  |  | 2017-09-12 | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-10-06 | 0 |  |  | 2017-09-25 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-06 | 0 |  |  | 2017-09-22 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-10-06 | 276 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-10-06 | 276 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-10-06 | 39 |  |  | 2017-11-14 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-10-06 | 106 |  |  | 2018-01-20 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-10-06 | 38 |  |  | 2017-11-13 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-10-06 | 38 |  |  | 2017-11-13 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2017-10-06 | 38 |  |  | 2017-11-13 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2017-10-06 | 276 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-06 | 102 |  |  | 2018-01-16 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline |  |  | 2017-10-06 | 0 |  |  | 2017-10-06 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-07 | 6 |  |  | 2017-10-13 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-07 | 275 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-07 | 275 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-10-07 | 275 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-10-07 | 275 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | OnCore Budget Build |  |  | User | Henry, Robin |  |  | 2017-10-07 | 75 |  |  | 2017-12-21 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-10-07 | 132 |  |  | 2018-02-16 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-10-07 | 38 |  |  | 2017-11-14 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2017-10-07 | 0 |  |  | 2017-09-20 | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-10-07 | 9 |  |  | 2017-10-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-07 | 244 |  |  | 2018-06-08 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-08 | 274 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-08 | 274 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-10-08 | 8 |  |  | 2017-10-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-08 | 243 |  |  | 2018-06-08 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-08 | 243 |  |  | 2018-06-08 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-09 | 273 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-09 | 273 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-09 | 184 |  |  | 2018-04-11 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-09 | 95 |  |  | 2018-01-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-09 | 11 |  |  | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-10-09 | 0 |  |  | 2017-09-28 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-09 | 0 |  |  | 2017-09-28 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-09 | 0 |  |  | 2017-10-09 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-10-09 | 273 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-10-09 | 273 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-09 | 21 |  |  | 2017-10-30 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-09 | 21 |  |  | 2017-10-30 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-10-09 | 273 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-10 | 272 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-10 | 272 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-10-10 | 22 |  |  | 2017-11-01 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-10 | 0 |  |  | 2017-10-03 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-10-10 | 3 |  |  | 2017-10-13 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-10-10 | 1 |  |  | 2017-10-11 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2017-10-10 | 0 |  |  | 2017-10-10 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-10 | 272 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-11 | 173 |  |  | 2018-04-02 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-11 | 173 |  |  | 2018-04-02 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-11 | 182 |  |  | 2018-04-11 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-11 | 114 |  |  | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-11 | 271 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-11 | 0 |  |  | 2017-10-11 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-10-11 | 271 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-10-11 | 271 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-10-11 | 271 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-10-11 | 33 |  |  | 2017-11-13 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-10-11 | 15 |  |  | 2017-10-26 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-10-11 | 141 |  |  | 2018-03-01 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-10-11 | 34 |  |  | 2017-11-14 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-11 | 271 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-10-11 | 22 |  |  | 2017-11-02 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-12 | 270 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-12 | 0 |  |  | 2017-10-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-12 | 0 |  |  | 2017-10-12 | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | IRB Approval |  |  | Role | CTSU Coordinator |  |  | 2017-10-12 | 0 |  |  | 2017-10-12 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-12 | 0 |  |  | 2017-10-12 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-12 | 168 |  |  | 2018-03-29 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-10-12 | 113 |  |  | 2018-02-02 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-10-12 | 0 |  |  | 2017-10-12 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-10-12 | 0 |  |  | 2017-10-11 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 359-SMITH | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-12 | 113 |  |  | 2018-02-02 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-12 | 145 |  |  | 2018-03-06 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-12 | 270 |  |  |  | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Request Research Pharmacy Budget |  |  | User | Oliver, Amy |  |  | 2017-10-12 | 19 |  |  | 2017-10-31 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-12 | 161 |  |  | 2018-03-22 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-10-12 | 270 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2017-10-12 | 270 |  |  |  | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 326-HIGGINS | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim |  |  | 2017-10-12 | 68 |  |  | 2017-12-19 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-13 | 269 |  |  |  | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-13 | 269 |  |  |  | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-13 | 0 |  |  | 2017-10-13 | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-13 | 0 |  |  | 2017-10-13 | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-10-13 | 269 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-10-13 | 70 |  |  | 2017-12-22 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-10-13 | 5 |  |  | 2017-10-18 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-13 | 0 |  |  | 2017-10-13 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-13 | 5 |  |  | 2017-10-18 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-13 | 13 |  |  | 2017-10-26 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-10-13 | 269 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-13 | 269 |  |  |  | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-13 | 55 |  |  | 2017-12-07 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-13 | 195 |  |  | 2018-04-26 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-10-13 | 0 |  |  | 2017-10-13 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-10-13 | 0 |  |  | 2017-10-12 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-10-13 | 0 |  |  | 2017-10-13 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-14 | 268 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-14 | 28 |  |  | 2017-11-11 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-14 | 0 |  |  | 2017-09-14 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-14 | 268 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-10-14 | 268 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-10-14 | 268 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-10-14 | 139 |  |  | 2018-03-02 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-10-14 | 31 |  |  | 2017-11-14 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz |  |  | 2017-10-14 | 268 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-15 | 102 |  |  | 2018-01-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-10-15 | 0 |  |  | 2017-10-09 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-15 | 0 |  |  | 2017-10-06 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-10-15 | 267 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-10-15 | 3 |  |  | 2017-10-18 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-15 | 12 |  |  | 2017-10-27 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-15 | 15 |  |  | 2017-10-30 | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-10-15 | 0 |  |  | 2017-10-13 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-10-15 | 2 |  |  | 2017-10-17 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-16 | 266 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-16 | 266 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-16 | 44 |  |  | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-10-16 | 266 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-16 | 266 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Nimblify Build is Complete & Ready for Import |  |  | User | Greene, Paula |  |  | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-10-16 | 137 |  |  | 2018-03-02 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Internal Budget Finished |  |  | User | VanderElzen, Liz |  |  | 2017-10-16 | 266 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Calendar build assigned to CRAO | [6 empty] | 2017-10-16 | 2 |  |  | 2017-10-18 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Calendar build assigned to CRAO | [6 empty] | 2017-10-16 | 0 |  |  | 2017-10-16 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-10-16 | 0 |  |  | 2016-10-16 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-17 | 0 |  |  | 2017-10-17 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-17 | 265 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-17 | 265 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-17 | 265 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-10-17 | 265 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-17 | 0 |  |  | 2017-10-17 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-10-17 | 0 |  |  | 2017-10-17 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-17 | 0 |  |  | 2017-10-17 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 370-LOK | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-17 | 265 |  |  |  | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-17 | 265 |  |  |  | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-17 | 265 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-18 | 264 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-18 | 0 |  |  | 2017-09-25 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-10-18 | 264 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-10-18 | 264 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-10-18 | 264 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-10-18 | 264 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-18 | 264 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-19 | 263 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-19 | 0 |  |  | 2017-09-20 | N |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-19 | 0 |  |  | 2017-10-19 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-10-19 | 263 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-10-19 | 263 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-10-19 | 6 |  |  | 2017-10-25 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | PI approved Budget |  |  | User | VanderElzen, Liz |  |  | 2017-10-19 | 263 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Planning Meeting Request Sent |  |  | User | Wu, Elizabeth |  |  | 2017-10-19 | 0 |  |  | 2017-10-17 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-19 | 263 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) |  |  | User | Zahs, Brian |  |  | 2017-10-19 | 0 |  |  | 2017-10-19 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Complete Calendar ( ie. Flag as Ready for Financials ) |  |  | User | Zahs, Brian |  |  | 2017-10-19 | 0 |  |  | 2017-10-19 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar |  |  | User | Zahs, Brian |  |  | 2017-10-19 | 0 |  |  | 2017-10-19 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) |  |  | User | van Dijk, Tim |  |  | 2017-10-19 | 0 |  |  | 2017-10-18 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Complete Calendar ( ie. Flag as Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-10-19 | 0 |  |  | 2017-10-18 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar |  |  | User | van Dijk, Tim |  |  | 2017-10-19 | 0 |  |  | 2017-10-18 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-20 | 262 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-20 | 3 |  |  | 2017-10-23 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-10-20 | 3 |  |  | 2017-10-23 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2017-10-20 | 11 |  |  | 2017-10-31 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2017-10-20 | 0 |  |  | 2017-10-17 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2017-10-20 | 5 |  |  | 2017-10-25 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-20 | 186 |  |  | 2018-04-24 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-20 | 186 |  |  | 2018-04-24 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-20 | 262 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Billing Calendar Received |  |  | User | Oliver, Amy |  |  | 2017-10-20 | 48 |  |  | 2017-12-07 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-20 | 137 |  |  | 2018-03-06 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2017-10-20 | 186 |  |  | 2018-04-24 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2017-10-20 | 186 |  |  | 2018-04-24 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Confirm calendar build completed | [6 empty] | 2017-10-20 | 0 |  |  | 2017-10-20 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Confirm calendar build completed | [6 empty] | 2017-10-20 | 0 |  |  | 2017-10-19 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-21 | 261 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-21 | 261 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-10-21 | 6 |  |  | 2017-10-27 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00122910 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-10-21 | 6 |  |  | 2017-10-27 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-22 | 101 |  |  | 2018-01-31 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-22 | 0 |  |  | 2017-10-19 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-22 | 260 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-10-22 | 260 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2017-10-22 | 54 |  |  | 2017-12-15 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-10-22 | 0 |  |  | 2017-10-17 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-10-22 | 0 |  |  | 2017-10-16 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2017-10-22 | 260 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-23 | 259 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-23 | 259 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-23 | 259 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-23 | 259 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-10-23 | 0 |  |  | 2017-10-09 | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-23 | 0 |  |  | 2017-10-06 | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-23 | 259 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-10-23 | 259 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 381-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-23 | 259 |  |  |  | N |  | 381-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Final Budget |  |  | User | Oliver, Amy |  |  | 2017-10-23 | 0 |  |  | 2017-09-20 | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 359-SMITH | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian |  |  | 2017-10-23 | 0 |  |  | 2017-10-23 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Complete MCA / QCT |  |  | User | Zahs, Brian |  |  | 2017-10-23 | 25 |  |  | 2017-11-17 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian |  |  | 2017-10-23 | 0 |  |  | 2017-10-23 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian |  |  | 2017-10-23 | 4 |  |  | 2017-10-27 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2017-10-23 | 1 |  |  | 2017-10-24 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2017-10-23 | 1 |  |  | 2017-10-24 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2017-10-23 | 7 |  |  | 2017-10-30 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-24 | 43 |  |  | 2017-12-06 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-24 | 44 |  |  | 2017-12-07 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-10-24 | 99 |  |  | 2018-01-31 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-24 | 9 |  |  | 2017-11-02 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-24 | 0 |  |  | 2017-10-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-10-24 | 258 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-10-24 | 101 |  |  | 2018-02-02 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-10-24 | 114 |  |  | 2018-02-15 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-24 | 258 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-10-24 | 258 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-10-24 | 8 |  |  | 2017-11-01 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-10-24 | 86 |  |  | 2018-01-18 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-10-24 | 86 |  |  | 2018-01-18 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-10-25 | 257 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-10-25 | 257 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-10-25 | 257 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2017-10-25 | 0 |  |  | 2017-10-25 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Make Updates |  |  | User | Hodges, Lynda |  |  | 2017-10-25 | 0 |  |  | 2017-10-25 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | PAF routed |  |  | User | Oliver, Amy |  |  | 2017-10-25 | 0 |  |  | 2017-09-20 | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Zahs, Brian |  |  | 2017-10-25 | 23 |  |  | 2017-11-17 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Zahs, Brian |  |  | 2017-10-25 | 23 |  |  | 2017-11-17 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2017-10-25 | 5 |  |  | 2017-10-30 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-10-25 | 5 |  |  | 2017-10-30 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-26 | 256 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 256 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 256 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 0 |  |  | 2017-09-18 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 256 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 84 |  |  | 2018-01-18 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 166 |  |  | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Initial Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | Acknowledge |  |  | User | Oliver, Amy |  |  | 2017-10-26 | 256 |  |  |  | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-10-26 | 6 |  |  | 2017-11-01 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-10-26 | 6 |  |  | 2017-11-01 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-26 | 256 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Update on subject data collection status - see communications | [6 empty] | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Update on training status - see communications | [6 empty] | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Update on subject data collection status - see communications | [6 empty] | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Update on training status - see communications | [6 empty] | 2017-10-26 | 0 |  |  | 2017-10-26 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Confirm budget build completed and calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-10-27 | 3 |  |  | 2017-10-30 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-10-27 | 3 |  |  | 2017-10-30 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Confirm budget build completed and calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-10-27 | 3 |  |  | 2017-10-30 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-10-27 | 3 |  |  | 2017-10-30 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-10-27 | 0 |  |  | 2017-10-27 | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-10-27 | 255 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-10-27 | 255 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-10-27 | 124 |  |  | 2018-02-28 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-10-27 | 0 |  |  | 2017-10-27 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-10-27 | 0 |  |  | 2017-10-26 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-27 | 255 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Care Designations completed |  |  | User | Oliver, Amy |  |  | 2017-10-27 | 45 |  |  | 2017-12-11 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-27 | 165 |  |  | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-10-28 | 254 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-10-28 | 17 |  |  | 2017-11-14 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-28 | 73 |  |  | 2018-01-09 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-28 | 186 |  |  | 2018-05-02 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-10-28 | 254 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-28 | 254 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-10-29 | 253 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-10-29 | 253 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-10-29 | 253 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Final Budget |  |  | User | Henry, Robin |  |  | 2017-10-29 | 0 |  |  | 2017-10-25 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-29 | 253 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-30 | 252 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-10-30 | 252 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-10-30 | 0 |  |  | 2017-10-10 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-10-30 | 0 |  |  | 2017-10-30 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-10-30 | 0 |  |  | 2017-10-30 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-30 | 154 |  |  | 2018-04-02 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-30 | 252 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-10-30 | 252 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-10-30 | 252 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-10-30 | 252 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-10-30 | 252 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-10-30 | 0 |  |  | 2017-10-30 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-10-30 | 135 |  |  | 2018-03-14 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-10-30 | 15 |  |  | 2017-11-14 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-10-30 | 1 |  |  | 2017-10-31 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-10-30 | 78 |  |  | 2018-01-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 396-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-10-30 | 252 |  |  |  | N |  | 396-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-10-30 | 0 |  |  | 2017-10-29 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-31 | 135 |  |  | 2018-03-15 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-10-31 | 251 |  |  |  | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-10-31 | 0 |  |  | 2017-08-30 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-10-31 | 251 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | PAF routed |  |  | User | Henry, Robin |  |  | 2017-10-31 | 0 |  |  | 2017-10-26 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-10-31 | 0 |  |  | 2017-10-31 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 346-BAPTIST | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2017-10-31 | 0 |  |  | 2017-10-31 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-10-31 | 251 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-01 | 250 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-01 | 250 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-01 | 0 |  |  | 2017-10-18 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-11-01 | 0 |  |  | 2017-10-30 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-11-01 | 0 |  |  | 2017-10-30 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-01 | 160 |  |  | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-11-01 | 250 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-01 | 250 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-11-01 | 250 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-11-01 | 250 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-11-01 | 72 |  |  | 2018-01-12 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-11-01 | 145 |  |  | 2018-03-26 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-11-01 | 0 |  |  | 2017-04-28 | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-11-01 | 103 |  |  | 2018-02-12 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-11-01 | 107 |  |  | 2018-02-16 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-11-01 | 27 |  |  | 2017-11-28 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-01 | 250 |  |  |  | N |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-01 | 250 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-02 | 0 |  |  | 2017-04-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-02 | 146 |  |  | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-02 | 249 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-11-02 | 0 |  |  | 2017-11-02 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-02 | 249 |  |  |  | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-11-02 | 249 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-11-02 | 0 |  |  | 2017-09-27 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-11-02 | 249 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-11-02 | 0 |  |  | 2017-10-30 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | AME Calendaring Process Initiated |  |  | User | VanderElzen, Liz |  |  | 2017-11-02 | 0 |  |  | 2017-11-02 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-02 | 249 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-02 | 249 |  |  |  | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-03 | 248 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-03 | 248 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-03 | 248 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-03 | 7 |  |  | 2017-11-10 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-11-03 | 0 |  |  | 2017-11-03 | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-03 | 0 |  |  | 2017-11-01 | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-11-03 | 0 |  |  | 2017-10-19 | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-03 | 0 |  |  | 2017-11-03 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-11-03 | 0 |  |  | 2017-10-30 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-11-03 | 0 |  |  | 2017-10-27 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | AME Calendaring Process Initiated |  |  | User | Henry, Robin |  |  | 2017-11-03 | 0 |  |  | 2017-11-03 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | OnCore Budget Build |  |  | User | Henry, Robin |  |  | 2017-11-03 | 48 |  |  | 2017-12-21 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-03 | 248 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-03 | 248 |  |  |  | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-03 | 139 |  |  | 2018-03-22 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-03 | 139 |  |  | 2018-03-22 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2017-11-03 | 28 |  |  | 2017-12-01 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Make Updates |  |  | User | van Dijk, Tim |  |  | 2017-11-03 | 28 |  |  | 2017-12-01 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Confirm calendar build completed |  |  | User | van Dijk, Tim |  |  | 2017-11-03 | 0 |  |  | 2017-10-31 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-04 | 193 |  |  | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-04 | 247 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-11-04 | 247 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-11-04 | 0 |  |  | 2017-11-02 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2017-11-04 | 0 |  |  | 2017-10-31 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-04 | 208 |  |  | 2018-05-31 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Final Budget |  |  | User | VanderElzen, Liz |  |  | 2017-11-04 | 247 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-05 | 115 |  |  | 2018-02-28 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-11-05 | 0 |  |  | 2017-09-27 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-11-05 | 116 |  |  | 2018-03-01 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-11-05 | 137 |  |  | 2018-03-22 | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-11-05 | 29 |  |  | 2017-12-04 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-05 | 0 |  |  | 2017-11-03 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-05 | 0 |  |  | 2017-11-03 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-06 | 245 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-06 | 245 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-06 | 245 |  |  |  | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-06 | 0 |  |  | 2017-11-06 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-11-06 | 0 |  |  | 2017-10-11 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-11-06 | 22 |  |  | 2017-11-28 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-11-06 | 0 |  |  | 2017-11-03 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Calendar build assigned to CRAO |  |  | User | Hess, Aaron |  |  | 2017-11-06 | 0 |  |  | 2017-11-06 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-06 | 0 |  |  | 2017-11-06 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-06 | 0 |  |  | 2017-11-03 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | PAF routed |  |  | User | VanderElzen, Liz |  |  | 2017-11-06 | 245 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-11-06 | 0 |  |  | 2017-11-06 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-11-06 | 0 |  |  | 2017-11-06 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-07 | 146 |  |  | 2018-04-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-07 | 0 |  |  | 2017-11-07 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-11-07 | 6 |  |  | 2017-11-13 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-07 | 0 |  |  | 2017-11-06 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-07 | 0 |  |  | 2017-11-03 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-07 | 244 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2017-11-07 | 0 |  |  | 2017-11-07 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-08 | 243 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-08 | 243 |  |  |  | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-08 | 0 |  |  | 2017-11-08 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-11-08 | 100 |  |  | 2018-02-16 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-11-08 | 243 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-08 | 243 |  |  |  | N |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-08 | 243 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-08 | 0 |  |  | 2017-11-06 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-08 | 0 |  |  | 2017-11-06 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2017-11-08 | 0 |  |  | 2017-11-07 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-11-09 | 242 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-09 | 242 |  |  |  | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-09 | 61 |  |  | 2018-01-09 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-11-09 | 0 |  |  | 2017-10-11 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-11-09 | 242 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2017-11-09 | 0 |  |  | 2017-11-09 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-09 | 0 |  |  | 2017-11-07 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2017-11-09 | 7 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | van Dijk, Tim |  |  | 2017-11-09 | 7 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Update on subject data collection status - see communications | [6 empty] | 2017-11-09 | 242 |  |  |  | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Update on training status - see communications | [6 empty] | 2017-11-09 | 242 |  |  |  | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-11-10 | 241 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-11-10 | 241 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-10 | 87 |  |  | 2018-02-05 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Confirm budget build completed and calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-11-10 | 3 |  |  | 2017-11-13 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-11-10 | 3 |  |  | 2017-11-13 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-11-10 | 0 |  |  | 2017-11-09 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-11-10 | 0 |  |  | 2017-11-03 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-10 | 0 |  |  | 2017-10-31 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-10 | 0 |  |  | 2017-11-10 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-10 | 241 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-11-10 | 19 |  |  | 2017-11-29 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-11-10 | 18 |  |  | 2017-11-28 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Confirm calendar build completed |  |  | User | Hess, Aaron |  |  | 2017-11-10 | 0 |  |  | 2017-11-10 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-10 | 241 |  |  |  | N |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-10 | 0 |  |  | 2017-11-07 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-10 | 0 |  |  | 2017-11-07 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2017-11-10 | 6 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-11 | 240 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-11-11 | 0 |  |  | 2017-11-10 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-11-11 | 240 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-11-11 | 240 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-11-11 | 240 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-11 | 0 |  |  | 2017-11-07 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-11-11 | 5 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Update RSH Source in MBECT |  |  | User | van Dijk, Tim |  |  | 2017-11-11 | 5 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-11-12 | 239 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-11-12 | 0 |  |  | 2017-11-03 | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-11-12 | 239 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-11-12 | 239 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-11-12 | 239 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2017-11-12 | 5 |  |  | 2017-11-17 | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-11-12 | 128 |  |  | 2018-03-20 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-13 | 238 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-13 | 238 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-13 | 238 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-11-13 | 238 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-11-13 | 238 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-11-13 | 32 |  |  | 2017-12-15 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-13 | 238 |  |  |  | N |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Calendar build assigned to CRAO |  |  | User | Zahs, Brian |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Calendar build assigned to CRAO |  |  | User | van Dijk, Tim |  |  | 2017-11-13 | 0 |  |  | 2017-11-13 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-11-14 | 0 |  |  | 2017-11-10 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-11-14 | 237 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-11-14 | 237 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2017-11-14 | 0 |  |  | 2017-11-14 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-14 | 35 |  |  | 2017-12-19 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-14 | 0 |  |  | 2017-11-03 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2017-11-14 | 36 |  |  | 2017-12-20 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-11-15 | 0 |  |  | 2017-11-13 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-15 | 0 |  |  | 2017-11-10 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-11-15 | 236 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-11-15 | 236 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-11-15 | 236 |  |  |  | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-11-15 | 138 |  |  | 2018-04-02 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-11-15 | 48 |  |  | 2018-01-02 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-15 | 236 |  |  |  | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-15 | 236 |  |  |  | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-15 | 0 |  |  | 2017-11-06 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-15 | 236 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-11-16 | 3 |  |  | 2017-11-19 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-16 | 0 |  |  | 2017-11-16 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-16 | 0 |  |  | 2017-11-16 | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-11-16 | 235 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-11-16 | 235 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2017-11-16 | 29 |  |  | 2017-12-15 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Huffman, Kate |  |  | 2017-11-16 | 0 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-16 | 235 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2017-11-16 | 0 |  |  | 2017-11-16 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-16 | 235 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Update on subject data collection status - see communications | [6 empty] | 2017-11-16 | 235 |  |  |  | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Update on training status - see communications | [6 empty] | 2017-11-16 | 235 |  |  |  | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-17 | 234 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-11-17 | 10 |  |  | 2017-11-27 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-11-17 | 10 |  |  | 2017-11-27 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-17 | 63 |  |  | 2018-01-19 | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-11-17 | 136 |  |  | 2018-04-02 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-11-17 | 0 |  |  | 2017-11-16 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-17 | 234 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2017-11-17 | 5 |  |  | 2017-11-22 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-17 | 234 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Confirm calendar build completed |  |  | User | Zahs, Brian |  |  | 2017-11-17 | 0 |  |  | 2017-11-13 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Confirm calendar build completed |  |  | User | van Dijk, Tim |  |  | 2017-11-17 | 0 |  |  | 2017-11-15 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-11-18 | 233 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-18 | 233 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2017-11-18 | 0 |  |  | 2017-11-16 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-19 | 232 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-11-19 | 232 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-11-19 | 0 |  |  | 2017-11-07 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-20 | 231 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-20 | 2 |  |  | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-20 | 0 |  |  | 2017-11-20 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-20 | 231 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-11-20 | 231 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-11-20 | 231 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-11-20 | 231 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2017-11-20 | 231 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-20 | 231 |  |  |  | N |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2017-11-20 | 0 |  |  | 2017-11-20 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-11-20 | 231 |  |  |  | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-11-20 | 0 |  |  | 2017-11-20 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-11-20 | 0 |  |  | 2017-11-13 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-11-20 | 0 |  |  | 2017-11-13 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-21 | 230 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-21 | 230 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-21 | 0 |  |  | 2017-11-21 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-11-21 | 0 |  |  | 2017-09-27 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | AME Calendaring Process Initiated |  |  | User | Huffman, Kate |  |  | 2017-11-21 | 0 |  |  | 2017-11-21 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-21 | 230 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-11-21 | 27 |  |  | 2017-12-18 | N |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-22 | 229 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-22 | 229 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-23 | 228 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-23 | 228 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-11-23 | 0 |  |  | 2017-09-29 | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-11-23 | 228 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-11-23 | 228 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-23 | 126 |  |  | 2018-03-29 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Assign to Analyst |  |  | User | Zahs, Brian |  |  | 2017-11-23 | 0 |  |  | 2017-11-22 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-11-24 | 227 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-11-24 | 0 |  |  | 2017-11-20 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-11-24 | 3 |  |  | 2017-11-27 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-24 | 227 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-11-24 | 227 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-11-24 | 227 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2017-11-24 | 227 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-24 | 227 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Footnote Edits |  |  | User | Zahs, Brian |  |  | 2017-11-24 | 3 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Zahs, Brian |  |  | 2017-11-24 | 3 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Visit Tolerance Edits |  |  | User | Zahs, Brian |  |  | 2017-11-24 | 3 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Zahs, Brian |  |  | 2017-11-24 | 3 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-25 | 226 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-11-25 | 2 |  |  | 2017-11-27 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-11-25 | 0 |  |  | 2017-10-11 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-11-25 | 226 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-25 | 226 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Zahs, Brian |  |  | 2017-11-25 | 2 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-26 | 134 |  |  | 2018-04-09 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-11-26 | 225 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-11-26 | 225 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-11-26 | 225 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-11-26 | 225 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Final Budget |  |  | User | Henry, Robin |  |  | 2017-11-26 | 130 |  |  | 2018-04-05 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Other |  |  | User | Zahs, Brian |  |  | 2017-11-26 | 1 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Zahs, Brian |  |  | 2017-11-26 | 1 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | ** Visits : Addition or Removal of Time Points |  |  | User | Zahs, Brian |  |  | 2017-11-26 | 1 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Request Care Designations |  |  | User | Zahs, Brian |  |  | 2017-11-26 | 1 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Update RSH Source in MBECT |  |  | User | Zahs, Brian |  |  | 2017-11-26 | 1 |  |  | 2017-11-27 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-27 | 224 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-11-27 | 0 |  |  | 2017-10-11 | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-11-27 | 224 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2017-11-27 | 224 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-11-27 | 0 |  |  | 2017-11-27 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-28 | 192 |  |  | 2018-06-08 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-11-28 | 223 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-28 | 9 |  |  | 2017-12-07 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-11-28 | 0 |  |  | 2017-11-28 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-28 | 0 |  |  | 2017-11-28 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-28 | 0 |  |  | 2017-11-28 | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-28 | 223 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Henry, Robin |  |  | 2017-11-28 | 2 |  |  | 2017-11-30 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 458-HERMAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-28 | 223 |  |  |  | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-28 | 223 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Footnote Edits |  |  | User | van Dijk, Tim |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | van Dijk, Tim |  |  | 2017-11-28 | 0 |  |  | 2017-11-27 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-11-29 | 64 |  |  | 2018-02-01 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00100452 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-11-29 | 0 |  |  | 2017-11-28 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-11-29 | 0 |  |  | 2017-11-27 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-11-29 | 0 |  |  | 2017-11-08 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-29 | 0 |  |  | 2017-11-29 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-11-29 | 0 |  |  | 2017-11-29 | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-29 | 222 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-11-29 | 48 |  |  | 2018-01-16 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2017-11-29 | 0 |  |  | 2017-11-27 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-29 | 222 |  |  |  | N |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-29 | 222 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2017-11-29 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-11-29 | 222 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-11-30 | 221 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-11-30 | 0 |  |  | 2017-11-30 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-11-30 | 221 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-11-30 | 221 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda |  |  | 2017-11-30 | 0 |  |  | 2017-11-30 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2017-11-30 | 0 |  |  | 2017-11-27 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 462-AUCHUS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-11-30 | 221 |  |  |  | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-11-30 | 221 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne |  |  | 2017-11-30 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2017-11-30 | 0 |  |  | 2017-11-27 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Update on subject data collection status - see communications | [6 empty] | 2017-11-30 | 221 |  |  |  | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Update on training status - see communications | [6 empty] | 2017-11-30 | 221 |  |  |  | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Update on subject data collection status - see communications | [6 empty] | 2017-11-30 | 221 |  |  |  | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Update on training status - see communications | [6 empty] | 2017-11-30 | 221 |  |  |  | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-01 | 7 |  |  | 2017-12-08 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 220 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Access to all PAFs confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Access to budget/contract confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-11-30 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-11-29 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-11-27 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Sponsor contact info received |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Access to all PAFs confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Access to budget/contract confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Sponsor contact info received |  |  | Role | CTSU Finance |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2017-12-01 | 220 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Final Budget |  |  | User | Henry, Robin |  |  | 2017-12-01 | 137 |  |  | 2018-04-17 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-12-01 | 48 |  |  | 2018-01-18 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Feasibility w/Documents received |  |  | User | Oliver, Amy |  |  | 2017-12-01 | 104 |  |  | 2018-03-15 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2017-12-01 | 0 |  |  | 2017-11-28 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2017-12-01 | 105 |  |  | 2018-03-16 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Budget Build Completed |  |  | User | Yunk, Jason |  |  | 2017-12-01 | 0 |  |  | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-02 | 219 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2017-12-02 | 90 |  |  | 2018-03-02 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-12-02 | 0 |  |  | 2017-12-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-03 | 64 |  |  | 2018-02-05 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-12-03 | 218 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | PAF routed |  |  | User | Henry, Robin |  |  | 2017-12-03 | 142 |  |  | 2018-04-24 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Complete Calendar and Document Approval |  |  | User | Hess, Aaron |  |  | 2017-12-03 | 107 |  |  | 2018-03-20 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-03 | 116 |  |  | 2018-03-29 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 217 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 217 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 4 |  |  | 2017-12-08 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 4 |  |  | 2017-12-08 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 4 |  |  | 2017-12-08 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-04 | 217 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-12-04 | 217 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-12-04 | 217 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Access to all PAFs confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2017-12-04 | 217 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 470-FLAHERTY | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-12-04 | 217 |  |  |  | N |  | 470-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-12-04 | 190 |  |  | 2018-06-12 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-12-04 | 0 |  |  | 2017-12-04 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-05 | 216 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-05 | 31 |  |  | 2018-01-05 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-05 | 0 |  |  | 2017-12-05 | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-05 | 114 |  |  | 2018-03-29 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-12-05 | 216 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2017-12-05 | 0 |  |  | 2017-12-05 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Henry, Robin |  |  | 2017-12-05 | 0 |  |  | 2017-11-28 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-05 | 189 |  |  | 2018-06-12 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136538 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2017-12-05 | 105 |  |  | 2018-03-20 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-06 | 93 |  |  | 2018-03-09 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-06 | 48 |  |  | 2018-01-23 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-06 | 2 |  |  | 2017-12-08 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-06 | 2 |  |  | 2017-12-08 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-06 | 0 |  |  | 2017-12-06 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-12-06 | 215 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2017-12-06 | 215 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Yunk, Jason |  |  | 2017-12-06 | 0 |  |  | 2017-12-06 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Yunk, Jason |  |  | 2017-12-06 | 0 |  |  | 2017-12-06 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-07 | 33 |  |  | 2018-01-09 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-07 | 214 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-07 | 13 |  |  | 2017-12-20 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-07 | 29 |  |  | 2018-01-05 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-07 | 0 |  |  | 2017-12-01 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-07 | 0 |  |  | 2017-12-01 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-07 | 214 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-12-07 | 46 |  |  | 2018-01-22 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-12-07 | 214 |  |  |  | N |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2017-12-07 | 0 |  |  | 2017-11-27 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2017-12-07 | 0 |  |  | 2017-12-07 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2017-12-07 | 0 |  |  | 2017-11-30 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Update on subject data collection status - see communications | [6 empty] | 2017-12-07 | 214 |  |  |  | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Update on training status - see communications | [6 empty] | 2017-12-07 | 214 |  |  |  | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Update on subject data collection status - see communications | [6 empty] | 2017-12-07 | 214 |  |  |  | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Update on training status - see communications | [6 empty] | 2017-12-07 | 214 |  |  |  | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 152 |  |  | 2018-05-09 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 213 |  |  |  | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-08 | 3 |  |  | 2017-12-11 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-08 | 213 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-12-08 | 213 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Transition Checklist signed by department |  |  | Role | CTSU Finance |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Access to budget/contract confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Confirm calendar build completed |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-08 | 0 |  |  | 2017-12-06 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Feasibility approved/CRAO Notified |  |  | User | Oliver, Amy |  |  | 2017-12-08 | 97 |  |  | 2018-03-15 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Transition Checklist signed by department |  |  | User | Oliver, Amy |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2017-12-08 | 0 |  |  | 2017-12-07 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Access to all PAFs confirmed |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Budget Build Completed |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Finance Validation Checklist Completed |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | SAPOC Changed |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Transition Checklist signed by department |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Budget Build Completed |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Finance Validation Checklist Completed |  |  | User | Yunk, Jason |  |  | 2017-12-08 | 0 |  |  | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-09 | 0 |  |  | 2017-12-08 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-12-09 | 212 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-12-09 | 2 |  |  | 2017-12-11 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2017-12-09 | 2 |  |  | 2017-12-11 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-12-09 | 9 |  |  | 2017-12-18 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-12-09 | 0 |  |  | 2017-11-28 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-10 | 207 |  |  | 2018-07-05 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-10 | 0 |  |  | 2017-12-10 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-10 | 0 |  |  | 2017-11-13 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-11 | 210 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-11 | 0 |  |  | 2017-11-30 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-11 | 210 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-12-11 | 210 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-12-11 | 210 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Access to all PAFs confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Access to budget/contract confirmed |  |  | Role | CTSU Finance |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-12-11 | 210 |  |  |  | N |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | SAPOC Changed |  |  | User | Yunk, Jason |  |  | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-12-11 | 0 |  |  | 2017-12-11 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-12 | 99 |  |  | 2018-03-21 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-12 | 0 |  |  | 2017-12-11 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-12 | 7 |  |  | 2017-12-19 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-12 | 7 |  |  | 2017-12-19 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-12-12 | 209 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Received Protocol Amendment |  |  | User | Henry, Robin |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-12-12 | 2 |  |  | 2017-12-14 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-12-12 | 0 |  |  | 2017-12-11 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-12-12 | 209 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Calendar Released |  |  | User | Yunk, Jason |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Finance Validation Checklist Completed |  |  | User | Yunk, Jason |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | SAPOC Changed |  |  | User | Yunk, Jason |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Transition Checklist signed by department |  |  | User | Yunk, Jason |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | OnCore Billing Calendar Change Needed |  |  | User | van Dijk, Tim |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | OnCore Billing Calendar Completed |  |  | User | van Dijk, Tim |  |  | 2017-12-12 | 0 |  |  | 2017-12-12 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-13 | 8 |  |  | 2017-12-21 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-13 | 0 |  |  | 2017-12-12 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-13 | 8 |  |  | 2017-12-21 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-13 | 208 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 208 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 208 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Transition Checklist signed by department |  |  | Role | CTSU Finance |  |  | 2017-12-13 | 0 |  |  | 2017-12-13 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-13 | 208 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-14 | 43 |  |  | 2018-01-26 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-14 | 207 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-14 | 29 |  |  | 2018-01-12 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-14 | 6 |  |  | 2017-12-20 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-14 | 0 |  |  | 2017-12-12 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-14 | 0 |  |  | 2017-12-12 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-14 | 19 |  |  | 2018-01-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2017-12-14 | 25 |  |  | 2018-01-08 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2017-12-14 | 0 |  |  | 2017-12-14 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2017-12-14 | 0 |  |  | 2017-12-14 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Update on subject data collection status - see communications | [6 empty] | 2017-12-14 | 207 |  |  |  | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Update on training status - see communications | [6 empty] | 2017-12-14 | 207 |  |  |  | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Update on subject data collection status - see communications | [6 empty] | 2017-12-14 | 207 |  |  |  | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Update on training status - see communications | [6 empty] | 2017-12-14 | 207 |  |  |  | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 41 |  |  | 2018-01-25 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 0 |  |  | 2017-12-08 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 0 |  |  | 2017-12-08 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 6 |  |  | 2017-12-21 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 6 |  |  | 2017-12-21 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 6 |  |  | 2017-12-21 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 25 |  |  | 2018-01-09 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 25 |  |  | 2018-01-09 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-15 | 25 |  |  | 2018-01-09 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2017-12-15 | 206 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2017-12-15 | 0 |  |  | 2017-12-15 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-12-15 | 77 |  |  | 2018-03-02 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | PAN Released |  |  | User | Farmer, Amber |  |  | 2017-12-15 | 73 |  |  | 2018-02-26 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-12-15 | 34 |  |  | 2018-01-18 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2017-12-15 | 0 |  |  | 2017-12-12 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Confirm calendar build completed |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-15 | 0 |  |  | 2017-12-13 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2017-12-15 | 0 |  |  | 2017-12-13 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-16 | 205 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-16 | 40 |  |  | 2018-01-25 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-16 | 0 |  |  | 2017-12-12 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-16 | 0 |  |  | 2017-12-12 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-16 | 41 |  |  | 2018-01-26 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-16 | 205 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-12-16 | 205 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-12-16 | 205 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-12-16 | 39 |  |  | 2018-01-24 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-16 | 18 |  |  | 2018-01-03 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-16 | 18 |  |  | 2018-01-03 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2017-12-16 | 0 |  |  | 2017-12-14 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2017-12-16 | 0 |  |  | 2017-12-14 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-12-17 | 193 |  |  | 2018-06-28 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 503-JAYASUNDERA | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2017-12-17 | 193 |  |  | 2018-06-28 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 203 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 0 |  |  | 2017-12-10 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 4 |  |  | 2017-12-22 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 4 |  |  | 2017-12-22 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 3 |  |  | 2017-12-21 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 4 |  |  | 2017-12-22 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-18 | 22 |  |  | 2018-01-09 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2017-12-18 | 203 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Transition Checklist signed by department |  |  | Role | CTSU Finance |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | AME Calendaring Process Initiated |  |  | User | Huffman, Kate |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2017-12-18 | 0 |  |  | 2017-12-18 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-19 | 35 |  |  | 2018-01-23 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-19 | 202 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-12-19 | 41 |  |  | 2018-01-29 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-12-19 | 0 |  |  | 2017-12-13 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-12-19 | 0 |  |  | 2017-12-13 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-19 | 77 |  |  | 2018-03-06 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-19 | 202 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-19 | 202 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-12-19 | 202 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2017-12-19 | 0 |  |  | 2017-12-19 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2017-12-19 | 0 |  |  | 2017-12-19 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-12-19 | 28 |  |  | 2018-01-16 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2017-12-19 | 0 |  |  | 2017-12-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 26 |  |  | 2018-01-15 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 201 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 40 |  |  | 2018-01-29 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 0 |  |  | 2017-12-13 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 0 |  |  | 2017-12-13 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 1 |  |  | 2017-12-21 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-20 | 2 |  |  | 2017-12-22 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-20 | 0 |  |  | 2017-12-08 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-20 | 0 |  |  | 2017-12-06 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-20 | 0 |  |  | 2017-12-05 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Final Budget |  |  | Role | CTSU Finance |  |  | 2017-12-20 | 201 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2017-12-20 | 201 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2017-12-20 | 0 |  |  | 2017-12-20 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2017-12-20 | 0 |  |  | 2017-12-18 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Final Budget |  |  | User | De Filippo, Julie |  |  | 2017-12-20 | 201 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-12-20 | 0 |  |  | 2017-12-15 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2017-12-20 | 0 |  |  | 2017-11-27 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2017-12-20 | 0 |  |  | 2017-11-30 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-21 | 22 |  |  | 2018-01-12 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-21 | 200 |  |  |  | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-12-21 | 200 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-12-21 | 200 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance |  |  | 2017-12-21 | 0 |  |  | 2017-12-21 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-21 | 0 |  |  | 2017-12-21 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-21 | 0 |  |  | 2017-12-21 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Farmer, Amber |  |  | 2017-12-21 | 0 |  |  | 2017-12-21 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2017-12-21 | 0 |  |  | 2017-12-21 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2017-12-21 | 0 |  |  | 2017-12-21 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-12-21 | 0 |  |  | 2017-12-20 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2017-12-21 | 0 |  |  | 2017-12-20 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 24 |  |  | 2018-01-15 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 0 |  |  | 2017-12-21 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-22 | 18 |  |  | 2018-01-09 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-22 | 67 |  |  | 2018-02-27 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | PAF routed |  |  | Role | CTSU Finance |  |  | 2017-12-22 | 199 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | PAF routed |  |  | User | De Filippo, Julie |  |  | 2017-12-22 | 199 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2017-12-22 | 0 |  |  | 2017-12-22 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-12-22 | 28 |  |  | 2018-01-19 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2017-12-22 | 0 |  |  | 2017-11-16 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2017-12-22 | 0 |  |  | 2017-12-22 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-22 | 0 |  |  | 2017-12-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-22 | 0 |  |  | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-12-22 | 199 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-23 | 31 |  |  | 2018-01-23 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-23 | 10 |  |  | 2018-01-02 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-12-23 | 13 |  |  | 2018-01-05 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2017-12-23 | 17 |  |  | 2018-01-09 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-23 | 198 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-23 | 0 |  |  | 2017-12-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-23 | 0 |  |  | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-23 | 0 |  |  | 2017-12-21 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-23 | 0 |  |  | 2017-12-21 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-12-23 | 198 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2017-12-23 | 198 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-24 | 22 |  |  | 2018-01-15 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2017-12-24 | 197 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-12-24 | 0 |  |  | 2017-12-21 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-12-24 | 53 |  |  | 2018-02-15 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-24 | 197 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Calendar Released |  |  | User | Oliver, Amy |  |  | 2017-12-24 | 197 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-24 | 0 |  |  | 2017-12-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-24 | 0 |  |  | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-25 | 196 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-25 | 15 |  |  | 2018-01-09 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-25 | 17 |  |  | 2018-01-11 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-25 | 15 |  |  | 2018-01-09 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2017-12-25 | 15 |  |  | 2018-01-09 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-25 | 196 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-25 | 57 |  |  | 2018-02-20 | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-25 | 57 |  |  | 2018-02-20 | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2017-12-25 | 196 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-12-25 | 196 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-25 | 18 |  |  | 2018-01-12 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2017-12-25 | 18 |  |  | 2018-01-12 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 518-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2017-12-25 | 196 |  |  |  | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2017-12-25 | 14 |  |  | 2018-01-08 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Make Updates |  |  | User | Przykucki, Anne |  |  | 2017-12-25 | 14 |  |  | 2018-01-08 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-26 | 195 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-26 | 48 |  |  | 2018-02-12 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-26 | 195 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-26 | 195 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-12-26 | 30 |  |  | 2018-01-25 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2017-12-26 | 7 |  |  | 2018-01-02 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-26 | 195 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-26 | 195 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-12-26 | 27 |  |  | 2018-01-22 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 194 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 194 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 23 |  |  | 2018-01-19 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 194 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 58 |  |  | 2018-02-23 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 27 |  |  | 2018-01-23 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 33 |  |  | 2018-01-29 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 27 |  |  | 2018-01-23 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 6 |  |  | 2018-01-02 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2017-12-27 | 23 |  |  | 2018-01-19 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2017-12-27 | 12 |  |  | 2018-01-08 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2017-12-27 | 6 |  |  | 2018-01-02 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-12-27 | 13 |  |  | 2018-01-09 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-12-27 | 13 |  |  | 2018-01-09 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | Acknowledge |  |  | User | Henry, Robin |  |  | 2017-12-27 | 19 |  |  | 2018-01-15 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-28 | 193 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-28 | 22 |  |  | 2018-01-19 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-28 | 13 |  |  | 2018-01-10 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2017-12-28 | 22 |  |  | 2018-01-19 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-28 | 43 |  |  | 2018-02-09 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2017-12-28 | 193 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-28 | 193 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-12-28 | 193 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2017-12-28 | 193 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-12-28 | 193 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-12-28 | 193 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2017-12-28 | 63 |  |  | 2018-03-01 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2017-12-28 | 7 |  |  | 2018-01-04 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-28 | 11 |  |  | 2018-01-08 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-28 | 11 |  |  | 2018-01-08 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-28 | 11 |  |  | 2018-01-08 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-28 | 11 |  |  | 2018-01-08 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Update on subject data collection status - see communications | [6 empty] | 2017-12-28 | 193 |  |  |  | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Update on training status - see communications | [6 empty] | 2017-12-28 | 193 |  |  |  | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 192 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 192 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 192 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 25 |  |  | 2018-01-23 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 25 |  |  | 2018-01-23 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 25 |  |  | 2018-01-23 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 26 |  |  | 2018-01-24 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2017-12-29 | 21 |  |  | 2018-01-19 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-29 | 21 |  |  | 2018-01-19 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2017-12-29 | 137 |  |  | 2018-05-15 | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2017-12-29 | 192 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2017-12-29 | 192 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2017-12-29 | 38 |  |  | 2018-02-05 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | PI approved Budget |  |  | User | Henry, Robin |  |  | 2017-12-29 | 45 |  |  | 2018-02-12 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Internal Budget Finished |  |  | User | Oliver, Amy |  |  | 2017-12-29 | 0 |  |  | 2017-11-17 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-30 | 25 |  |  | 2018-01-24 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2017-12-30 | 20 |  |  | 2018-01-19 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2017-12-30 | 32 |  |  | 2018-01-31 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | Acknowledge |  |  | User | Farmer, Amber |  |  | 2017-12-30 | 17 |  |  | 2018-01-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2017-12-31 | 190 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2017-12-31 | 15 |  |  | 2018-01-15 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2017-12-31 | 43 |  |  | 2018-02-12 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Care Designations completed |  |  | User | Henry, Robin |  |  | 2017-12-31 | 47 |  |  | 2018-02-16 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-31 | 0 |  |  | 2017-12-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2017-12-31 | 0 |  |  | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-01 | 189 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-01-01 | 189 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-01-01 | 22 |  |  | 2018-01-23 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-01 | 0 |  |  | 2017-12-26 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-01-01 | 14 |  |  | 2018-01-15 | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-01 | 14 |  |  | 2018-01-15 | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-01 | 189 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-01-01 | 0 |  |  | 2017-12-15 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | PI approved Budget |  |  | User | Oliver, Amy |  |  | 2018-01-01 | 0 |  |  | 2017-11-17 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Request Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-01 | 0 |  |  | 2017-12-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-01-02 | 188 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-02 | 188 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-01-02 | 23 |  |  | 2018-01-25 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-01-02 | 20 |  |  | 2018-01-22 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-01-02 | 0 |  |  | 2018-01-02 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-01-02 | 30 |  |  | 2018-02-01 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | AME Calendaring Process Initiated |  |  | User | Przykucki, Anne |  |  | 2018-01-02 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-02 | 0 |  |  | 2017-12-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-02 | 0 |  |  | 2017-12-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-02 | 0 |  |  | 2017-12-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-02 | 59 |  |  | 2018-03-02 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-02 | 0 |  |  | 2017-12-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-01-02 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-01-02 | 30 |  |  | 2018-02-01 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2018-01-02 | 48 |  |  | 2018-02-19 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-03 | 56 |  |  | 2018-02-28 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-01-03 | 28 |  |  | 2018-01-31 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-03 | 26 |  |  | 2018-01-29 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-03 | 19 |  |  | 2018-01-22 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-03 | 187 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-01-03 | 187 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-01-03 | 187 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-01-03 | 187 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-01-03 | 0 |  |  | 2018-01-03 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-01-03 | 0 |  |  | 2018-01-03 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-01-03 | 0 |  |  | 2018-01-03 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-01-03 | 14 |  |  | 2018-01-17 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-04 | 186 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-01-04 | 186 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-04 | 186 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-04 | 186 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-01-04 | 186 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-01-04 | 186 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Amendment Requires Budget Revisions |  |  | User | Henry, Robin |  |  | 2018-01-04 | 0 |  |  | 2018-01-04 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Amendment Requires Contract Amendment |  |  | User | Henry, Robin |  |  | 2018-01-04 | 0 |  |  | 2018-01-04 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Cloned Current PAF |  |  | User | Henry, Robin |  |  | 2018-01-04 | 0 |  |  | 2018-01-04 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | PAF Complete |  |  | User | Henry, Robin |  |  | 2018-01-04 | 0 |  |  | 2018-01-04 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | PI Signed PAF |  |  | User | Henry, Robin |  |  | 2018-01-04 | 0 |  |  | 2018-01-04 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Sent Budget to Sponsor for Revisions |  |  | User | Henry, Robin |  |  | 2018-01-04 | 0 |  |  | 2018-01-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-01-04 | 88 |  |  | 2018-04-02 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-01-04 | 6 |  |  | 2018-01-10 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-01-04 | 186 |  |  |  | N |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2018-01-04 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-01-04 | 60 |  |  | 2018-03-05 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-05 | 185 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-01-05 | 0 |  |  | 2017-02-06 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-01-05 | 33 |  |  | 2018-02-07 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-01-05 | 14 |  |  | 2018-01-19 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-05 | 54 |  |  | 2018-02-28 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 185 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 185 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 46 |  |  | 2018-02-20 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 185 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-01-05 | 185 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-01-05 | 12 |  |  | 2018-01-17 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-01-05 | 48 |  |  | 2018-02-22 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-01-05 | 48 |  |  | 2018-02-22 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 540-JOHNSON | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-01-05 | 185 |  |  |  | N |  | 540-JOHNSON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-01-05 | 185 |  |  |  | N |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-01-05 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2018-01-05 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-01-05 | 0 |  |  | 2018-01-05 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-01-06 | 31 |  |  | 2018-02-06 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-01-06 | 32 |  |  | 2018-02-07 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-01-06 | 13 |  |  | 2018-01-19 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-01-06 | 184 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-06 | 184 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-01-06 | 80 |  |  | 2018-03-27 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-01-06 | 0 |  |  | 2017-12-08 | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-01-06 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-07 | 0 |  |  | 2017-12-11 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-07 | 183 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-01-07 | 183 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-01-07 | 86 |  |  | 2018-04-03 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-07 | 183 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-01-07 | 0 |  |  | 2018-01-03 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-08 | 182 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-08 | 0 |  |  | 2018-01-08 | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-08 | 0 |  |  | 2018-01-08 | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-01-08 | 0 |  |  | 2018-01-08 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-08 | 0 |  |  | 2018-01-08 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2018-01-08 | 0 |  |  | 2018-01-08 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-01-08 | 0 |  |  | 2018-01-08 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-01-08 | 0 |  |  | 2018-01-04 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2018-01-08 | 11 |  |  | 2018-01-19 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2018-01-08 | 0 |  |  | 2018-01-05 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2018-01-08 | 8 |  |  | 2018-01-16 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-09 | 181 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-01-09 | 29 |  |  | 2018-02-07 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-01-09 | 30 |  |  | 2018-02-08 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-01-09 | 13 |  |  | 2018-01-22 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-09 | 21 |  |  | 2018-01-30 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-09 | 181 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-01-09 | 181 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-09 | 181 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-01-09 | 87 |  |  | 2018-04-06 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-10 | 180 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-10 | 28 |  |  | 2018-02-07 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-10 | 29 |  |  | 2018-02-08 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-10 | 12 |  |  | 2018-01-22 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-10 | 2 |  |  | 2018-01-12 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-10 | 180 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-10 | 180 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-10 | 0 |  |  | 2018-01-10 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-10 | 0 |  |  | 2018-01-10 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 22 |  |  | 2018-02-01 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 155 |  |  | 2018-06-14 | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 180 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 180 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 0 |  |  | 2018-01-10 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 0 |  |  | 2018-01-10 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 0 |  |  | 2018-01-10 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2018-01-10 | 0 |  |  | 2018-01-10 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2018-01-10 | 7 |  |  | 2018-01-17 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-01-10 | 7 |  |  | 2018-01-17 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-11 | 179 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-11 | 0 |  |  | 2018-01-11 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-11 | 0 |  |  | 2018-01-11 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-11 | 0 |  |  | 2018-01-11 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-01-11 | 179 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-01-11 | 179 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-11 | 179 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Revised Billing Grid Sent to Study Team |  |  | User | Henry, Robin |  |  | 2018-01-11 | 35 |  |  | 2018-02-15 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-01-11 | 0 |  |  | 2017-12-19 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-01-12 | 178 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-01-12 | 19 |  |  | 2018-01-31 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-12 | 4 |  |  | 2018-01-16 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-12 | 49 |  |  | 2018-03-02 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-12 | 178 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-12 | 178 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Amendment Requires Budget Revisions |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Cloned Current PAF |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Contract Executed |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | PAF Complete |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | PI Signed PAF |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Study Team Contacted to Approve Amendment Change |  |  | User | Yunk, Jason |  |  | 2018-01-12 | 0 |  |  | 2018-01-12 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-01-13 | 18 |  |  | 2018-01-31 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-13 | 177 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-01-13 | 73 |  |  | 2018-03-27 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-01-13 | 0 |  |  | 2018-01-04 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-01-13 | 61 |  |  | 2018-03-15 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Final Budget |  |  | User | Henry, Robin |  |  | 2018-01-14 | 40 |  |  | 2018-02-23 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2018-01-14 | 0 |  |  | 2018-01-02 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-15 | 175 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-15 | 175 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-15 | 175 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Received Protocol Amendment |  |  | User | Henry, Robin |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2018-01-15 | 1 |  |  | 2018-01-16 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2018-01-15 | 1 |  |  | 2018-01-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Amendment Requires Budget Revisions |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Cloned Current PAF |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Contract Executed |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | PAF Complete |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | PI Signed PAF |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Sent Budget to Sponsor for Revisions |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Study Team Contacted to Approve Amendment Change |  |  | User | Yunk, Jason |  |  | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-15 | 0 |  |  | 2018-01-15 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-01-16 | 16 |  |  | 2018-02-01 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-16 | 174 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-16 | 0 |  |  | 2018-01-16 | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-16 | 49 |  |  | 2018-03-06 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-16 | 174 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-16 | 174 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-01-16 | 0 |  |  | 2018-01-16 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | PAF routed |  |  | User | Henry, Robin |  |  | 2018-01-16 | 41 |  |  | 2018-02-26 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2018-01-16 | 24 |  |  | 2018-02-09 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-17 | 19 |  |  | 2018-02-05 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-17 | 54 |  |  | 2018-03-12 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-17 | 173 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-01-17 | 70 |  |  | 2018-03-28 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-01-17 | 147 |  |  | 2018-06-13 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-01-17 | 50 |  |  | 2018-03-08 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-01-17 | 2 |  |  | 2018-01-19 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Final Budget |  |  | User | Oliver, Amy |  |  | 2018-01-17 | 0 |  |  | 2017-11-17 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2018-01-17 | 0 |  |  | 2018-01-17 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-18 | 0 |  |  | 2018-01-18 | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-18 | 172 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-18 | 172 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2018-01-18 | 0 |  |  | 2018-01-18 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | AME Calendaring Process Initiated |  |  | User | Henry, Robin |  |  | 2018-01-18 | 0 |  |  | 2018-01-18 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Received Protocol Amendment |  |  | User | Oliver, Amy |  |  | 2018-01-18 | 0 |  |  | 2018-01-18 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-18 | 146 |  |  | 2018-06-13 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-19 | 171 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 171 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 171 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 46 |  |  | 2018-03-06 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 171 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 171 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | SAPOC Changed |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-01-19 | 60 |  |  | 2018-03-20 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-01-19 | 3 |  |  | 2018-01-22 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-01-19 | 3 |  |  | 2018-01-22 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Final Budget |  |  | User | Henry, Robin |  |  | 2018-01-19 | 103 |  |  | 2018-05-02 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | AME Calendaring Process Initiated |  |  | User | Henry, Robin |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-01-19 | 171 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | PAF routed |  |  | User | Oliver, Amy |  |  | 2018-01-19 | 0 |  |  | 2017-11-21 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Confirm calendar build completed |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Make Updates |  |  | User | van Dijk, Tim |  |  | 2018-01-19 | 0 |  |  | 2018-01-19 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-01-20 | 170 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-20 | 170 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-01-20 | 0 |  |  | 2018-01-20 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-01-20 | 68 |  |  | 2018-03-29 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-01-20 | 121 |  |  | 2018-05-21 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Assign to Analyst |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-20 | 0 |  |  | 2018-01-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-01-20 | 0 |  |  | 2018-01-20 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-01-20 | 0 |  |  | 2018-01-20 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-01-20 | 88 |  |  | 2018-04-18 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-21 | 169 |  |  |  | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-01-21 | 169 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-01-21 | 0 |  |  | 2018-01-12 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | PAF routed |  |  | User | Henry, Robin |  |  | 2018-01-21 | 101 |  |  | 2018-05-02 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-01-21 | 1 |  |  | 2018-01-22 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-21 | 0 |  |  | 2018-01-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-21 | 0 |  |  | 2018-01-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-21 | 101 |  |  | 2018-05-02 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | IRB Amendment Submitted in eRRM |  |  | Role | CTSU Coordinator |  |  | 2018-01-22 | 25 |  |  | 2018-02-16 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-22 | 168 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 168 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 168 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 168 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 168 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 168 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | ** Structural Edits |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | Submit Update Request(s) |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-01-22 | 87 |  |  | 2018-04-19 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Study Team Approves OnCore Billing Grid |  |  | User | Henry, Robin |  |  | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Complete MCA / QCT |  |  | User | Hess, Aaron |  |  | 2018-01-22 | 8 |  |  | 2018-01-30 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-01-22 | 9 |  |  | 2018-01-31 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-01-22 | 8 |  |  | 2018-01-30 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2018-01-22 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-01-22 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne |  |  | 2018-01-22 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2018-01-22 | 0 |  |  | 2018-01-17 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-01-22 | 94 |  |  | 2018-04-26 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-22 | 0 |  |  | 2018-01-22 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-01-23 | 167 |  |  |  | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-01-23 | 167 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-23 | 0 |  |  | 2018-01-23 | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-23 | 0 |  |  | 2018-01-23 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-01-23 | 69 |  |  | 2018-04-02 | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-01-23 | 167 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-23 | 167 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-01-23 | 0 |  |  | 2018-01-23 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-23 | 0 |  |  | 2018-01-23 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-01-23 | 2 |  |  | 2018-01-25 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-01-23 | 2 |  |  | 2018-01-25 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Final Budget |  |  | User | Henry, Robin |  |  | 2018-01-23 | 93 |  |  | 2018-04-26 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Request Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-23 | 0 |  |  | 2018-01-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Update RSH Source in MBECT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-23 | 0 |  |  | 2018-01-11 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | OnCore Billing Calendar Change Needed |  |  | User | Oliver, Amy |  |  | 2018-01-23 | 0 |  |  | 2018-01-23 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | OnCore Billing Calendar Completed |  |  | User | Oliver, Amy |  |  | 2018-01-23 | 0 |  |  | 2018-01-23 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-23 | 94 |  |  | 2018-04-27 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-01-23 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-01-23 | 167 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-24 | 166 |  |  |  | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-24 | 0 |  |  | 2018-01-24 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-24 | 0 |  |  | 2018-01-24 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-01-24 | 76 |  |  | 2018-04-10 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-01-24 | 7 |  |  | 2018-01-31 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-01-24 | 15 |  |  | 2018-02-08 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-01-24 | 0 |  |  | 2018-01-23 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-24 | 166 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne |  |  | 2018-01-24 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-01-24 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-01-24 | 0 |  |  | 2018-01-18 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-01-25 | 165 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-25 | 165 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-25 | 165 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-25 | 0 |  |  | 2018-01-25 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | PAF routed |  |  | User | Henry, Robin |  |  | 2018-01-25 | 97 |  |  | 2018-05-02 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-25 | 1 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-01-25 | 0 |  |  | 2018-01-25 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-25 | 0 |  |  | 2018-01-25 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Update on subject data collection status - see communications | [6 empty] | 2018-01-25 | 165 |  |  |  | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Update on training status - see communications | [6 empty] | 2018-01-25 | 165 |  |  |  | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Feasibility Approval Notice Received |  |  | Role | CRAO |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 126 |  |  | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 164 |  |  |  | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 3 |  |  | 2018-01-29 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 3 |  |  | 2018-01-29 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 3 |  |  | 2018-01-29 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 3 |  |  | 2018-01-29 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 3 |  |  | 2018-01-29 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-01-26 | 3 |  |  | 2018-01-29 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-01-26 | 164 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-01-26 | 164 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-26 | 164 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Budget Build Completed |  |  | Role | CTSU Finance |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-25 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Received Protocol Amendment |  |  | User | Oliver, Amy |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-01-26 | 0 |  |  | 2018-01-24 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-01-26 | 0 |  |  | 2018-01-25 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Confirm calendar build completed |  |  | User | Radenbaugh, Pauline |  |  | 2018-01-26 | 0 |  |  | 2018-01-25 | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Amendment Requires Budget Revisions |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Cloned Current PAF |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | PAF Complete |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | PI Signed PAF |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Sent Budget to Sponsor for Revisions |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Study Team Contacted to Approve Amendment Change |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 0 |  |  | 2018-01-26 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 135 |  |  | 2018-06-10 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-01-26 | 164 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-27 | 163 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-01-27 | 163 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Final Budget |  |  | User | Henry, Robin |  |  | 2018-01-27 | 0 |  |  | 2018-01-09 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-01-27 | 73 |  |  | 2018-04-10 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-27 | 134 |  |  | 2018-06-10 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-27 | 163 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-01-28 | 124 |  |  | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-01-28 | 0 |  |  | 2018-01-26 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-01-28 | 162 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-01-28 | 8 |  |  | 2018-02-05 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-01-28 | 8 |  |  | 2018-02-05 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-01-28 | 2 |  |  | 2018-01-30 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Henry, Robin |  |  | 2018-01-28 | 0 |  |  | 2018-01-12 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2018-01-28 | 0 |  |  | 2018-01-26 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Assign to Analyst |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-28 | 0 |  |  | 2018-01-26 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 161 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 161 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 161 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 161 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-01-29 | 43 |  |  | 2018-03-13 | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-29 | 36 |  |  | 2018-03-06 | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-29 | 161 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-01-29 | 81 |  |  | 2018-04-20 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | ** Other Request(s) |  |  | User | Farmer, Amber |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Contract Executed |  |  | User | Henry, Robin |  |  | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | PAF routed |  |  | User | Henry, Robin |  |  | 2018-01-29 | 0 |  |  | 2018-01-09 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-01-29 | 72 |  |  | 2018-04-11 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Henry, Robin |  |  | 2018-01-29 | 0 |  |  | 2018-01-25 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | Make Update(s) |  |  | User | Hodges, Lynda |  |  | 2018-01-29 | 0 |  |  | 2018-01-23 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | Re-Complete Calendar |  |  | User | Hodges, Lynda |  |  | 2018-01-29 | 0 |  |  | 2018-01-23 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2018-01-29 | 3 |  |  | 2018-02-01 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2018-01-29 | 4 |  |  | 2018-02-02 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-01-29 | 0 |  |  | 2018-01-29 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-30 | 119 |  |  | 2018-05-29 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-01-30 | 160 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-01-30 | 160 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-01-30 | 160 |  |  |  | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-01-30 | 0 |  |  | 2018-01-26 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | OnCore Billing Calendar Change Needed |  |  | User | Huffman, Kate |  |  | 2018-01-30 | 0 |  |  | 2018-01-30 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Complete Calendar and Document Approval |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-30 | 0 |  |  | 2018-01-12 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-01-30 | 160 |  |  |  | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason |  |  | 2018-01-30 | 0 |  |  | 2018-01-30 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-01-30 | 0 |  |  | 2018-01-30 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-01-30 | 10 |  |  | 2018-02-09 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-01-31 | 8 |  |  | 2018-02-08 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-01-31 | 0 |  |  | 2018-01-24 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-01-31 | 0 |  |  | 2018-01-29 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-01-31 | 0 |  |  | 2018-01-29 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-01-31 | 0 |  |  | 2018-01-11 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-31 | 0 |  |  | 2018-01-10 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-01-31 | 0 |  |  | 2018-01-31 | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2018-01-31 | 1 |  |  | 2018-02-01 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2018-01-31 | 0 |  |  | 2018-01-31 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2018-01-31 | 0 |  |  | 2018-01-31 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-01-31 | 79 |  |  | 2018-04-20 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-01-31 | 51 |  |  | 2018-03-23 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-01-31 | 1 |  |  | 2018-02-01 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-01-31 | 1 |  |  | 2018-02-01 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-01-31 | 1 |  |  | 2018-02-01 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-01-31 | 1 |  |  | 2018-02-01 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-01-31 | 1 |  |  | 2018-02-01 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-01-31 | 0 |  |  | 2018-01-31 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-01-31 | 0 |  |  | 2018-01-30 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-31 | 35 |  |  | 2018-03-07 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-31 | 6 |  |  | 2018-02-06 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2018-01-31 | 14 |  |  | 2018-02-14 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-01-31 | 9 |  |  | 2018-02-09 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2018-01-31 | 0 |  |  | 2018-01-25 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2018-01-31 | 0 |  |  | 2018-01-26 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-01 | 158 |  |  |  | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-01 | 158 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-01 | 41 |  |  | 2018-03-14 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-01 | 54 |  |  | 2018-03-27 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-01 | 1 |  |  | 2018-02-02 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-01 | 1 |  |  | 2018-02-02 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-02-01 | 0 |  |  | 2018-01-15 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-01 | 0 |  |  | 2018-01-12 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-02-01 | 0 |  |  | 2018-01-15 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-01 | 0 |  |  | 2018-01-12 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-02-01 | 158 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-02-01 | 4 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-02-01 | 1 |  |  | 2018-02-02 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-01 | 0 |  |  | 2018-01-12 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 521-CONJEEVARAM | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne |  |  | 2018-02-01 | 0 |  |  | 2018-02-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Update on subject data collection status - see communications | [6 empty] | 2018-02-01 | 158 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Update on training status - see communications | [6 empty] | 2018-02-01 | 158 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 1 |  |  | 2018-02-03 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 157 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 157 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 157 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 3 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 3 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 3 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-02-02 | 157 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | PAF Complete |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-01-29 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 3 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-01-31 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-02-01 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-01-29 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 0 |  |  | 2018-01-31 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-02 | 68 |  |  | 2018-04-11 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-02 | 0 |  |  | 2018-01-29 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-02-02 | 53 |  |  | 2018-03-27 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-02-02 | 53 |  |  | 2018-03-27 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-02-02 | 39 |  |  | 2018-03-13 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-02-02 | 0 |  |  | 2018-01-30 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-02-02 | 4 |  |  | 2018-02-06 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-02 | 12 |  |  | 2018-02-14 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-02 | 12 |  |  | 2018-02-14 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-02 | 157 |  |  |  | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-02 | 89 |  |  | 2018-05-02 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-02 | 3 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-02 | 157 |  |  |  | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-02-02 | 0 |  |  | 2018-02-01 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | AME Calendaring Process Initiated |  |  | User | van Dijk, Tim |  |  | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Initiate CRAO Amendment Task List | [6 empty] | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | OnCore Billing Calendar Change Needed | [6 empty] | 2018-02-02 | 0 |  |  | 2018-02-02 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-03 | 0 |  |  | 2018-01-24 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-02-03 | 156 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Complete MCA / QCT |  |  | User | Hess, Aaron |  |  | 2018-02-03 | 23 |  |  | 2018-02-26 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-02-03 | 4 |  |  | 2018-02-07 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-02-03 | 5 |  |  | 2018-02-08 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2018-02-03 | 4 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2018-02-03 | 3 |  |  | 2018-02-06 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2018-02-03 | 3 |  |  | 2018-02-06 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2018-02-03 | 10 |  |  | 2018-02-13 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-02-04 | 155 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-04 | 30 |  |  | 2018-03-06 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-04 | 155 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-02-04 | 51 |  |  | 2018-03-27 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-02-04 | 155 |  |  |  | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-02-04 | 5 |  |  | 2018-02-09 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-04 | 155 |  |  |  | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-02-04 | 3 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2018-02-04 | 3 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2018-02-04 | 0 |  |  | 2018-02-02 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 154 |  |  |  | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 154 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 154 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 154 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-02-05 | 154 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-05 | 154 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-02-05 | 4 |  |  | 2018-02-09 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-02-05 | 57 |  |  | 2018-04-03 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-02-05 | 3 |  |  | 2018-02-08 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-02-05 | 3 |  |  | 2018-02-08 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | Make Update(s) |  |  | User | Hodges, Lynda |  |  | 2018-02-05 | 0 |  |  | 2018-01-31 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | Re-Complete Calendar |  |  | User | Hodges, Lynda |  |  | 2018-02-05 | 0 |  |  | 2018-01-31 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 603-MCCUNE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-05 | 154 |  |  |  | N |  | 603-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-02-05 | 2 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2018-02-05 | 11 |  |  | 2018-02-16 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2018-02-05 | 2 |  |  | 2018-02-07 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2018-02-05 | 7 |  |  | 2018-02-12 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Calendar build assigned to CRAO |  |  | User | Przykucki, Anne |  |  | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | van Dijk, Tim |  |  | 2018-02-05 | 0 |  |  | 2018-02-02 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2018-02-05 | 8 |  |  | 2018-02-13 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-02-05 | 8 |  |  | 2018-02-13 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-02-05 | 0 |  |  | 2018-02-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-06 | 153 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-02-06 | 15 |  |  | 2018-02-21 | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-06 | 7 |  |  | 2018-02-13 | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-02-06 | 153 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Transition Checklist signed by department |  |  | Role | CTSU Finance |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne |  |  | 2018-02-06 | 1 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-02-06 | 13 |  |  | 2018-02-19 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-02-06 | 0 |  |  | 2018-02-06 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2018-02-06 | 7 |  |  | 2018-02-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-07 | 0 |  |  | 2018-01-31 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-07 | 152 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-07 | 0 |  |  | 2018-02-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-07 | 152 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-07 | 152 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 152 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 152 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 152 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 152 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 152 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 152 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-02-07 | 14 |  |  | 2018-02-21 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-02-07 | 86 |  |  | 2018-05-04 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Create new OnCore Budget Version |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 57 |  |  | 2018-04-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 6 |  |  | 2018-02-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-06 | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 2 |  |  | 2018-02-09 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-05 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-06 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-02-07 | 0 |  |  | 2018-02-05 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | IRB Amendment Submitted in eRRM |  |  | User | Oliver, Amy |  |  | 2018-02-07 | 152 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Revised Billing Grid Sent to Study Team |  |  | User | Oliver, Amy |  |  | 2018-02-07 | 8 |  |  | 2018-02-15 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Study Team Approves OnCore Billing Grid |  |  | User | Oliver, Amy |  |  | 2018-02-07 | 37 |  |  | 2018-03-16 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-02-07 | 0 |  |  | 2018-02-07 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2018-02-07 | 9 |  |  | 2018-02-16 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-02-07 | 9 |  |  | 2018-02-16 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-02-07 | 6 |  |  | 2018-02-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Update RSH Source in MBECT |  |  | User | van Dijk, Tim |  |  | 2018-02-07 | 6 |  |  | 2018-02-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | OnCore Billing Calendar Completed | [6 empty] | 2018-02-07 | 68 |  |  | 2018-04-16 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Revised Billing Grid Sent to Study Team | [6 empty] | 2018-02-07 | 6 |  |  | 2018-02-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-08 | 0 |  |  | 2018-02-08 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-08 | 151 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-08 | 151 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-08 | 11 |  |  | 2018-02-19 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-08 | 0 |  |  | 2018-01-17 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-08 | 0 |  |  | 2018-02-07 | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-08 | 0 |  |  | 2018-02-08 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-02-08 | 151 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-02-08 | 124 |  |  | 2018-06-12 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-02-08 | 151 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-08 | 0 |  |  | 2018-02-08 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-08 | 0 |  |  | 2018-02-08 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-08 | 0 |  |  | 2018-02-08 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-08 | 5 |  |  | 2018-02-13 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-08 | 5 |  |  | 2018-02-13 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-08 | 5 |  |  | 2018-02-13 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-08 | 151 |  |  |  | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-08 | 151 |  |  |  | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2018-02-08 | 151 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2018-02-08 | 151 |  |  |  | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Calendar Released |  |  | User | Yunk, Jason |  |  | 2018-02-08 | 49 |  |  | 2018-03-29 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Calendar Released |  |  | User | Yunk, Jason |  |  | 2018-02-08 | 151 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 0 |  |  | 2018-01-30 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 5 |  |  | 2018-02-14 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 5 |  |  | 2018-02-14 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 5 |  |  | 2018-02-14 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 5 |  |  | 2018-02-14 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 5 |  |  | 2018-02-14 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-02-09 | 0 |  |  | 2018-02-08 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-09 | 32 |  |  | 2018-03-13 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-09 | 0 |  |  | 2018-01-31 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-09 | 0 |  |  | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-09 | 0 |  |  | 2018-02-07 | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-09 | 0 |  |  | 2018-02-06 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-07 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-02-09 | 3 |  |  | 2018-02-12 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-02-09 | 0 |  |  | 2018-01-31 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-02-09 | 7 |  |  | 2018-02-16 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Confirm calendar released (see details in Migration: Financials) |  |  | User | Huffman, Kate |  |  | 2018-02-09 | 5 |  |  | 2018-02-14 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | IRB Amendment Approved in eRRM |  |  | User | Oliver, Amy |  |  | 2018-02-09 | 150 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-09 | 150 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Planning Meeting Completed |  |  | User | Oliver, Amy |  |  | 2018-02-09 | 7 |  |  | 2018-02-16 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-02-09 | 0 |  |  | 2018-02-09 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-02-09 | 0 |  |  | 2018-02-08 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Calendar Released |  |  | User | Yunk, Jason |  |  | 2018-02-09 | 123 |  |  | 2018-06-12 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Calendar Released |  |  | User | Yunk, Jason |  |  | 2018-02-09 | 150 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | CRAO Amendment Task List Completed | [6 empty] | 2018-02-09 | 150 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-02-10 | 0 |  |  | 2018-01-30 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-02-10 | 0 |  |  | 2018-02-08 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-10 | 0 |  |  | 2018-01-17 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-10 | 149 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-02-10 | 10 |  |  | 2018-02-20 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-02-10 | 31 |  |  | 2018-03-13 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy |  |  | 2018-02-10 | 149 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-11 | 148 |  |  |  | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-11 | 148 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-11 | 7 |  |  | 2018-02-18 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-11 | 3 |  |  | 2018-02-14 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-11 | 7 |  |  | 2018-02-18 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-11 | 7 |  |  | 2018-02-18 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-11 | 148 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-02-11 | 15 |  |  | 2018-02-26 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-02-11 | 15 |  |  | 2018-02-26 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-02-11 | 15 |  |  | 2018-02-26 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-02-11 | 15 |  |  | 2018-02-26 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-02-11 | 23 |  |  | 2018-03-06 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-02-11 | 2 |  |  | 2018-02-13 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-11 | 24 |  |  | 2018-03-07 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-11 | 19 |  |  | 2018-03-02 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2018-02-11 | 4 |  |  | 2018-02-15 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2018-02-11 | 2 |  |  | 2018-02-13 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2018-02-11 | 9 |  |  | 2018-02-20 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-12 | 147 |  |  |  | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-12 | 147 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-12 | 147 |  |  |  | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-12 | 2 |  |  | 2018-02-14 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-12 | 2 |  |  | 2018-02-14 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 147 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 2 |  |  | 2018-02-14 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 2 |  |  | 2018-02-14 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-02-12 | 85 |  |  | 2018-05-08 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Create new OnCore Budget Version |  |  | User | Farmer, Amber |  |  | 2018-02-12 | 1 |  |  | 2018-02-13 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-02-12 | 15 |  |  | 2018-02-27 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-02-12 | 63 |  |  | 2018-04-16 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Final Budget |  |  | User | Henry, Robin |  |  | 2018-02-12 | 92 |  |  | 2018-05-15 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-02-12 | 4 |  |  | 2018-02-16 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-02-12 | 15 |  |  | 2018-02-27 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-02-12 | 23 |  |  | 2018-03-07 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 0 |  |  | 2018-02-09 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 8 |  |  | 2018-02-20 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Calendar build assigned to CRAO |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Calendar build assigned to CRAO |  |  | User | Hodges, Lynda |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-12 | 9 |  |  | 2018-02-21 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-12 | 8 |  |  | 2018-02-20 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-12 | 8 |  |  | 2018-02-20 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-12 | 15 |  |  | 2018-02-27 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Amendment Requires Budget Revisions |  |  | User | Yunk, Jason |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Cloned Current PAF |  |  | User | Yunk, Jason |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | PAF Complete |  |  | User | Yunk, Jason |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2018-02-12 | 3 |  |  | 2018-02-15 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2018-02-12 | 3 |  |  | 2018-02-15 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2018-02-12 | 8 |  |  | 2018-02-20 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-02-12 | 0 |  |  | 2018-02-12 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 146 |  |  |  | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 146 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 146 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 146 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 92 |  |  | 2018-05-16 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 0 |  |  | 2017-02-01 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-02-13 | 0 |  |  | 2018-02-12 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-02-13 | 7 |  |  | 2018-02-20 | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-13 | 1 |  |  | 2018-02-14 | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-02-13 | 16 |  |  | 2018-03-01 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-13 | 13 |  |  | 2018-02-26 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-02-13 | 146 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-13 | 23 |  |  | 2018-03-08 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-02-13 | 0 |  |  | 2018-02-13 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2018-02-13 | 0 |  |  | 2018-02-07 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-02-13 | 146 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 7 |  |  | 2018-02-20 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 8 |  |  | 2018-02-21 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 6 |  |  | 2018-02-19 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 6 |  |  | 2018-02-19 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 3 |  |  | 2018-02-16 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 3 |  |  | 2018-02-16 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 6 |  |  | 2018-02-19 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-02-13 | 6 |  |  | 2018-02-19 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 145 |  |  |  | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 145 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 145 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 145 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 0 |  |  | 2018-02-05 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 0 |  |  | 2018-02-05 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 0 |  |  | 2018-02-05 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-14 | 4 |  |  | 2018-02-18 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-02-14 | 0 |  |  | 2018-02-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-02-14 | 0 |  |  | 2018-02-14 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-02-14 | 86 |  |  | 2018-05-11 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-02-14 | 75 |  |  | 2018-04-30 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-14 | 0 |  |  | 2018-02-13 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | PAF routed |  |  | User | Henry, Robin |  |  | 2018-02-14 | 96 |  |  | 2018-05-21 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-02-14 | 15 |  |  | 2018-03-01 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-02-14 | 12 |  |  | 2018-02-26 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-02-14 | 12 |  |  | 2018-02-26 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-02-14 | 21 |  |  | 2018-03-07 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-02-14 | 27 |  |  | 2018-03-13 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-14 | 7 |  |  | 2018-02-21 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-14 | 7 |  |  | 2018-02-21 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-14 | 145 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-02-14 | 145 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2018-02-14 | 62 |  |  | 2018-04-17 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2018-02-14 | 6 |  |  | 2018-02-20 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-02-14 | 7 |  |  | 2018-02-21 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2018-02-14 | 14 |  |  | 2018-02-28 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Make Updates |  |  | User | van Dijk, Tim |  |  | 2018-02-14 | 14 |  |  | 2018-02-28 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Study Team Approves OnCore Billing Grid | [6 empty] | 2018-02-14 | 61 |  |  | 2018-04-16 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-15 | 144 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-15 | 18 |  |  | 2018-03-05 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-15 | 18 |  |  | 2018-03-05 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-15 | 144 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-15 | 144 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-15 | 144 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-02-15 | 144 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-02-15 | 144 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-02-15 | 144 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-02-15 | 144 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-15 | 0 |  |  | 2018-02-14 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-02-15 | 0 |  |  | 2018-02-13 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-02-15 | 0 |  |  | 2018-02-13 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-02-15 | 4 |  |  | 2018-02-19 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Initiate CRAO Amendment Task List |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | OnCore Billing Calendar Change Needed |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | OnCore Billing Calendar Completed |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Received Protocol Amendment |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Received Protocol Amendment |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 144 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Finance Validation Checklist Completed |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 1 |  |  | 2018-02-16 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Transition Checklist signed by department |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 1 |  |  | 2018-02-16 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Contract Executed |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | AME Calendaring Process Initiated |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 0 |  |  | 2018-02-15 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 42 |  |  | 2018-03-29 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 42 |  |  | 2018-03-29 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-02-15 | 4 |  |  | 2018-02-19 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 143 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 26 |  |  | 2018-03-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 26 |  |  | 2018-03-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 26 |  |  | 2018-03-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 17 |  |  | 2018-03-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 17 |  |  | 2018-03-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 17 |  |  | 2018-03-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-02-16 | 20 |  |  | 2018-03-08 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-16 | 0 |  |  | 2018-02-16 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-16 | 25 |  |  | 2018-03-13 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-02-16 | 60 |  |  | 2018-04-17 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-02-16 | 63 |  |  | 2018-04-20 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-02-16 | 63 |  |  | 2018-04-20 | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-02-16 | 0 |  |  | 2018-02-12 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-16 | 18 |  |  | 2018-03-06 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-16 | 14 |  |  | 2018-03-02 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-02-16 | 0 |  |  | 2018-02-14 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-02-16 | 0 |  |  | 2018-02-14 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-16 | 143 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-16 | 0 |  |  | 2018-02-16 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-17 | 142 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-02-17 | 142 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-02-17 | 22 |  |  | 2018-03-11 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-17 | 142 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-17 | 142 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-02-17 | 142 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-02-17 | 142 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Amendment Requires Contract Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-17 | 0 |  |  | 2018-02-17 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-02-17 | 0 |  |  | 2018-02-17 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-17 | 4 |  |  | 2018-02-21 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-17 | 4 |  |  | 2018-02-21 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-17 | 4 |  |  | 2018-02-21 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-02-17 | 0 |  |  | 2018-02-15 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-02-17 | 3 |  |  | 2018-02-20 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-02-17 | 3 |  |  | 2018-02-20 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2018-02-17 | 0 |  |  | 2018-02-15 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-02-17 | 142 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2018-02-17 | 4 |  |  | 2018-02-21 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-18 | 141 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-02-18 | 141 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-18 | 3 |  |  | 2018-02-21 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-02-18 | 8 |  |  | 2018-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hess, Aaron |  |  | 2018-02-18 | 8 |  |  | 2018-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-18 | 141 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2018-02-18 | 0 |  |  | 2018-02-15 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-02-18 | 4 |  |  | 2018-02-22 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | van Dijk, Tim |  |  | 2018-02-18 | 5 |  |  | 2018-02-23 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Footnote Edits |  |  | User | van Dijk, Tim |  |  | 2018-02-18 | 9 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2018-02-18 | 9 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim |  |  | 2018-02-18 | 9 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | van Dijk, Tim |  |  | 2018-02-18 | 9 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-19 | 140 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-19 | 140 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-19 | 23 |  |  | 2018-03-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-19 | 14 |  |  | 2018-03-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-19 | 140 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-19 | 140 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 140 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 140 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 140 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 3 |  |  | 2018-02-22 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-02-19 | 87 |  |  | 2018-05-17 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-02-19 | 3 |  |  | 2018-02-22 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-02-19 | 66 |  |  | 2018-04-26 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-02-19 | 3 |  |  | 2018-02-22 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-02-19 | 3 |  |  | 2018-02-22 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-02-19 | 7 |  |  | 2018-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-02-19 | 0 |  |  | 2018-02-19 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2018-02-19 | 51 |  |  | 2018-04-11 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-02-19 | 0 |  |  | 2018-02-15 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2018-02-19 | 3 |  |  | 2018-02-22 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2018-02-19 | 4 |  |  | 2018-02-23 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2018-02-19 | 8 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-02-19 | 0 |  |  | 2018-02-16 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-02-19 | 0 |  |  | 2018-02-16 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-20 | 139 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-20 | 139 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-02-20 | 139 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-02-20 | 139 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-20 | 72 |  |  | 2018-05-03 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-02-20 | 139 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-02-20 | 139 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-20 | 0 |  |  | 2018-01-30 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hess, Aaron |  |  | 2018-02-20 | 6 |  |  | 2018-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Request Care Designations |  |  | User | Hess, Aaron |  |  | 2018-02-20 | 6 |  |  | 2018-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Update RSH Source in MBECT |  |  | User | Hess, Aaron |  |  | 2018-02-20 | 6 |  |  | 2018-02-26 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-20 | 37 |  |  | 2018-03-29 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-20 | 139 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 624-MCCUNE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-20 | 139 |  |  |  | N |  | 624-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2018-02-20 | 50 |  |  | 2018-04-11 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline |  |  | 2018-02-20 | 2 |  |  | 2018-02-22 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-02-20 | 0 |  |  | 2018-02-20 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-02-20 | 3 |  |  | 2018-02-23 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Update RSH Source in MBECT |  |  | User | van Dijk, Tim |  |  | 2018-02-20 | 3 |  |  | 2018-02-23 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim |  |  | 2018-02-20 | 7 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim |  |  | 2018-02-20 | 7 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-02-20 | 7 |  |  | 2018-02-27 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 28 |  |  | 2018-03-21 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 12 |  |  | 2018-03-05 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-21 | 138 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-21 | 14 |  |  | 2018-03-07 | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-02-21 | 98 |  |  | 2018-05-30 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-02-21 | 68 |  |  | 2018-04-30 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-02-21 | 43 |  |  | 2018-04-05 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-02-21 | 0 |  |  | 2018-02-07 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-02-21 | 1 |  |  | 2018-02-22 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-02-21 | 9 |  |  | 2018-03-02 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-02-21 | 71 |  |  | 2018-05-03 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-02-21 | 71 |  |  | 2018-05-03 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-02-21 | 1 |  |  | 2018-02-22 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-02-21 | 1 |  |  | 2018-02-22 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-02-21 | 0 |  |  | 2018-02-19 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-02-21 | 1 |  |  | 2018-02-22 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-21 | 111 |  |  | 2018-06-12 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-21 | 91 |  |  | 2018-05-23 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-02-21 | 138 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-21 | 138 |  |  |  | N |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-02-21 | 0 |  |  | 2018-02-21 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-02-21 | 138 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Calendar Released |  |  | User | Yunk, Jason |  |  | 2018-02-21 | 138 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-02-21 | 36 |  |  | 2018-03-29 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-22 | 40 |  |  | 2018-04-03 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-02-22 | 137 |  |  |  | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-22 | 34 |  |  | 2018-03-28 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-22 | 137 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-02-22 | 137 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-02-22 | 137 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-22 | 0 |  |  | 2018-01-30 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-02-22 | 137 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-02-22 | 137 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Revised Billing Grid Sent to Study Team |  |  | User | Oliver, Amy |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Study Team Approves OnCore Billing Grid |  |  | User | Oliver, Amy |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-22 | 137 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-02-22 | 0 |  |  | 2018-02-22 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2018-02-22 | 50 |  |  | 2018-04-13 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Make Updates |  |  | User | van Dijk, Tim |  |  | 2018-02-22 | 50 |  |  | 2018-04-13 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 136 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 60 |  |  | 2018-04-24 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-02-23 | 60 |  |  | 2018-04-24 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 0 |  |  | 2018-02-21 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 13 |  |  | 2018-03-08 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 19 |  |  | 2018-03-14 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 0 |  |  | 2018-01-24 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 0 |  |  | 2018-01-24 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 38 |  |  | 2018-04-02 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 0 |  |  | 2018-02-23 | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-23 | 0 |  |  | 2018-02-23 | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-23 | 5 |  |  | 2018-02-28 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-02-23 | 47 |  |  | 2018-04-11 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-23 | 136 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-23 | 5 |  |  | 2018-02-28 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-02-23 | 87 |  |  | 2018-05-21 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-02-23 | 34 |  |  | 2018-03-29 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-02-23 | 0 |  |  | 2018-02-22 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-02-23 | 0 |  |  | 2018-02-20 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-02-23 | 0 |  |  | 2018-02-20 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-02-23 | 12 |  |  | 2018-03-07 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-02-23 | 12 |  |  | 2018-03-07 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-02-23 | 0 |  |  | 2018-02-23 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-23 | 4 |  |  | 2018-02-27 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-02-23 | 7 |  |  | 2018-03-02 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Make Updates |  |  | User | van Dijk, Tim |  |  | 2018-02-23 | 10 |  |  | 2018-03-05 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-24 | 135 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-02-24 | 59 |  |  | 2018-04-24 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-02-24 | 59 |  |  | 2018-04-24 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-02-24 | 135 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-02-24 | 3 |  |  | 2018-02-27 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2018-02-24 | 5 |  |  | 2018-03-01 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2018-02-24 | 0 |  |  | 2018-02-23 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-02-25 | 134 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-02-25 | 45 |  |  | 2018-04-11 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-02-25 | 134 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-02-25 | 23 |  |  | 2018-03-20 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-25 | 1 |  |  | 2018-02-26 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-02-25 | 15 |  |  | 2018-03-12 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2018-02-25 | 1 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-02-25 | 1 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne |  |  | 2018-02-25 | 1 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Przykucki, Anne |  |  | 2018-02-25 | 1 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2018-02-25 | 134 |  |  |  | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2018-02-25 | 3 |  |  | 2018-02-28 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason |  |  | 2018-02-25 | 12 |  |  | 2018-03-09 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-26 | 133 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-26 | 7 |  |  | 2018-03-05 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-02-26 | 7 |  |  | 2018-03-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-02-26 | 133 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-02-26 | 133 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-02-26 | 133 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-02-26 | 44 |  |  | 2018-04-11 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-02-26 | 0 |  |  | 2018-02-12 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-02-26 | 28 |  |  | 2018-03-26 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-02-26 | 64 |  |  | 2018-05-01 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-02-26 | 0 |  |  | 2018-02-22 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-02-26 | 14 |  |  | 2018-03-12 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 634-FLAHERTY | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-26 | 133 |  |  |  | N |  | 634-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-02-26 | 0 |  |  | 2018-02-26 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-02-27 | 132 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-02-27 | 56 |  |  | 2018-04-24 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-02-27 | 56 |  |  | 2018-04-24 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-02-27 | 132 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-02-27 | 132 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-02-27 | 46 |  |  | 2018-04-14 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-02-27 | 132 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Amendment Requires Budget Revisions |  |  | User | Farmer, Amber |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Amendment Requires Contract Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Complete Calendar and Document Approval |  |  | User | Hess, Aaron |  |  | 2018-02-27 | 29 |  |  | 2018-03-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Huffman, Kate |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | ** Structural Edits |  |  | User | Huffman, Kate |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | Submit Update Request(s) |  |  | User | Huffman, Kate |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 638-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-27 | 132 |  |  |  | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne |  |  | 2018-02-27 | 0 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-02-27 | 0 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-02-27 | 0 |  |  | 2018-02-26 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2018-02-27 | 0 |  |  | 2018-02-22 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-02-27 | 0 |  |  | 2018-02-27 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2018-02-27 | 132 |  |  |  | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2018-02-27 | 1 |  |  | 2018-02-28 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2018-02-27 | 21 |  |  | 2018-03-20 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-02-28 | 131 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-02-28 | 0 |  |  | 2018-02-08 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-28 | 5 |  |  | 2018-03-05 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-02-28 | 5 |  |  | 2018-03-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-28 | 72 |  |  | 2018-05-11 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-02-28 | 72 |  |  | 2018-05-11 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-02-28 | 41 |  |  | 2018-04-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121481 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135919 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-02-28 | 131 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-02-28 | 0 |  |  | 2018-02-23 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 641-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-02-28 | 131 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-02-28 | 0 |  |  | 2018-02-28 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-01 | 9 |  |  | 2018-03-10 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-03-01 | 130 |  |  |  | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-03-01 | 130 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-01 | 130 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-03-01 | 0 |  |  | 2018-03-01 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-01 | 0 |  |  | 2018-03-01 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-01 | 130 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-01 | 130 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-01 | 44 |  |  | 2018-04-14 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-03-01 | 130 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-03-01 | 19 |  |  | 2018-03-20 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | Acknowledge |  |  | User | Oliver, Amy |  |  | 2018-03-01 | 53 |  |  | 2018-04-23 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | Assign to Analyst |  |  | User | Przykucki, Anne |  |  | 2018-03-01 | 0 |  |  | 2018-02-28 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-01 | 0 |  |  | 2018-02-27 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-03-01 | 130 |  |  |  | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-03-01 | 0 |  |  | 2018-03-01 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-03-01 | 35 |  |  | 2018-04-05 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-03-02 | 41 |  |  | 2018-04-12 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-03-02 | 53 |  |  | 2018-04-24 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-02 | 129 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-03-02 | 129 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-02 | 48 |  |  | 2018-04-19 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-03-02 | 129 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-03-02 | 129 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-02 | 129 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-02 | 129 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-03-02 | 48 |  |  | 2018-04-19 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-03-02 | 49 |  |  | 2018-04-20 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-03-02 | 46 |  |  | 2018-04-17 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber |  |  | 2018-03-02 | 43 |  |  | 2018-04-14 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-03-02 | 11 |  |  | 2018-03-13 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-03-02 | 13 |  |  | 2018-03-15 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-03-02 | 0 |  |  | 2018-03-02 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-02 | 94 |  |  | 2018-06-04 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-03-02 | 129 |  |  |  | N |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-03-03 | 40 |  |  | 2018-04-12 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-03-03 | 52 |  |  | 2018-04-24 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-03 | 128 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-03 | 128 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-03-03 | 128 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-03-03 | 128 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-03-03 | 0 |  |  | 2018-02-26 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-03 | 11 |  |  | 2018-03-14 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-03 | 4 |  |  | 2018-03-07 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-03 | 11 |  |  | 2018-03-14 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-04 | 46 |  |  | 2018-04-19 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-04 | 59 |  |  | 2018-05-02 | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-03-04 | 127 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 623-TAPPER | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-03-04 | 2 |  |  | 2018-03-06 | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-03-04 | 31 |  |  | 2018-04-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-04 | 1 |  |  | 2018-03-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-03-04 | 1 |  |  | 2018-03-05 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-05 | 44 |  |  | 2018-04-18 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-05 | 46 |  |  | 2018-04-20 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-03-05 | 7 |  |  | 2018-03-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-03-05 | 17 |  |  | 2018-03-22 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-03-05 | 11 |  |  | 2018-03-16 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-03-05 | 0 |  |  | 2018-02-26 | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00139005 | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2018-03-05 | 0 |  |  | 2018-03-05 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-05 | 45 |  |  | 2018-04-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-05 | 31 |  |  | 2018-04-05 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | IRB Amendment Submitted in eRRM |  |  | User | Oliver, Amy |  |  | 2018-03-05 | 0 |  |  | 2018-03-05 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-03-05 | 126 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 644-WHITE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-03-05 | 126 |  |  |  | N |  | 644-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Attach Build Notes ( as Protocol Doc ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-05 | 9 |  |  | 2018-03-14 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-05 | 9 |  |  | 2018-03-14 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-03-05 | 0 |  |  | 2018-02-15 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-03-05 | 0 |  |  | 2018-03-05 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-03-05 | 0 |  |  | 2018-03-05 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-03-05 | 0 |  |  | 2018-02-05 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-03-06 | 37 |  |  | 2018-04-12 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-03-06 | 49 |  |  | 2018-04-24 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-06 | 125 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-03-06 | 125 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-06 | 57 |  |  | 2018-05-02 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-06 | 125 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-03-06 | 125 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | PI Signed PAF |  |  | User | Farmer, Amber |  |  | 2018-03-06 | 0 |  |  | 2018-03-06 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-03-06 | 16 |  |  | 2018-03-22 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 503-JAYASUNDERA | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron |  |  | 2018-03-06 | 0 |  |  | 2018-03-06 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-03-06 | 125 |  |  |  | N |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Complete Calendar and Document Approval |  |  | User | Przykucki, Anne |  |  | 2018-03-06 | 29 |  |  | 2018-04-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-06 | 0 |  |  | 2018-02-27 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-06 | 0 |  |  | 2018-02-27 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-03-06 | 0 |  |  | 2018-03-06 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-03-06 | 0 |  |  | 2018-03-06 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-03-06 | 8 |  |  | 2018-03-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-03-06 | 8 |  |  | 2018-03-14 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-03-07 | 36 |  |  | 2018-04-12 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-03-07 | 65 |  |  | 2018-05-11 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-07 | 124 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-07 | 124 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-03-07 | 0 |  |  | 2018-01-31 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-03-07 | 0 |  |  | 2018-01-31 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-07 | 111 |  |  | 2018-06-26 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-03-07 | 43 |  |  | 2018-04-19 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-03-07 | 47 |  |  | 2018-04-23 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-03-07 | 23 |  |  | 2018-03-30 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-03-07 | 12 |  |  | 2018-03-19 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Request Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-07 | 43 |  |  | 2018-04-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Update RSH Source in MBECT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-07 | 124 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-03-07 | 0 |  |  | 2018-03-07 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-03-07 | 0 |  |  | 2018-03-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-08 | 123 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-03-08 | 1 |  |  | 2018-03-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-03-08 | 27 |  |  | 2018-04-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | AME Calendaring Process Initiated |  |  | User | Huffman, Kate |  |  | 2018-03-08 | 0 |  |  | 2018-03-08 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-03-08 | 0 |  |  | 2018-03-08 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-03-08 | 0 |  |  | 2018-03-08 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-03-08 | 123 |  |  |  | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-09 | 42 |  |  | 2018-04-20 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-03-09 | 46 |  |  | 2018-04-24 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-03-09 | 46 |  |  | 2018-04-24 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-09 | 122 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-03-09 | 122 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-03-09 | 111 |  |  | 2018-06-28 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | ** Other Request(s) |  |  | User | Farmer, Amber |  |  | 2018-03-09 | 0 |  |  | 2018-03-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Farmer, Amber |  |  | 2018-03-09 | 0 |  |  | 2018-03-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2018-03-09 | 0 |  |  | 2018-03-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-03-09 | 0 |  |  | 2018-03-09 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-03-09 | 4 |  |  | 2018-03-13 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-03-10 | 45 |  |  | 2018-04-24 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-03-10 | 45 |  |  | 2018-04-24 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-03-10 | 121 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-03-10 | 121 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-03-10 | 121 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-10 | 0 |  |  | 2018-03-09 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-10 | 121 |  |  |  | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-11 | 120 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-11 | 120 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Footnote Edits |  |  | User | Hess, Aaron |  |  | 2018-03-11 | 1 |  |  | 2018-03-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hess, Aaron |  |  | 2018-03-11 | 1 |  |  | 2018-03-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-11 | 120 |  |  |  | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-11 | 5 |  |  | 2018-03-16 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-12 | 28 |  |  | 2018-04-09 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-12 | 39 |  |  | 2018-04-20 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-12 | 0 |  |  | 2018-02-28 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-03-12 | 0 |  |  | 2018-03-08 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-12 | 0 |  |  | 2018-03-06 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-03-12 | 50 |  |  | 2018-05-01 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-12 | 1 |  |  | 2018-03-13 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-12 | 1 |  |  | 2018-03-13 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-12 | 1 |  |  | 2018-03-13 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-03-12 | 63 |  |  | 2018-05-14 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Calendar build assigned to CRAO |  |  | User | Hess, Aaron |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Confirm calendar build completed |  |  | User | Hess, Aaron |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Calendar build assigned to CRAO |  |  | User | Hess, Aaron |  |  | 2018-03-12 | 8 |  |  | 2018-03-20 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Confirm calendar build completed |  |  | User | Hess, Aaron |  |  | 2018-03-12 | 15 |  |  | 2018-03-27 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Calendar build assigned to CRAO |  |  | User | Hodges, Lynda |  |  | 2018-03-12 | 1 |  |  | 2018-03-13 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-03-12 | 1 |  |  | 2018-03-13 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Calendar build assigned to CRAO |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-12 | 9 |  |  | 2018-03-21 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Confirm calendar build completed |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-12 | 9 |  |  | 2018-03-21 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Calendar build assigned to CRAO |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Confirm calendar build completed |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-03-12 | 0 |  |  | 2018-03-12 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Calendar build assigned to CRAO |  |  | User | van Dijk, Tim |  |  | 2018-03-12 | 1 |  |  | 2018-03-13 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Confirm calendar build completed |  |  | User | van Dijk, Tim |  |  | 2018-03-12 | 119 |  |  |  | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-03-13 | 42 |  |  | 2018-04-24 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-03-13 | 42 |  |  | 2018-04-24 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | IRB Amendment Approved in eRRM |  |  | Role | CTSU Coordinator |  |  | 2018-03-13 | 0 |  |  | 2018-03-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-13 | 118 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-13 | 118 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-03-13 | 17 |  |  | 2018-03-30 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Request Care Designations |  |  | User | Hess, Aaron |  |  | 2018-03-13 | 0 |  |  | 2018-03-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-14 | 117 |  |  |  | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-14 | 117 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-14 | 117 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-03-14 | 58 |  |  | 2018-05-11 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-03-14 | 58 |  |  | 2018-05-11 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 117 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 0 |  |  | 2018-03-12 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 16 |  |  | 2018-03-30 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 117 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 117 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 0 |  |  | 2018-03-14 | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-14 | 0 |  |  | 2018-03-14 | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-14 | 0 |  |  | 2018-02-01 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-14 | 0 |  |  | 2018-02-01 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-03-14 | 117 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-03-14 | 9 |  |  | 2018-03-23 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-03-14 | 0 |  |  | 2018-03-14 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-03-14 | 0 |  |  | 2018-03-14 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-03-14 | 0 |  |  | 2018-03-14 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-03-14 | 0 |  |  | 2018-03-14 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-03-14 | 7 |  |  | 2018-03-21 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-03-14 | 5 |  |  | 2018-03-19 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Complete Calendar and Document Approval |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-14 | 117 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-14 | 68 |  |  | 2018-05-21 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-14 | 68 |  |  | 2018-05-21 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-15 | 0 |  |  | 2018-03-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-03-15 | 0 |  |  | 2018-03-15 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-15 | 1 |  |  | 2018-03-16 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-15 | 1 |  |  | 2018-03-16 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-15 | 0 |  |  | 2018-03-15 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-15 | 1 |  |  | 2018-03-16 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-15 | 1 |  |  | 2018-03-16 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-15 | 0 |  |  | 2018-03-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-03-15 | 11 |  |  | 2018-03-26 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-03-15 | 12 |  |  | 2018-03-27 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2018-03-15 | 0 |  |  | 2018-03-15 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-16 | 115 |  |  |  | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-16 | 115 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-16 | 115 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-03-16 | 0 |  |  | 2018-03-08 | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-16 | 0 |  |  | 2018-03-06 | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-16 | 115 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Amendment Requires Budget Revisions |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Amendment Requires Contract Amendment |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Cloned Current PAF |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | PAF Complete |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Sent Budget to Sponsor for Revisions |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-03-16 | 115 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-03-16 | 66 |  |  | 2018-05-21 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-03-16 | 3 |  |  | 2018-03-19 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-03-16 | 0 |  |  | 2018-03-16 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-17 | 0 |  |  | 2018-03-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-03-17 | 114 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-03-17 | 114 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-17 | 0 |  |  | 2018-02-02 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-17 | 0 |  |  | 2018-02-02 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-03-17 | 114 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-03-17 | 2 |  |  | 2018-03-19 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-03-17 | 2 |  |  | 2018-03-19 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-03-18 | 113 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-18 | 113 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-03-18 | 0 |  |  | 2018-03-17 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-03-18 | 36 |  |  | 2018-04-23 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-18 | 1 |  |  | 2018-03-19 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-18 | 2 |  |  | 2018-03-20 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-03-18 | 1 |  |  | 2018-03-19 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-19 | 112 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-19 | 112 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-03-19 | 46 |  |  | 2018-05-04 | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-19 | 46 |  |  | 2018-05-04 | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-03-19 | 0 |  |  | 2018-03-08 | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-19 | 0 |  |  | 2018-03-06 | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-03-19 | 112 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-03-19 | 112 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | PI Signed PAF |  |  | User | Farmer, Amber |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Create new OnCore Budget Version |  |  | User | Farmer, Amber |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-19 | 1 |  |  | 2018-03-20 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-19 | 1 |  |  | 2018-03-20 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-19 | 1 |  |  | 2018-03-20 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Final Budget |  |  | User | Henry, Robin |  |  | 2018-03-19 | 112 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Other |  |  | User | Hodges, Lynda |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-03-19 | 6 |  |  | 2018-03-25 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Create new OnCore Budget Version |  |  | User | Yunk, Jason |  |  | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | OnCore Billing Calendar Completed | [6 empty] | 2018-03-19 | 0 |  |  | 2018-03-19 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-20 | 111 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-03-20 | 111 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-03-20 | 111 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-03-20 | 0 |  |  | 2018-03-20 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Complete Calendar and Document Approval |  |  | User | Hess, Aaron |  |  | 2018-03-20 | 0 |  |  | 2018-03-20 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-20 | 7 |  |  | 2018-03-27 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-03-20 | 0 |  |  | 2018-03-20 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-20 | 111 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-20 | 111 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-21 | 110 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-21 | 110 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-21 | 110 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-03-21 | 0 |  |  | 2018-03-08 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-21 | 0 |  |  | 2018-03-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-03-21 | 110 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-21 | 98 |  |  | 2018-06-27 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-03-21 | 1 |  |  | 2018-03-22 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-21 | 1 |  |  | 2018-03-22 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-21 | 30 |  |  | 2018-04-20 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Final Budget |  |  | User | Henry, Robin |  |  | 2018-03-21 | 37 |  |  | 2018-04-27 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Final Budget |  |  | User | Henry, Robin |  |  | 2018-03-21 | 110 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | PAF routed |  |  | User | Henry, Robin |  |  | 2018-03-21 | 110 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-21 | 110 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-21 | 110 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-03-21 | 0 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-03-21 | 0 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-03-21 | 0 |  |  | 2018-03-21 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-21 | 110 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-22 | 0 |  |  | 2018-03-22 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-03-22 | 109 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-03-22 | 0 |  |  | 2018-03-21 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance |  |  | 2018-03-22 | 0 |  |  | 2018-03-22 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-03-22 | 0 |  |  | 2018-03-22 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-03-22 | 8 |  |  | 2018-03-30 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-03-22 | 0 |  |  | 2018-03-21 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-03-22 | 19 |  |  | 2018-04-10 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-22 | 109 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-22 | 109 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-23 | 108 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-23 | 108 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-23 | 108 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-23 | 108 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-03-23 | 108 |  |  |  | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-23 | 108 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-23 | 108 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-23 | 108 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-23 | 108 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-03-23 | 96 |  |  | 2018-06-27 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-03-23 | 70 |  |  | 2018-06-01 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-03-23 | 0 |  |  | 2018-03-23 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-03-23 | 0 |  |  | 2018-03-23 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-03-23 | 108 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-03-23 | 0 |  |  | 2018-03-23 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | PAF routed |  |  | User | Henry, Robin |  |  | 2018-03-23 | 35 |  |  | 2018-04-27 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | PAF routed |  |  | User | Henry, Robin |  |  | 2018-03-23 | 108 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-03-23 | 6 |  |  | 2018-03-29 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-23 | 108 |  |  |  | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-03-23 | 108 |  |  |  | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-23 | 108 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-23 | 108 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-24 | 107 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-24 | 107 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-03-24 | 107 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-03-24 | 107 |  |  |  | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-03-24 | 16 |  |  | 2018-04-09 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-03-24 | 17 |  |  | 2018-04-10 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-03-24 | 17 |  |  | 2018-04-10 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-24 | 107 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-24 | 80 |  |  | 2018-06-12 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-24 | 107 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-24 | 107 |  |  |  | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-25 | 106 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-25 | 0 |  |  | 2018-03-06 | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-25 | 106 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-03-25 | 106 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-25 | 106 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-25 | 106 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-25 | 106 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-25 | 106 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-03-25 | 5 |  |  | 2018-03-30 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-25 | 1 |  |  | 2018-03-26 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-03-25 | 5 |  |  | 2018-03-30 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-25 | 79 |  |  | 2018-06-12 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-25 | 106 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-25 | 106 |  |  |  | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-25 | 106 |  |  |  | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-26 | 105 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-26 | 105 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-26 | 105 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-26 | 105 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-26 | 105 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-26 | 85 |  |  | 2018-06-19 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-03-26 | 2 |  |  | 2018-03-28 | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-03-26 | 105 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-03-26 | 2 |  |  | 2018-03-28 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-03-26 | 2 |  |  | 2018-03-28 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-03-26 | 2 |  |  | 2018-03-28 | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-03-26 | 2 |  |  | 2018-03-28 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-03-26 | 1 |  |  | 2018-03-27 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda |  |  | 2018-03-26 | 14 |  |  | 2018-04-09 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-03-26 | 1 |  |  | 2018-03-27 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Calendar build assigned to CRAO |  |  | User | Hodges, Lynda |  |  | 2018-03-26 | 2 |  |  | 2018-03-28 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-03-26 | 0 |  |  | 2018-03-26 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-03-26 | 0 |  |  | 2018-03-26 | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-03-26 | 0 |  |  | 2018-03-26 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-03-26 | 0 |  |  | 2018-03-26 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 0 |  |  | 2018-03-27 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 0 |  |  | 2018-03-27 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 0 |  |  | 2018-03-27 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 104 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 104 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 104 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-27 | 0 |  |  | 2018-03-27 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-03-27 | 104 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-03-27 | 104 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-03-27 | 104 |  |  |  | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-03-27 | 1 |  |  | 2018-03-28 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-03-27 | 0 |  |  | 2018-03-27 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-28 | 12 |  |  | 2018-04-09 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-28 | 103 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-28 | 96 |  |  | 2018-07-02 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-28 | 103 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-03-28 | 96 |  |  | 2018-07-02 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-03-28 | 103 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-28 | 103 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-28 | 103 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135919 | Next Scheduled Reconciliation |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 103 |  |  |  | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 103 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 103 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 103 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 103 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 0 |  |  | 2018-03-28 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 0 |  |  | 2018-03-28 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Migration Meeting held |  |  | Role | CTSU Finance |  |  | 2018-03-28 | 0 |  |  | 2018-03-28 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121481 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-03-28 | 103 |  |  |  | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-03-28 | 6 |  |  | 2018-04-03 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-03-28 | 7 |  |  | 2018-04-04 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-03-28 | 0 |  |  | 2018-03-27 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-28 | 103 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Yunk, Jason |  |  | 2018-03-28 | 0 |  |  | 2018-03-28 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-03-28 | 22 |  |  | 2018-04-19 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-29 | 102 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-29 | 0 |  |  | 2018-03-27 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-29 | 0 |  |  | 2018-03-27 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-29 | 0 |  |  | 2018-03-27 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-29 | 0 |  |  | 2018-02-28 | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-03-29 | 8 |  |  | 2018-04-06 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-29 | 0 |  |  | 2018-03-27 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-03-29 | 102 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Migration Meeting scheduled |  |  | Role | CTSU Finance |  |  | 2018-03-29 | 0 |  |  | 2018-03-28 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-03-29 | 19 |  |  | 2018-04-17 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-29 | 18 |  |  | 2018-04-16 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-03-29 | 21 |  |  | 2018-04-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-03-29 | 0 |  |  | 2018-03-28 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-03-29 | 48 |  |  | 2018-05-16 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-03-29 | 4 |  |  | 2018-04-02 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-03-29 | 11 |  |  | 2018-04-09 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-03-29 | 0 |  |  | 2018-03-27 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-03-29 | 0 |  |  | 2018-03-28 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-29 | 0 |  |  | 2018-03-27 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-29 | 102 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Budget Build Completed |  |  | User | Yunk, Jason |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Finance Validation Checklist Completed |  |  | User | Yunk, Jason |  |  | 2018-03-29 | 0 |  |  | 2018-03-29 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-03-30 | 101 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Complete MCA / QCT |  |  | User | Hess, Aaron |  |  | 2018-03-30 | 7 |  |  | 2018-04-06 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-03-30 | 4 |  |  | 2018-04-03 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-03-30 | 7 |  |  | 2018-04-06 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-03-30 | 0 |  |  | 2018-03-29 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-03-30 | 0 |  |  | 2018-03-28 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-30 | 66 |  |  | 2018-06-04 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-30 | 17 |  |  | 2018-04-16 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Confirm calendar build completed |  |  | User | Munasinghe, Sadeepa |  |  | 2018-03-30 | 0 |  |  | 2018-03-28 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2018-03-30 | 3 |  |  | 2018-04-02 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2018-03-30 | 3 |  |  | 2018-04-02 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2018-03-30 | 7 |  |  | 2018-04-06 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-03-30 | 0 |  |  | 2018-03-30 | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason |  |  | 2018-03-30 | 0 |  |  | 2018-03-30 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-03-30 | 101 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Complete MCA / QCT |  |  | User | van Dijk, Tim |  |  | 2018-03-30 | 6 |  |  | 2018-04-05 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | van Dijk, Tim |  |  | 2018-03-30 | 3 |  |  | 2018-04-02 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Nimblify Build is Complete & Ready for Import |  |  | User | van Dijk, Tim |  |  | 2018-03-30 | 10 |  |  | 2018-04-09 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-03-31 | 100 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-03-31 | 100 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-03-31 | 0 |  |  | 2018-03-29 | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-03-31 | 18 |  |  | 2018-04-18 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-31 | 0 |  |  | 2018-03-30 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-31 | 0 |  |  | 2018-03-30 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-03-31 | 0 |  |  | 2018-03-30 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-03-31 | 100 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | Assign to Analyst |  |  | User | van Dijk, Tim |  |  | 2018-03-31 | 10 |  |  | 2018-04-10 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-01 | 99 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-01 | 99 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-04-01 | 8 |  |  | 2018-04-09 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-04-01 | 5 |  |  | 2018-04-06 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-04-01 | 5 |  |  | 2018-04-06 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2018-04-01 | 5 |  |  | 2018-04-06 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-04-01 | 5 |  |  | 2018-04-06 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Attach Build Notes ( as Protocol Doc ) |  |  | User | van Dijk, Tim |  |  | 2018-04-01 | 8 |  |  | 2018-04-09 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-04-01 | 8 |  |  | 2018-04-09 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-02 | 98 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-02 | 98 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-02 | 2 |  |  | 2018-04-04 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-02 | 98 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-02 | 0 |  |  | 2018-04-01 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 98 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 98 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 8 |  |  | 2018-04-10 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 0 |  |  | 2018-02-02 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 0 |  |  | 2018-02-02 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 98 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 98 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 98 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 2 |  |  | 2018-04-04 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-04-02 | 4 |  |  | 2018-04-06 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Budget build completed, calendar released |  |  | User | Farmer, Amber |  |  | 2018-04-02 | 13 |  |  | 2018-04-15 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-02 | 9 |  |  | 2018-04-11 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-02 | 9 |  |  | 2018-04-11 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-02 | 1 |  |  | 2018-04-03 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-04-02 | 4 |  |  | 2018-04-06 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-04-02 | 17 |  |  | 2018-04-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-04-02 | 17 |  |  | 2018-04-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-02 | 98 |  |  |  | N |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 685-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-02 | 98 |  |  |  | N |  | 685-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119175 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119399 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123231 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | SAPOC Changed |  |  | User | Yunk, Jason |  |  | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-02 | 0 |  |  | 2018-04-02 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-03 | 97 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-03 | 97 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-03 | 97 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-04-03 | 97 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-04-03 | 0 |  |  | 2018-04-03 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-03 | 0 |  |  | 2018-04-03 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-03 | 0 |  |  | 2018-04-03 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-03 | 0 |  |  | 2018-04-03 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-03 | 0 |  |  | 2018-04-03 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-03 | 97 |  |  |  | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Budget build completed, calendar released |  |  | User | Oliver, Amy |  |  | 2018-04-03 | 12 |  |  | 2018-04-15 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | PI Signed PAF |  |  | User | Yunk, Jason |  |  | 2018-04-03 | 0 |  |  | 2018-04-03 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-04 | 96 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-04 | 96 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-04 | 96 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-04 | 96 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-04 | 0 |  |  | 2018-03-20 | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-04-04 | 0 |  |  | 2018-02-12 | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-04-04 | 0 |  |  | 2018-02-12 | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-04 | 96 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-04 | 96 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | ** Structural Edits |  |  | Role | CTSU Finance |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-04-04 | 15 |  |  | 2018-04-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 14 |  |  | 2018-04-18 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 96 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 1 |  |  | 2018-04-05 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 1 |  |  | 2018-04-05 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 6 |  |  | 2018-04-10 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 26 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 7 |  |  | 2018-04-11 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 5 |  |  | 2018-04-09 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-04 | 1 |  |  | 2018-04-05 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-04-04 | 2 |  |  | 2018-04-06 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-04 | 96 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-04 | 0 |  |  | 2018-04-04 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2018-04-04 | 96 |  |  |  | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-04-04 | 96 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim |  |  | 2018-04-04 | 96 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-05 | 95 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-05 | 95 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-05 | 95 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-05 | 95 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-04-05 | 14 |  |  | 2018-04-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-04-05 | 1 |  |  | 2018-04-06 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-04-05 | 4 |  |  | 2018-04-09 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-04-05 | 0 |  |  | 2018-04-04 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-04-05 | 1 |  |  | 2018-04-06 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | Make Update(s) |  |  | User | Hess, Aaron |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | Re-Complete Calendar |  |  | User | Hess, Aaron |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | Make Update(s) |  |  | User | Hodges, Lynda |  |  | 2018-04-05 | 0 |  |  | 2018-04-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | Re-Complete Calendar |  |  | User | Hodges, Lynda |  |  | 2018-04-05 | 0 |  |  | 2018-04-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-05 | 95 |  |  |  | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-05 | 95 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Create new OnCore Budget Version |  |  | User | Yunk, Jason |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Create new OnCore Budget Version |  |  | User | Yunk, Jason |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120726 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-04-05 | 95 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-04-05 | 95 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-04-05 | 0 |  |  | 2018-04-05 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-04-05 | 5 |  |  | 2018-04-10 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-04-05 | 5 |  |  | 2018-04-10 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Update on subject data collection status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Update on training status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Update on subject data collection status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Update on training status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Update on subject data collection status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Update on training status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Update on subject data collection status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Update on training status - see communications | [6 empty] | 2018-04-05 | 95 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 0 |  |  | 2018-03-26 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 10 |  |  | 2018-04-16 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 10 |  |  | 2018-04-16 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 10 |  |  | 2018-04-16 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 25 |  |  | 2018-05-01 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 25 |  |  | 2018-05-01 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 25 |  |  | 2018-05-01 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 32 |  |  | 2018-05-08 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 32 |  |  | 2018-05-08 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-06 | 32 |  |  | 2018-05-08 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-06 | 0 |  |  | 2018-04-06 | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-06 | 94 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-06 | 0 |  |  | 2018-03-21 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-06 | 94 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-06 | 94 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-06 | 0 |  |  | 2018-04-06 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-04-06 | 13 |  |  | 2018-04-19 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-04-06 | 0 |  |  | 2018-04-06 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-04-06 | 3 |  |  | 2018-04-09 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-04-06 | 67 |  |  | 2018-06-12 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-06 | 0 |  |  | 2018-04-05 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-06 | 6 |  |  | 2018-04-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-06 | 13 |  |  | 2018-04-19 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-04-06 | 4 |  |  | 2018-04-10 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Confirm calendar build completed |  |  | User | Hess, Aaron |  |  | 2018-04-06 | 0 |  |  | 2018-04-05 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-04-06 | 3 |  |  | 2018-04-09 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-04-06 | 0 |  |  | 2018-04-03 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Confirm calendar build completed |  |  | User | Hodges, Lynda |  |  | 2018-04-06 | 0 |  |  | 2018-04-03 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Confirm calendar build completed |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-06 | 0 |  |  | 2018-04-05 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 47 |  |  | 2018-05-23 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 689-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 94 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 94 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 94 |  |  |  | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-06 | 9 |  |  | 2018-04-15 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-04-06 | 0 |  |  | 2018-04-05 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Contract Executed |  |  | User | Yunk, Jason |  |  | 2018-04-06 | 0 |  |  | 2018-04-06 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Confirm calendar build completed |  |  | User | van Dijk, Tim |  |  | 2018-04-06 | 0 |  |  | 2018-04-05 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-07 | 93 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-07 | 93 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-07 | 93 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-04-07 | 2 |  |  | 2018-04-09 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-07 | 2 |  |  | 2018-04-09 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Make Updates |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-07 | 2 |  |  | 2018-04-09 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-04-07 | 0 |  |  | 2018-04-05 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-04-07 | 10 |  |  | 2018-04-17 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-04-07 | 93 |  |  |  | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | Acknowledge |  |  | User | Yunk, Jason |  |  | 2018-04-07 | 10 |  |  | 2018-04-17 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-08 | 92 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-04-08 | 4 |  |  | 2018-04-12 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-04-08 | 19 |  |  | 2018-04-27 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-04-08 | 0 |  |  | 2018-04-06 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-04-08 | 10 |  |  | 2018-04-18 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-08 | 0 |  |  | 2018-04-08 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-08 | 15 |  |  | 2018-04-23 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-08 | 0 |  |  | 2018-04-08 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 7 |  |  | 2018-04-16 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 22 |  |  | 2018-05-01 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 0 |  |  | 2018-04-04 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 0 |  |  | 2018-04-04 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-09 | 29 |  |  | 2018-05-08 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-09 | 91 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-09 | 91 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-09 | 91 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-09 | 91 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-09 | 91 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-09 | 91 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-04-09 | 8 |  |  | 2018-04-17 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 9 |  |  | 2018-04-18 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 1 |  |  | 2018-04-10 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 7 |  |  | 2018-04-16 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 2 |  |  | 2018-04-11 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 2 |  |  | 2018-04-11 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 3 |  |  | 2018-04-12 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 59 |  |  | 2018-06-07 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 3 |  |  | 2018-04-12 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 0 |  |  | 2018-04-06 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 16 |  |  | 2018-04-25 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-09 | 91 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-04-09 | 2 |  |  | 2018-04-11 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-04-09 | 2 |  |  | 2018-04-11 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-04-09 | 1 |  |  | 2018-04-10 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-09 | 11 |  |  | 2018-04-20 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-09 | 0 |  |  | 2018-04-04 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-09 | 0 |  |  | 2018-04-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-10 | 90 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-10 | 35 |  |  | 2018-05-15 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-10 | 31 |  |  | 2018-05-11 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-10 | 1 |  |  | 2018-04-11 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-10 | 90 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-10 | 28 |  |  | 2018-05-08 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-10 | 90 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-04-10 | 6 |  |  | 2018-04-16 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-04-10 | 0 |  |  | 2018-03-30 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-04-10 | 0 |  |  | 2018-04-05 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-04-10 | 1 |  |  | 2018-04-11 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-04-10 | 0 |  |  | 2018-03-02 | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-04-10 | 0 |  |  | 2018-04-06 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-04-10 | 2 |  |  | 2018-04-12 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-04-10 | 2 |  |  | 2018-04-12 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-04-10 | 1 |  |  | 2018-04-11 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-04-10 | 1 |  |  | 2018-04-11 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 715-KHANNA | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-10 | 90 |  |  |  | N |  | 715-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2018-04-10 | 15 |  |  | 2018-04-25 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Make Updates |  |  | User | van Dijk, Tim |  |  | 2018-04-10 | 15 |  |  | 2018-04-25 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 5 |  |  | 2018-04-16 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-11 | 27 |  |  | 2018-05-08 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-11 | 0 |  |  | 2018-04-09 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-11 | 0 |  |  | 2018-04-09 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-11 | 0 |  |  | 2018-04-11 | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-11 | 0 |  |  | 2018-04-11 | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-11 | 0 |  |  | 2018-04-11 | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-04-11 | 89 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-11 | 89 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-11 | 89 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-04-11 | 6 |  |  | 2018-04-17 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-11 | 6 |  |  | 2018-04-17 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-04-11 | 6 |  |  | 2018-04-17 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-11 | 6 |  |  | 2018-04-17 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 5 |  |  | 2018-04-16 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 5 |  |  | 2018-04-16 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 1 |  |  | 2018-04-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 5 |  |  | 2018-04-16 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 0 |  |  | 2018-04-11 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 0 |  |  | 2018-04-11 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 0 |  |  | 2018-03-31 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 0 |  |  | 2018-03-31 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 19 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124998 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-11 | 5 |  |  | 2018-04-16 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-11 | 7 |  |  | 2018-04-18 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason |  |  | 2018-04-11 | 0 |  |  | 2018-04-11 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00081173 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100501 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-04-11 | 89 |  |  |  | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-12 | 8 |  |  | 2018-04-20 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-12 | 88 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-12 | 88 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-12 | 88 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-12 | 61 |  |  | 2018-06-12 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-12 | 88 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-12 | 88 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-12 | 88 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-12 | 29 |  |  | 2018-05-11 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-04-12 | 0 |  |  | 2018-04-12 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-04-12 | 0 |  |  | 2018-04-12 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-04-12 | 13 |  |  | 2018-04-25 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Complete MCA / QCT |  |  | User | Hess, Aaron |  |  | 2018-04-12 | 6 |  |  | 2018-04-18 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-04-12 | 7 |  |  | 2018-04-19 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-04-12 | 4 |  |  | 2018-04-16 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | IRB Amendment Approved in eRRM |  |  | User | Oliver, Amy |  |  | 2018-04-12 | 0 |  |  | 2018-04-12 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-12 | 88 |  |  |  | N |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Complete MCA / QCT |  |  | User | Penix, Faith |  |  | 2018-04-12 | 6 |  |  | 2018-04-18 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-04-12 | 25 |  |  | 2018-05-07 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-04-12 | 88 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Update on subject data collection status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Update on training status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Update on subject data collection status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Update on training status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Update on subject data collection status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Update on training status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Update on subject data collection status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Update on training status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Update on subject data collection status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Update on training status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Update on subject data collection status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Update on training status - see communications | [6 empty] | 2018-04-12 | 88 |  |  |  | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 87 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 87 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 87 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 87 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 87 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 17 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 17 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 17 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 18 |  |  | 2018-05-01 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 17 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 17 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-13 | 17 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-13 | 0 |  |  | 2018-03-15 | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-13 | 87 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-13 | 87 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-13 | 87 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-04-13 | 87 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-04-13 | 87 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-04-13 | 87 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-04-13 | 87 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-04-13 | 27 |  |  | 2018-05-10 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-04-13 | 0 |  |  | 2018-04-12 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-04-13 | 14 |  |  | 2018-04-27 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-13 | 0 |  |  | 2018-04-06 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-04-13 | 87 |  |  |  | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-13 | 12 |  |  | 2018-04-25 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-13 | 0 |  |  | 2018-04-10 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-04-13 | 12 |  |  | 2018-04-25 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-13 | 87 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00108610 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-13 | 11 |  |  | 2018-04-24 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-13 | 12 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason |  |  | 2018-04-13 | 0 |  |  | 2018-04-13 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-14 | 86 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-14 | 86 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-14 | 86 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-04-14 | 30 |  |  | 2018-05-14 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Confirm Calendar is correct and ready for financials |  |  | User | De Filippo, Julie |  |  | 2018-04-14 | 26 |  |  | 2018-05-10 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-04-14 | 5 |  |  | 2018-04-19 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-15 | 85 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-15 | 85 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-04-15 | 85 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-04-15 | 85 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-04-15 | 85 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-04-15 | 85 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 84 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 84 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 84 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 15 |  |  | 2018-05-01 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 14 |  |  | 2018-04-30 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 15 |  |  | 2018-05-01 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 15 |  |  | 2018-05-01 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-16 | 14 |  |  | 2018-04-30 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-04-16 | 84 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-16 | 84 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-16 | 84 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-16 | 84 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-16 | 84 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-16 | 84 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-16 | 84 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-16 | 84 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 0 |  |  | 2018-04-10 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 14 |  |  | 2018-04-30 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | OnCore Calendar Released |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 67 |  |  | 2018-06-22 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | ** Structural Edits |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 14 |  |  | 2018-04-30 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 0 |  |  | 2018-04-12 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-16 | 0 |  |  | 2018-04-12 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Penix, Faith |  |  | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-16 | 0 |  |  | 2018-04-16 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-17 | 0 |  |  | 2018-04-17 | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-17 | 83 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-04-17 | 36 |  |  | 2018-05-23 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-04-17 | 0 |  |  | 2018-04-17 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-04-17 | 48 |  |  | 2018-06-04 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | ** Structural Edits |  |  | User | Farmer, Amber |  |  | 2018-04-17 | 0 |  |  | 2018-04-17 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | Submit Update Request(s) |  |  | User | Farmer, Amber |  |  | 2018-04-17 | 0 |  |  | 2018-04-17 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-04-17 | 7 |  |  | 2018-04-24 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-04-17 | 0 |  |  | 2018-03-06 | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Received Protocol Amendment |  |  | User | Oliver, Amy |  |  | 2018-04-17 | 0 |  |  | 2018-04-17 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 723-MCCUNE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-17 | 83 |  |  |  | N |  | 723-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Oliver, Amy |  |  | 2018-04-17 | 0 |  |  | 2018-04-17 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Nimblify Build is Complete & Ready for Import |  |  | User | Penix, Faith |  |  | 2018-04-17 | 1 |  |  | 2018-04-18 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 82 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 47 |  |  | 2018-06-04 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 20 |  |  | 2018-05-08 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 55 |  |  | 2018-06-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 47 |  |  | 2018-06-04 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-04-18 | 47 |  |  | 2018-06-04 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-18 | 0 |  |  | 2018-04-16 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-18 | 82 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-18 | 82 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-18 | 82 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-18 | 82 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-04-18 | 22 |  |  | 2018-05-10 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-11 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-11 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-16 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 1 |  |  | 2018-04-19 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-11 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-16 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 1 |  |  | 2018-04-19 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 7 |  |  | 2018-04-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 6 |  |  | 2018-04-24 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-12 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-03-31 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-03-31 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 82 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-09 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 12 |  |  | 2018-04-30 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123115 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-04-18 | 0 |  |  | 2018-04-12 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-04-18 | 0 |  |  | 2018-04-10 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 784-LUGOGO | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-18 | 82 |  |  |  | N |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-18 | 82 |  |  |  | N |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-04-18 | 0 |  |  | 2018-04-18 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 1 |  |  | 2018-04-20 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 81 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 81 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 54 |  |  | 2018-06-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 81 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 81 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-04-19 | 46 |  |  | 2018-06-04 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-19 | 81 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-19 | 81 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Send questions to CTSU finance |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-19 | 1 |  |  | 2018-04-20 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Penix, Faith |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Penix, Faith |  |  | 2018-04-19 | 0 |  |  | 2018-04-19 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2018-04-19 | 29 |  |  | 2018-05-18 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2018-04-19 | 4 |  |  | 2018-04-23 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2018-04-19 | 4 |  |  | 2018-04-23 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-04-19 | 0 |  |  | 2018-04-18 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-04-19 | 0 |  |  | 2018-04-18 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-20 | 0 |  |  | 2018-04-20 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-20 | 0 |  |  | 2018-04-20 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-20 | 80 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-20 | 80 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-20 | 80 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-20 | 53 |  |  | 2018-06-12 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-20 | 0 |  |  | 2018-04-20 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-20 | 49 |  |  | 2018-06-08 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-20 | 21 |  |  | 2018-05-11 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-20 | 53 |  |  | 2018-06-12 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-20 | 19 |  |  | 2018-05-09 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-20 | 0 |  |  | 2018-04-17 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-20 | 4 |  |  | 2018-04-24 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-20 | 4 |  |  | 2018-04-24 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-04-20 | 0 |  |  | 2018-04-13 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-04-20 | 3 |  |  | 2018-04-23 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-04-20 | 12 |  |  | 2018-05-02 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-04-20 | 0 |  |  | 2018-03-06 | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-20 | 45 |  |  | 2018-06-04 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00088900 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-20 | 0 |  |  | 2018-04-20 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-20 | 4 |  |  | 2018-04-24 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123661 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-20 | 7 |  |  | 2018-04-27 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-04-20 | 0 |  |  | 2018-04-20 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Confirm calendar build completed |  |  | User | van Dijk, Tim |  |  | 2018-04-20 | 0 |  |  | 2018-04-20 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00066148 | Calendar Released | [6 empty] | 2018-04-20 | 20 |  |  | 2018-05-10 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-21 | 79 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-21 | 79 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-21 | 79 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-21 | 52 |  |  | 2018-06-12 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-21 | 0 |  |  | 2018-03-29 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-21 | 79 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-21 | 79 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-04-21 | 79 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-21 | 79 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-21 | 79 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-21 | 0 |  |  | 2018-04-09 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-04-21 | 13 |  |  | 2018-05-04 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | CTSU finance respond |  |  | User | Farmer, Amber |  |  | 2018-04-21 | 79 |  |  |  | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Final Budget |  |  | User | Henry, Robin |  |  | 2018-04-21 | 0 |  |  | 2018-04-09 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2018-04-21 | 2 |  |  | 2018-04-23 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-04-21 | 2 |  |  | 2018-04-23 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-04-21 | 0 |  |  | 2018-04-20 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-22 | 0 |  |  | 2018-02-16 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-22 | 4 |  |  | 2018-04-26 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-04-22 | 0 |  |  | 2018-03-06 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-22 | 78 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-04-22 | 22 |  |  | 2018-05-14 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-04-22 | 19 |  |  | 2018-05-11 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-04-22 | 4 |  |  | 2018-04-26 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-04-22 | 58 |  |  | 2018-06-19 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-04-22 | 47 |  |  | 2018-06-08 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-04-22 | 11 |  |  | 2018-05-03 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-22 | 0 |  |  | 2018-04-20 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Request Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-22 | 0 |  |  | 2018-04-20 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Update RSH Source in MBECT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-22 | 46 |  |  | 2018-06-07 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-04-23 | 77 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-23 | 0 |  |  | 2018-04-03 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-23 | 77 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-23 | 77 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-23 | 10 |  |  | 2018-05-03 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-23 | 0 |  |  | 2018-03-20 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-23 | 0 |  |  | 2018-04-23 | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-04-23 | 77 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-23 | 77 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-04-23 | 77 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-04-23 | 0 |  |  | 2018-04-17 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-04-23 | 0 |  |  | 2018-04-17 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-23 | 0 |  |  | 2018-04-23 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-23 | 1 |  |  | 2018-04-24 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | PAF routed |  |  | User | Henry, Robin |  |  | 2018-04-23 | 15 |  |  | 2018-05-08 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-04-23 | 14 |  |  | 2018-05-07 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-23 | 2 |  |  | 2018-04-25 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-23 | 2 |  |  | 2018-04-25 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Complete MCA / QCT |  |  | User | Penix, Faith |  |  | 2018-04-23 | 8 |  |  | 2018-05-01 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Penix, Faith |  |  | 2018-04-23 | 21 |  |  | 2018-05-14 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2018-04-23 | 15 |  |  | 2018-05-08 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2018-04-23 | 2 |  |  | 2018-04-25 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2018-04-23 | 9 |  |  | 2018-05-02 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-23 | 16 |  |  | 2018-05-09 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-23 | 16 |  |  | 2018-05-09 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-23 | 0 |  |  | 2018-04-23 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-04-24 | 76 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-04-24 | 76 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-04-24 | 76 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-04-24 | 49 |  |  | 2018-06-12 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-24 | 0 |  |  | 2018-04-24 | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-24 | 0 |  |  | 2018-04-24 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Final Budget |  |  | User | Henry, Robin |  |  | 2018-04-24 | 13 |  |  | 2018-05-07 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Visits : Addition or Removal of Time Points |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-24 | 8 |  |  | 2018-05-02 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Request Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-04-24 | 8 |  |  | 2018-05-02 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-24 | 0 |  |  | 2018-04-24 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | Make Update(s) |  |  | User | Przykucki, Anne |  |  | 2018-04-24 | 0 |  |  | 2018-04-23 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | Re-Complete Calendar |  |  | User | Przykucki, Anne |  |  | 2018-04-24 | 0 |  |  | 2018-04-23 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-04-24 | 76 |  |  |  | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-25 | 75 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-25 | 75 |  |  |  | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-25 | 75 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-25 | 54 |  |  | 2018-06-18 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-25 | 75 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-25 | 75 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-04-25 | 0 |  |  | 2018-03-28 | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-04-25 | 75 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-25 | 75 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-25 | 75 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-04-25 | 75 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-04-25 | 75 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | Role | CTSU Finance |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-24 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 0 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-04-25 | 15 |  |  | 2018-05-10 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-04-25 | 14 |  |  | 2018-05-09 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-04-25 | 75 |  |  |  | N |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-25 | 75 |  |  |  | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2018-04-25 | 12 |  |  | 2018-05-07 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-04-25 | 12 |  |  | 2018-05-07 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | OnCore Billing Calendar Completed | [6 empty] | 2018-04-25 | 75 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-26 | 0 |  |  | 2018-04-26 | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-04-26 | 12 |  |  | 2018-05-08 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-04-26 | 56 |  |  | 2018-06-21 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-04-26 | 56 |  |  | 2018-06-21 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-04-26 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | CTSU finance respond |  |  | User | Farmer, Amber |  |  | 2018-04-26 | 0 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-04-26 | 0 |  |  | 2018-04-25 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-04-26 | 0 |  |  | 2018-04-25 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | PAF routed |  |  | User | Henry, Robin |  |  | 2018-04-26 | 11 |  |  | 2018-05-07 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Update on subject data collection status - see communications | [6 empty] | 2018-04-26 | 74 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Update on training status - see communications | [6 empty] | 2018-04-26 | 74 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Update on subject data collection status - see communications | [6 empty] | 2018-04-26 | 74 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Update on training status - see communications | [6 empty] | 2018-04-26 | 74 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 11 |  |  | 2018-05-08 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 11 |  |  | 2018-05-08 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 39 |  |  | 2018-06-05 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 39 |  |  | 2018-06-05 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 39 |  |  | 2018-06-05 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 73 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 73 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 73 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 46 |  |  | 2018-06-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 73 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 38 |  |  | 2018-06-04 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-04-27 | 38 |  |  | 2018-06-04 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-27 | 73 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-27 | 73 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-27 | 73 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-04-27 | 73 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Confirm Calendar is correct and ready for financials |  |  | User | De Filippo, Julie |  |  | 2018-04-27 | 13 |  |  | 2018-05-10 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-04-27 | 42 |  |  | 2018-06-08 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-04-27 | 28 |  |  | 2018-05-25 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-04-27 | 7 |  |  | 2018-05-04 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-04-27 | 0 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Send questions to CTSU finance |  |  | User | Hodges, Lynda |  |  | 2018-04-27 | 0 |  |  | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-04-27 | 0 |  |  | 2018-04-27 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-04-27 | 0 |  |  | 2018-04-27 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-27 | 10 |  |  | 2018-05-07 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-27 | 28 |  |  | 2018-05-25 | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Nimblify Build is Complete & Ready for Import |  |  | User | Penix, Faith |  |  | 2018-04-27 | 14 |  |  | 2018-05-11 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Send questions to CTSU finance |  |  | User | Przykucki, Anne |  |  | 2018-04-27 | 7 |  |  | 2018-05-04 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Assign to Analyst |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-27 | 0 |  |  | 2018-04-25 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Send questions to CTSU finance |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-27 | 0 |  |  | 2018-04-25 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Confirm calendar build completed |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-27 | 0 |  |  | 2018-04-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-04-27 | 0 |  |  | 2018-04-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 72 |  |  |  | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 37 |  |  | 2018-06-04 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 10 |  |  | 2018-05-08 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 45 |  |  | 2018-06-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 72 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 37 |  |  | 2018-06-04 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-04-28 | 37 |  |  | 2018-06-04 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-28 | 72 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-28 | 72 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-28 | 72 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-04-28 | 11 |  |  | 2018-05-09 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2018-04-28 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2018-04-28 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda |  |  | 2018-04-28 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-04-28 | 41 |  |  | 2018-06-08 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-28 | 0 |  |  | 2018-04-25 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Footnote Edits |  |  | User | van Dijk, Tim |  |  | 2018-04-28 | 19 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2018-04-28 | 19 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim |  |  | 2018-04-28 | 19 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | CTSU finance respond |  |  | Role | CTSU Finance |  |  | 2018-04-29 | 71 |  |  |  | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-04-29 | 11 |  |  | 2018-05-10 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-04-29 | 54 |  |  | 2018-06-22 | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | CTSU finance respond |  |  | User | Farmer, Amber |  |  | 2018-04-29 | 11 |  |  | 2018-05-10 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-04-29 | 25 |  |  | 2018-05-24 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2018-04-29 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Attach Build Notes ( as Protocol Doc ) |  |  | User | Penix, Faith |  |  | 2018-04-29 | 15 |  |  | 2018-05-14 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Penix, Faith |  |  | 2018-04-29 | 23 |  |  | 2018-05-22 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim |  |  | 2018-04-29 | 18 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-04-30 | 70 |  |  |  | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-30 | 70 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-04-30 | 70 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-30 | 36 |  |  | 2018-06-05 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-04-30 | 70 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-04-30 | 70 |  |  |  | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 17 |  |  | 2018-05-17 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 0 |  |  | 2018-04-12 | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 0 |  |  | 2018-04-12 | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 21 |  |  | 2018-05-21 | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 21 |  |  | 2018-05-21 | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-04-30 | 70 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-30 | 70 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-04-30 | 70 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-30 | 70 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-04-30 | 70 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-04-30 | 22 |  |  | 2018-05-22 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-04-30 | 22 |  |  | 2018-05-22 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-04-30 | 30 |  |  | 2018-05-30 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Feedback from CTSU to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-04-30 | 70 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Initial Feedback from CTSU to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-04-30 | 70 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Received Protocol Amendment |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066148 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00094631 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00099421 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00102868 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00109151 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00116976 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119527 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120883 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127612 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130757 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130803 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131329 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134035 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134236 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134443 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134444 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134933 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134997 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 582-SCHIOPU | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-04-30 | 1 |  |  | 2018-05-01 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-30 | 0 |  |  | 2018-04-27 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Calendar build assigned to CRAO |  |  | User | Greene, Paula |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-04-30 | 8 |  |  | 2018-05-08 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-04-30 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda |  |  | 2018-04-30 | 0 |  |  | 2018-04-26 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Penix, Faith |  |  | 2018-04-30 | 53 |  |  | 2018-06-22 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-04-30 | 14 |  |  | 2018-05-14 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Make Updates |  |  | User | Przykucki, Anne |  |  | 2018-04-30 | 14 |  |  | 2018-05-14 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline |  |  | 2018-04-30 | 0 |  |  | 2018-04-25 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066077 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119175 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119399 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120726 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123231 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim |  |  | 2018-04-30 | 17 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim |  |  | 2018-04-30 | 17 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Request Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-04-30 | 17 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Update RSH Source in MBECT |  |  | User | van Dijk, Tim |  |  | 2018-04-30 | 17 |  |  | 2018-05-17 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-30 | 70 |  |  |  | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-04-30 | 0 |  |  | 2018-04-30 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 16 |  |  | 2018-05-17 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 36 |  |  | 2018-06-06 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 10 |  |  | 2018-05-11 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 42 |  |  | 2018-06-12 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 69 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 35 |  |  | 2018-06-05 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-01 | 35 |  |  | 2018-06-05 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-01 | 0 |  |  | 2018-05-01 | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-05-01 | 69 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Department Reach out |  |  | User | Farmer, Amber |  |  | 2018-05-01 | 0 |  |  | 2018-05-01 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Migration Meeting held |  |  | User | Farmer, Amber |  |  | 2018-05-01 | 0 |  |  | 2018-05-01 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Migration Meeting scheduled |  |  | User | Farmer, Amber |  |  | 2018-05-01 | 0 |  |  | 2018-05-01 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 68 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 68 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 68 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 41 |  |  | 2018-06-12 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 9 |  |  | 2018-05-11 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 34 |  |  | 2018-06-05 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 68 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 47 |  |  | 2018-06-18 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 68 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 41 |  |  | 2018-06-12 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-02 | 47 |  |  | 2018-06-18 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-02 | 0 |  |  | 2018-04-13 | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-02 | 0 |  |  | 2018-04-12 | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-02 | 14 |  |  | 2018-05-16 | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-02 | 14 |  |  | 2018-05-16 | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-02 | 0 |  |  | 2018-04-16 | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-02 | 0 |  |  | 2018-04-16 | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 68 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 68 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 68 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 68 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 68 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 68 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-02 | 0 |  |  | 2018-05-02 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-05-02 | 15 |  |  | 2018-05-17 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Confirm Calendar is correct and ready for financials |  |  | User | De Filippo, Julie |  |  | 2018-05-02 | 56 |  |  | 2018-06-27 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-05-02 | 0 |  |  | 2018-04-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-05-02 | 13 |  |  | 2018-05-15 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-02 | 1 |  |  | 2018-05-03 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-02 | 0 |  |  | 2018-04-30 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Calendar Released |  |  | User | Yunk, Jason |  |  | 2018-05-02 | 68 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-03 | 67 |  |  |  | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-05-03 | 40 |  |  | 2018-06-12 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-05-03 | 67 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-03 | 0 |  |  | 2018-05-03 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-03 | 42 |  |  | 2018-06-14 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-03 | 67 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-03 | 19 |  |  | 2018-05-22 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-05-03 | 0 |  |  | 2018-04-12 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-03 | 19 |  |  | 2018-05-22 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-05-03 | 14 |  |  | 2018-05-17 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Huffman, Kate |  |  | 2018-05-03 | 29 |  |  | 2018-06-01 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-03 | 1 |  |  | 2018-05-04 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason |  |  | 2018-05-03 | 0 |  |  | 2018-05-03 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-03 | 67 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-03 | 67 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Update on subject data collection status - see communications | [6 empty] | 2018-05-03 | 67 |  |  |  | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Update on training status - see communications | [6 empty] | 2018-05-03 | 67 |  |  |  | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-05-04 | 21 |  |  | 2018-05-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-05-04 | 21 |  |  | 2018-05-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-05-04 | 21 |  |  | 2018-05-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-04 | 0 |  |  | 2018-05-01 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-04 | 11 |  |  | 2018-05-15 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-04 | 0 |  |  | 2018-03-01 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-04 | 66 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-04 | 66 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-04 | 66 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-04 | 66 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-05-04 | 3 |  |  | 2018-05-07 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | OnCore Billing Calendar Change Needed |  |  | User | Farmer, Amber |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | AME Calendaring Process Initiated |  |  | User | Farmer, Amber |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-05-04 | 0 |  |  | 2018-05-01 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-04 | 66 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-04 | 66 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-04 | 18 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-05-04 | 14 |  |  | 2018-05-18 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Make Updates |  |  | User | Przykucki, Anne |  |  | 2018-05-04 | 14 |  |  | 2018-05-18 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Confirm calendar build completed |  |  | User | Przykucki, Anne |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Confirm calendar build completed |  |  | User | Weathers, Sarah |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | OnCore Billing Calendar Change Needed |  |  | User | Yunk, Jason |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Received Protocol Amendment |  |  | User | Yunk, Jason |  |  | 2018-05-04 | 0 |  |  | 2018-05-04 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-05 | 65 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-05 | 65 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-05 | 65 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-05 | 65 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-05 | 65 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-05-05 | 25 |  |  | 2018-05-30 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-05-05 | 25 |  |  | 2018-05-30 | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-05-05 | 17 |  |  | 2018-05-22 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-05-05 | 4 |  |  | 2018-05-09 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Request Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-05 | 0 |  |  | 2018-05-04 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Update RSH Source in MBECT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-05 | 65 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-05 | 30 |  |  | 2018-06-04 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-05 | 65 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-05 | 65 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-06 | 64 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-06 | 64 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-06 | 64 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-05-06 | 43 |  |  | 2018-06-18 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-05-06 | 43 |  |  | 2018-06-18 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-05-06 | 24 |  |  | 2018-05-30 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Final Budget |  |  | User | Henry, Robin |  |  | 2018-05-06 | 19 |  |  | 2018-05-25 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Footnote Edits |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-06 | 31 |  |  | 2018-06-06 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-06 | 64 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-06 | 64 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-06 | 1 |  |  | 2018-05-07 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 18 |  |  | 2018-05-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-07 | 0 |  |  | 2018-05-07 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-07 | 63 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-07 | 63 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-05-07 | 45 |  |  | 2018-06-21 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Planning Meeting Completed |  |  | User | De Filippo, Julie |  |  | 2018-05-07 | 0 |  |  | 2018-04-04 | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-05-07 | 3 |  |  | 2018-05-10 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Footnote Edits |  |  | User | Hess, Aaron |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Visit Tolerance Edits |  |  | User | Hess, Aaron |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hess, Aaron |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | CTSU finance respond |  |  | User | Oliver, Amy |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 792-NELSON | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2018-05-07 | 63 |  |  |  | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | van Dijk, Tim |  |  | 2018-05-07 | 22 |  |  | 2018-05-29 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-08 | 62 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-08 | 0 |  |  | 2018-05-04 | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-08 | 0 |  |  | 2018-05-03 | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-08 | 62 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-05-08 | 62 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | PAF routed |  |  | User | De Filippo, Julie |  |  | 2018-05-08 | 62 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 62 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-02 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 10 |  |  | 2018-05-18 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-02 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-05-08 | 0 |  |  | 2018-05-08 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | PAF routed |  |  | User | Henry, Robin |  |  | 2018-05-08 | 27 |  |  | 2018-06-04 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-05-08 | 62 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Visits : Addition or Removal of Time Points |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-08 | 29 |  |  | 2018-06-06 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Request Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-08 | 29 |  |  | 2018-06-06 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Update RSH Source in MBECT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-08 | 62 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Penix, Faith |  |  | 2018-05-08 | 23 |  |  | 2018-05-31 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Make Updates |  |  | User | Penix, Faith |  |  | 2018-05-08 | 23 |  |  | 2018-05-31 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-08 | 62 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-08 | 62 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-05-09 | 16 |  |  | 2018-05-25 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-09 | 1 |  |  | 2018-05-10 | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-09 | 61 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-09 | 61 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-04-24 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Amendment Requires Budget Revisions |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 61 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-05-09 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber |  |  | 2018-05-09 | 0 |  |  | 2018-05-09 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Other |  |  | User | Hess, Aaron |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hess, Aaron |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | ** Visits : Addition or Removal of Time Points |  |  | User | Hess, Aaron |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Request Care Designations |  |  | User | Hess, Aaron |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Update RSH Source in MBECT |  |  | User | Hess, Aaron |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-09 | 61 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-09 | 61 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-09 | 61 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-05-10 | 33 |  |  | 2018-06-12 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-10 | 0 |  |  | 2018-05-10 | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-05-10 | 60 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-05-10 | 0 |  |  | 2018-04-20 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | AME Calendaring Process Initiated |  |  | User | De Filippo, Julie |  |  | 2018-05-10 | 0 |  |  | 2018-05-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-05-10 | 27 |  |  | 2018-06-06 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-05-10 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-05-10 | 12 |  |  | 2018-05-22 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-05-10 | 19 |  |  | 2018-05-29 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-10 | 20 |  |  | 2018-05-30 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-10 | 60 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Przykucki, Anne |  |  | 2018-05-10 | 0 |  |  | 2018-05-10 | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-10 | 60 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Update on subject data collection status - see communications | [6 empty] | 2018-05-10 | 60 |  |  |  | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Update on training status - see communications | [6 empty] | 2018-05-10 | 60 |  |  |  | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Update on subject data collection status - see communications | [6 empty] | 2018-05-10 | 60 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Update on training status - see communications | [6 empty] | 2018-05-10 | 60 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 45 |  |  | 2018-06-25 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 32 |  |  | 2018-06-12 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 25 |  |  | 2018-06-05 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 25 |  |  | 2018-06-05 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 25 |  |  | 2018-06-05 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-11 | 0 |  |  | 2018-05-11 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-11 | 59 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-11 | 0 |  |  | 2018-05-04 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-11 | 0 |  |  | 2018-05-03 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-11 | 59 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-11 | 59 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-11 | 59 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-11 | 59 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-11 | 59 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-11 | 59 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-05-11 | 0 |  |  | 2018-03-07 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-05-11 | 27 |  |  | 2018-06-07 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-05-11 | 38 |  |  | 2018-06-18 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Initiate CRAO Amendment Task List |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 0 |  |  | 2018-05-11 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 0 |  |  | 2018-05-11 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121107 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-05-11 | 11 |  |  | 2018-05-22 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-11 | 59 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-12 | 58 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-12 | 58 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-05-12 | 37 |  |  | 2018-06-18 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-05-12 | 58 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-12 | 58 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-12 | 58 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-05-12 | 23 |  |  | 2018-06-04 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-05-12 | 10 |  |  | 2018-05-22 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-05-12 | 0 |  |  | 2018-05-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Complete Calendar and Document Approval |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-12 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-12 | 51 |  |  | 2018-07-02 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-13 | 57 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-13 | 57 |  |  |  | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-13 | 57 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-13 | 57 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-13 | 57 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-13 | 57 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2018-05-13 | 0 |  |  | 2018-05-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2018-05-13 | 0 |  |  | 2018-05-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda |  |  | 2018-05-13 | 0 |  |  | 2018-05-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Oliver, Amy |  |  | 2018-05-13 | 57 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Send questions to CTSU finance |  |  | User | Penix, Faith |  |  | 2018-05-13 | 1 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-13 | 0 |  |  | 2018-05-11 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-14 | 56 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-14 | 56 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-14 | 44 |  |  | 2018-06-27 | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-05-14 | 22 |  |  | 2018-06-05 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Notify study team to start validation |  |  | Role | CTSU Administrator |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-14 | 56 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-14 | 0 |  |  | 2018-03-08 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-14 | 24 |  |  | 2018-06-07 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | De Filippo, Julie |  |  | 2018-05-14 | 10 |  |  | 2018-05-24 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Received completed calendar from CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Transition Checklist signed by department |  |  | User | Farmer, Amber |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | Initiate Post-Award Task List |  |  | User | Oliver, Amy |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 696-LOK | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-14 | 56 |  |  |  | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-14 | 8 |  |  | 2018-05-22 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Footnote Edits |  |  | User | Penix, Faith |  |  | 2018-05-14 | 0 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 35 |  |  | 2018-06-19 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-15 | 55 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | CTSU finance respond |  |  | User | Farmer, Amber |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-05-15 | 0 |  |  | 2018-05-10 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-15 | 55 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-15 | 36 |  |  | 2018-06-20 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-16 | 0 |  |  | 2018-05-16 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-16 | 54 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-16 | 40 |  |  | 2018-06-25 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-16 | 54 |  |  |  | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-05-16 | 20 |  |  | 2018-06-05 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-05-16 | 54 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-16 | 54 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-16 | 54 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-05-16 | 21 |  |  | 2018-06-06 | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-05-16 | 23 |  |  | 2018-06-08 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | ** Other Request(s) |  |  | User | Farmer, Amber |  |  | 2018-05-16 | 0 |  |  | 2018-05-16 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-05-16 | 1 |  |  | 2018-05-17 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-05-16 | 1 |  |  | 2018-05-17 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-05-16 | 1 |  |  | 2018-05-17 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-05-16 | 1 |  |  | 2018-05-17 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-05-16 | 1 |  |  | 2018-05-17 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-05-16 | 1 |  |  | 2018-05-17 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Complete Calendar and Document Approval |  |  | User | Hess, Aaron |  |  | 2018-05-16 | 54 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Send questions to CTSU finance |  |  | User | Hodges, Lynda |  |  | 2018-05-16 | 0 |  |  | 2018-05-15 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-16 | 54 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 825-ORAL | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-16 | 54 |  |  |  | N |  | 825-ORAL |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Request Care Designations |  |  | User | Penix, Faith |  |  | 2018-05-16 | 0 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-16 | 0 |  |  | 2018-05-15 | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-16 | 0 |  |  | 2018-05-16 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Initial feedback from CRAO to CTSU |  |  | User | van Dijk, Tim |  |  | 2018-05-16 | 54 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Make Updates |  |  | User | van Dijk, Tim |  |  | 2018-05-16 | 54 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-17 | 53 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-05-17 | 39 |  |  | 2018-06-25 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Check-in on validation progress |  |  | Role | CTSU Administrator |  |  | 2018-05-17 | 53 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-17 | 53 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-17 | 53 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-17 | 53 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-17 | 53 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-17 | 53 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-17 | 53 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Confirm Calendar is correct and ready for financials |  |  | User | De Filippo, Julie |  |  | 2018-05-17 | 35 |  |  | 2018-06-21 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-05-18 | 25 |  |  | 2018-06-12 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-18 | 0 |  |  | 2018-05-16 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-18 | 52 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-18 | 52 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 205-KHANNA | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 52 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 52 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 52 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00102868 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Access to all PAFs confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Access to budget/contract confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-16 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | SAPOC Changed |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120029 | Sponsor contact info received |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 0 |  |  | 2018-05-18 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-05-18 | 52 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-05-18 | 18 |  |  | 2018-06-05 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-05-18 | 0 |  |  | 2018-05-15 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-18 | 52 |  |  |  | N |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 833-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-18 | 52 |  |  |  | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-05-18 | 0 |  |  | 2018-04-25 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | van Dijk, Tim |  |  | 2018-05-18 | 52 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-05-19 | 24 |  |  | 2018-06-12 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-19 | 51 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-05-19 | 51 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-19 | 51 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-19 | 51 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-19 | 51 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-19 | 51 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Complete MCA / QCT |  |  | User | Penix, Faith |  |  | 2018-05-19 | 4 |  |  | 2018-05-23 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Penix, Faith |  |  | 2018-05-19 | 5 |  |  | 2018-05-24 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Nimblify Build is Complete & Ready for Import |  |  | User | Penix, Faith |  |  | 2018-05-19 | 10 |  |  | 2018-05-29 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-05-20 | 50 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Confirm Calendar is correct and ready for financials |  |  | User | Oliver, Amy |  |  | 2018-05-20 | 9 |  |  | 2018-05-29 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Feedback from CRAO to CTSU |  |  | User | van Dijk, Tim |  |  | 2018-05-20 | 50 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-21 | 49 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-21 | 49 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-21 | 1 |  |  | 2018-05-22 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-21 | 36 |  |  | 2018-06-26 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-21 | 0 |  |  | 2018-05-21 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-21 | 49 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-21 | 49 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-21 | 0 |  |  | 2018-05-14 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-21 | 0 |  |  | 2018-05-14 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 49 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Department Reach out |  |  | Role | CTSU Finance |  |  | 2018-05-21 | 0 |  |  | 2018-05-21 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-05-21 | 0 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-05-21 | 49 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-05-21 | 0 |  |  | 2018-05-21 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 834-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-21 | 49 |  |  |  | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 835-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-21 | 49 |  |  |  | N |  | 835-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Attach Build Notes ( as Protocol Doc ) |  |  | User | Penix, Faith |  |  | 2018-05-21 | 8 |  |  | 2018-05-29 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Penix, Faith |  |  | 2018-05-21 | 10 |  |  | 2018-05-31 | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2018-05-21 | 0 |  |  | 2018-05-21 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2018-05-21 | 0 |  |  | 2018-05-21 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-22 | 48 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-22 | 48 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-22 | 21 |  |  | 2018-06-12 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-22 | 0 |  |  | 2018-05-11 | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-22 | 0 |  |  | 2018-05-10 | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-05-22 | 48 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 482-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 697-LOK | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-22 | 48 |  |  |  | N |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-22 | 48 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-23 | 26 |  |  | 2018-06-18 | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-23 | 0 |  |  | 2018-05-23 | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-23 | 0 |  |  | 2018-05-23 | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-23 | 47 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-23 | 47 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-23 | 47 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-23 | 47 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-23 | 47 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142488 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-23 | 0 |  |  | 2018-05-23 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | Acknowledge |  |  | User | Farmer, Amber |  |  | 2018-05-23 | 0 |  |  | 2018-05-23 | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-23 | 47 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-05-23 | 47 |  |  |  | N |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-23 | 47 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Penix, Faith |  |  | 2018-05-23 | 0 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason |  |  | 2018-05-23 | 0 |  |  | 2018-05-23 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00141300 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-23 | 0 |  |  | 2018-05-23 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-24 | 14 |  |  | 2018-06-07 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-24 | 46 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-24 | 46 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-05-24 | 46 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-05-24 | 46 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-24 | 46 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-24 | 46 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-05-24 | 0 |  |  | 2018-05-24 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Feasibility Approval Notice Received |  |  | User | Hess, Aaron |  |  | 2018-05-24 | 0 |  |  | 2018-05-24 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Initial feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-24 | 46 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-24 | 46 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2018-05-24 | 6 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-05-24 | 6 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-05-24 | 6 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne |  |  | 2018-05-24 | 6 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne |  |  | 2018-05-24 | 6 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-05-24 | 6 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-24 | 46 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-24 | 46 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-25 | 45 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-25 | 45 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-05-25 | 31 |  |  | 2018-06-25 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Confirm study team validation complete |  |  | Role | CTSU Administrator |  |  | 2018-05-25 | 45 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-25 | 0 |  |  | 2018-05-25 | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-25 | 45 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-05-25 | 45 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-25 | 45 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2018-05-25 | 0 |  |  | 2018-05-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Create new OnCore Budget Version |  |  | User | Farmer, Amber |  |  | 2018-05-25 | 45 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-05-25 | 45 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2018-05-25 | 0 |  |  | 2018-05-25 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda |  |  | 2018-05-25 | 0 |  |  | 2018-05-24 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-05-25 | 0 |  |  | 2018-05-25 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-25 | 45 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-25 | 45 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-26 | 44 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-26 | 44 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-05-26 | 30 |  |  | 2018-06-25 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-05-26 | 44 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-26 | 44 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-05-26 | 44 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-05-26 | 44 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-05-26 | 44 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-26 | 44 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-26 | 44 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-05-26 | 4 |  |  | 2018-05-30 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Final Budget |  |  | User | Henry, Robin |  |  | 2018-05-26 | 9 |  |  | 2018-06-04 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-26 | 44 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Feedback from CTSU to CRAO |  |  | User | Oliver, Amy |  |  | 2018-05-26 | 44 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Initial feedback from CTSU to CRAO |  |  | User | Oliver, Amy |  |  | 2018-05-26 | 44 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Send questions to CTSU finance |  |  | User | Przykucki, Anne |  |  | 2018-05-26 | 0 |  |  | 2018-05-25 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-05-26 | 0 |  |  | 2018-05-25 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-26 | 44 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-26 | 44 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Acknowledge |  |  | User | De Filippo, Julie |  |  | 2018-05-27 | 0 |  |  | 2018-05-25 | N |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Assign to Analyst |  |  | User | Hess, Aaron |  |  | 2018-05-27 | 0 |  |  | 2018-05-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-27 | 43 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-27 | 43 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2018-05-27 | 5 |  |  | 2018-06-01 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-05-27 | 5 |  |  | 2018-06-01 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 23 |  |  | 2018-06-20 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 0 |  |  | 2018-05-28 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 42 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 42 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 42 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 42 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-28 | 42 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-28 | 0 |  |  | 2018-05-08 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-28 | 42 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-28 | 42 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-05-28 | 42 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-05-28 | 1 |  |  | 2018-05-29 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-05-28 | 1 |  |  | 2018-05-29 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-05-28 | 1 |  |  | 2018-05-29 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | PAF routed |  |  | User | Henry, Robin |  |  | 2018-05-28 | 42 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hess, Aaron |  |  | 2018-05-28 | 2 |  |  | 2018-05-30 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-05-28 | 1 |  |  | 2018-05-29 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-05-28 | 7 |  |  | 2018-06-04 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa |  |  | 2018-05-28 | 42 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-28 | 42 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Confirm Calendar is correct and ready for financials |  |  | User | Oliver, Amy |  |  | 2018-05-28 | 42 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-05-28 | 4 |  |  | 2018-06-01 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-05-29 | 41 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-29 | 15 |  |  | 2018-06-13 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-29 | 28 |  |  | 2018-06-26 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-05-29 | 41 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-29 | 0 |  |  | 2018-05-16 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-29 | 0 |  |  | 2018-05-15 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-29 | 0 |  |  | 2018-05-29 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-29 | 41 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-05-29 | 41 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-05-29 | 0 |  |  | 2018-05-29 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Final Budget |  |  | User | De Filippo, Julie |  |  | 2018-05-29 | 41 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-05-29 | 1 |  |  | 2018-05-30 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-05-29 | 0 |  |  | 2018-05-29 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne |  |  | 2018-05-29 | 3 |  |  | 2018-06-01 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-05-29 | 3 |  |  | 2018-06-01 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne |  |  | 2018-05-29 | 3 |  |  | 2018-06-01 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-05-29 | 41 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 28 |  |  | 2018-06-27 | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-30 | 0 |  |  | 2018-05-24 | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-30 | 0 |  |  | 2018-05-24 | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-30 | 0 |  |  | 2018-05-18 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-30 | 0 |  |  | 2018-04-30 | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-30 | 40 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-30 | 40 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-05-30 | 40 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066148 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00094631 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00099421 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00102868 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00109151 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00116976 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119527 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120883 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127612 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130757 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130803 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131329 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134035 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134236 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134443 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134444 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134933 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134997 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 582-SCHIOPU | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 40 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber |  |  | 2018-05-30 | 0 |  |  | 2018-05-14 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-05-30 | 2 |  |  | 2018-06-01 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-05-30 | 1 |  |  | 2018-05-31 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-05-30 | 0 |  |  | 2018-05-30 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Request Care Designations |  |  | User | Hess, Aaron |  |  | 2018-05-30 | 1 |  |  | 2018-05-31 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-05-30 | 0 |  |  | 2018-05-29 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-05-30 | 0 |  |  | 2018-05-29 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Penix, Faith |  |  | 2018-05-30 | 16 |  |  | 2018-06-15 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Penix, Faith |  |  | 2018-05-30 | 40 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Make Updates |  |  | User | Penix, Faith |  |  | 2018-05-30 | 40 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason |  |  | 2018-05-30 | 0 |  |  | 2018-05-30 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066077 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119175 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119399 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120726 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123231 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-05-30 | 40 |  |  |  | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-05-31 | 39 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-05-31 | 39 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-05-31 | 39 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-31 | 39 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-05-31 | 39 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-05-31 | 39 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-31 | 39 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-05-31 | 39 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-05-31 | 39 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082007 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082896 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00088900 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00106445 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108610 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111185 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111923 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115761 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00117806 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121049 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123115 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123661 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124998 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125022 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125493 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00126010 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127136 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128325 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129652 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129716 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131837 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131840 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131953 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132020 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132173 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132200 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132700 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133286 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133290 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133684 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134040 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135268 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136152 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00137399 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138579 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140577 | Date Reconciled |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-29 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Farmer, Amber |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-05-31 | 0 |  |  | 2018-05-29 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-05-31 | 0 |  |  | 2018-05-30 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-05-31 | 0 |  |  | 2018-05-30 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00077539 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00081173 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089260 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089615 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089664 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00095080 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00096782 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00096782 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00098496 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100452 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100501 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101426 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00104229 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00105982 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107927 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107954 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108880 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113391 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113496 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113845 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114593 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00114593 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114708 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115787 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118069 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118570 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119871 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122254 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122910 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123861 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124920 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125425 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125566 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125786 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125794 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127537 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127778 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128157 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128531 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128743 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129427 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129820 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129851 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130575 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133054 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133153 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133341 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133457 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134232 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134503 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134870 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134884 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134895 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134896 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135072 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135279 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135388 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136538 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136916 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136917 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136918 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138433 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140097 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140403 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-05-31 | 0 |  |  | 2018-05-31 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-01 | 38 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-01 | 38 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-01 | 0 |  |  | 2018-05-18 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-01 | 38 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-01 | 38 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-01 | 38 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-01 | 38 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-01 | 38 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-01 | 38 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-06-01 | 38 |  |  |  | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-06-01 | 14 |  |  | 2018-06-15 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-01 | 38 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-02 | 37 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-02 | 9 |  |  | 2018-06-11 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-02 | 37 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-06-02 | 0 |  |  | 2018-05-21 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-06-02 | 17 |  |  | 2018-06-19 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-06-02 | 0 |  |  | 2018-05-31 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-06-02 | 0 |  |  | 2018-05-30 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-06-02 | 0 |  |  | 2018-05-30 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-02 | 37 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-02 | 37 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-03 | 0 |  |  | 2018-04-27 | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-03 | 0 |  |  | 2018-05-04 | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-06-03 | 36 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-03 | 36 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-06-03 | 36 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-03 | 36 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-04 | 35 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 0 |  |  | 2018-06-04 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Initial feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 0 |  |  | 2018-06-04 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Received completed calendar from CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-04 | 0 |  |  | 2018-06-04 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Send questions to CTSU finance |  |  | User | Hodges, Lynda |  |  | 2018-06-04 | 0 |  |  | 2018-06-04 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 12-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-04 | 35 |  |  |  | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-06-04 | 0 |  |  | 2018-06-04 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Calendar build assigned to CRAO |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-04 | 2 |  |  | 2018-06-06 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason |  |  | 2018-06-04 | 0 |  |  | 2018-06-04 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Start timeline (2 weeks before study go-live date) | [6 empty] | 2018-06-04 | 35 |  |  |  | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-05 | 34 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-05 | 34 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-05 | 34 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-05 | 34 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | CTSU finance respond |  |  | User | Farmer, Amber |  |  | 2018-06-05 | 34 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-06-05 | 0 |  |  | 2018-06-05 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-05 | 0 |  |  | 2018-06-05 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-06-05 | 34 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127778 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-06-05 | 34 |  |  |  | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-05 | 34 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-06 | 33 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-06 | 33 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-06 | 33 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-06 | 33 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-06 | 33 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-06-06 | 0 |  |  | 2018-06-05 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Budget Build Completed |  |  | User | Farmer, Amber |  |  | 2018-06-06 | 0 |  |  | 2018-06-06 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-06-06 | 0 |  |  | 2018-06-04 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Complete Calendar and Document Approval |  |  | User | Hess, Aaron |  |  | 2018-06-06 | 33 |  |  |  | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2018-06-06 | 1 |  |  | 2018-06-07 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2018-06-06 | 1 |  |  | 2018-06-07 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Other |  |  | User | Hodges, Lynda |  |  | 2018-06-06 | 1 |  |  | 2018-06-07 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-06 | 33 |  |  |  | N |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-06 | 33 |  |  |  | N |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-06 | 33 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-07 | 32 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-07 | 32 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-07 | 32 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-07 | 32 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-07 | 32 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-06-07 | 0 |  |  | 2018-05-31 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-06-07 | 0 |  |  | 2018-06-07 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-06-07 | 0 |  |  | 2018-06-05 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-08 | 31 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-08 | 31 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-08 | 31 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-08 | 0 |  |  | 2018-06-08 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-08 | 31 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 31 |  |  |  | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 0 |  |  | 2018-06-08 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-08 | 0 |  |  | 2018-06-08 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-06-08 | 3 |  |  | 2018-06-11 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-06-08 | 3 |  |  | 2018-06-11 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-06-08 | 3 |  |  | 2018-06-11 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Confirm Calendar is correct and ready for financials |  |  | User | Henry, Robin |  |  | 2018-06-08 | 6 |  |  | 2018-06-14 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-06-08 | 0 |  |  | 2018-06-08 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-08 | 31 |  |  |  | N |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 879-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-08 | 31 |  |  |  | N |  | 879-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Confirm calendar build completed |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-08 | 0 |  |  | 2018-06-06 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128173 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-06-08 | 0 |  |  | 2018-06-08 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-09 | 30 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-09 | 30 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-09 | 30 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-09 | 30 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-06-09 | 0 |  |  | 2018-06-07 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-06-09 | 0 |  |  | 2018-06-08 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-06-09 | 0 |  |  | 2018-06-05 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-06-09 | 0 |  |  | 2018-06-06 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-10 | 0 |  |  | 2018-05-21 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-10 | 29 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-10 | 29 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie |  |  | 2018-06-10 | 0 |  |  | 2018-05-29 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie |  |  | 2018-06-10 | 0 |  |  | 2018-05-29 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-06-10 | 10 |  |  | 2018-06-20 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Complete MCA / QCT |  |  | User | Weathers, Sarah |  |  | 2018-06-10 | 3 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Weathers, Sarah |  |  | 2018-06-10 | 1 |  |  | 2018-06-11 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Nimblify Build is Complete & Ready for Import |  |  | User | Weathers, Sarah |  |  | 2018-06-10 | 2 |  |  | 2018-06-12 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-11 | 0 |  |  | 2018-06-07 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-11 | 28 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-11 | 28 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-11 | 0 |  |  | 2018-05-23 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-11 | 0 |  |  | 2018-06-11 | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-11 | 0 |  |  | 2018-06-11 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-11 | 28 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-11 | 28 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-06-11 | 0 |  |  | 2018-05-30 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-06-11 | 0 |  |  | 2018-06-05 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-06-11 | 0 |  |  | 2018-05-03 | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Complete MCA / QCT |  |  | User | Hess, Aaron |  |  | 2018-06-11 | 0 |  |  | 2018-06-11 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-06-11 | 0 |  |  | 2018-06-11 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-06-11 | 7 |  |  | 2018-06-18 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-11 | 28 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne |  |  | 2018-06-11 | 0 |  |  | 2018-06-11 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122254 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-06-11 | 0 |  |  | 2018-03-12 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2018-06-11 | 28 |  |  |  | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-12 | 0 |  |  | 2018-06-12 | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-12 | 27 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-12 | 0 |  |  | 2018-06-12 | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-12 | 0 |  |  | 2018-06-12 | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-12 | 27 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-12 | 27 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber |  |  | 2018-06-12 | 27 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber |  |  | 2018-06-12 | 27 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-06-12 | 27 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-06-12 | 0 |  |  | 2018-06-12 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Attach Build Notes ( as Protocol Doc ) |  |  | User | Weathers, Sarah |  |  | 2018-06-12 | 1 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Weathers, Sarah |  |  | 2018-06-12 | 0 |  |  | 2018-06-12 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-13 | 26 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-13 | 26 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-06-13 | 0 |  |  | 2018-05-29 | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-13 | 0 |  |  | 2018-05-29 | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-06-13 | 0 |  |  | 2018-06-12 | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-13 | 0 |  |  | 2018-06-11 | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-13 | 0 |  |  | 2018-06-13 | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134933 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-06-13 | 26 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-06-13 | 6 |  |  | 2018-06-19 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-06-13 | 6 |  |  | 2018-06-19 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-06-13 | 0 |  |  | 2018-06-07 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | ** Other Request(s) |  |  | User | Oliver, Amy |  |  | 2018-06-13 | 0 |  |  | 2018-06-13 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | Submit Update Request(s) |  |  | User | Oliver, Amy |  |  | 2018-06-13 | 0 |  |  | 2018-06-13 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140656 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-06-13 | 0 |  |  | 2018-06-13 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-14 | 25 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-14 | 25 |  |  |  | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-14 | 25 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-14 | 25 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-06-14 | 0 |  |  | 2018-06-11 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-06-14 | 0 |  |  | 2018-06-06 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-06-14 | 25 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Initial feedback from CRAO to CTSU |  |  | User | Przykucki, Anne |  |  | 2018-06-14 | 25 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Make Updates |  |  | User | Przykucki, Anne |  |  | 2018-06-14 | 25 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2018-06-14 | 0 |  |  | 2018-06-14 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Update on subject data collection status - see communications | [6 empty] | 2018-06-14 | 25 |  |  |  | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Update on training status - see communications | [6 empty] | 2018-06-14 | 25 |  |  |  | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 0 |  |  | 2018-06-15 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 24 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 24 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 0 |  |  | 2018-06-15 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 10 |  |  | 2018-06-25 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 10 |  |  | 2018-06-25 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator |  |  | 2018-06-15 | 10 |  |  | 2018-06-25 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-15 | 24 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-15 | 24 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-06-15 | 0 |  |  | 2018-06-15 | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-15 | 0 |  |  | 2018-06-14 | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-15 | 24 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | PAN Released |  |  | Role | CTSU Finance |  |  | 2018-06-15 | 24 |  |  |  | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-15 | 24 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-15 | 24 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-15 | 24 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121049 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-06-15 | 24 |  |  |  | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125022 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-06-15 | 0 |  |  | 2018-03-08 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131953 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-06-15 | 0 |  |  | 2018-03-08 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138579 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-06-15 | 0 |  |  | 2018-03-08 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-06-15 | 3 |  |  | 2018-06-18 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-06-15 | 3 |  |  | 2018-06-18 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-06-15 | 0 |  |  | 2018-06-15 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Assign to Analyst |  |  | User | Greene, Paula |  |  | 2018-06-15 | 3 |  |  | 2018-06-18 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Feasibility Approval Notice Received |  |  | User | Greene, Paula |  |  | 2018-06-15 | 3 |  |  | 2018-06-18 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Greene, Paula |  |  | 2018-06-15 | 0 |  |  | 2018-06-15 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-06-15 | 0 |  |  | 2018-04-27 | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | AME Calendaring Process Initiated |  |  | User | Huffman, Kate |  |  | 2018-06-15 | 0 |  |  | 2018-06-15 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 830-CONJEEVARAM | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-15 | 24 |  |  |  | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Oliver, Amy |  |  | 2018-06-15 | 24 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-06-15 | 0 |  |  | 2018-06-14 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-16 | 23 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-16 | 23 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-16 | 23 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-16 | 23 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-06-16 | 23 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-06-16 | 23 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-06-16 | 23 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-17 | 0 |  |  | 2018-05-18 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-17 | 0 |  |  | 2018-06-15 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-17 | 22 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-17 | 22 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-06-17 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Request Research Pharmacy Budget |  |  | User | Henry, Robin |  |  | 2018-06-17 | 22 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Initial Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-06-17 | 22 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-06-17 | 22 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-06-17 | 1 |  |  | 2018-06-18 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-18 | 0 |  |  | 2018-06-18 | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-06-18 | 21 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-18 | 21 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-18 | 21 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-18 | 21 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-18 | 21 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-18 | 21 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Billing Calendar Received |  |  | User | De Filippo, Julie |  |  | 2018-06-18 | 8 |  |  | 2018-06-26 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-06-18 | 21 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-06-18 | 0 |  |  | 2018-06-15 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-06-18 | 0 |  |  | 2018-05-04 | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-06-18 | 11 |  |  | 2018-06-29 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-06-18 | 21 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-06-18 | 0 |  |  | 2018-06-18 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Huffman, Kate |  |  | 2018-06-18 | 3 |  |  | 2018-06-21 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 893-PAI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-06-18 | 21 |  |  |  | N |  | 893-PAI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne |  |  | 2018-06-18 | 21 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Complete MCA / QCT |  |  | User | Przykucki, Anne |  |  | 2018-06-18 | 1 |  |  | 2018-06-19 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Przykucki, Anne |  |  | 2018-06-18 | 3 |  |  | 2018-06-21 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Nimblify Build is Complete & Ready for Import |  |  | User | Przykucki, Anne |  |  | 2018-06-18 | 7 |  |  | 2018-06-25 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-18 | 21 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-18 | 21 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-18 | 21 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-18 | 21 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-19 | 0 |  |  | 2018-05-30 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-19 | 20 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-19 | 20 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | AME Calendaring Process Initiated |  |  | Role | CTSU Finance |  |  | 2018-06-19 | 0 |  |  | 2018-06-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-19 | 20 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-19 | 20 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-06-19 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-06-19 | 20 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-19 | 20 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-19 | 20 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-19 | 20 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-20 | 19 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-20 | 19 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | CTSU Admin validation completed |  |  | Role | CTSU Administrator |  |  | 2018-06-20 | 5 |  |  | 2018-06-25 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-20 | 19 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-20 | 19 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-20 | 19 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-20 | 19 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-20 | 19 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-06-20 | 6 |  |  | 2018-06-26 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Henry, Robin |  |  | 2018-06-20 | 19 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-06-20 | 19 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-06-20 | 19 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda |  |  | 2018-06-20 | 0 |  |  | 2018-06-20 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Lynda |  |  | 2018-06-20 | 0 |  |  | 2018-06-18 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-06-20 | 0 |  |  | 2018-06-19 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | Make Update(s) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-20 | 0 |  |  | 2018-06-20 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | Re-Complete Calendar |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-20 | 0 |  |  | 2018-06-20 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-20 | 19 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-20 | 19 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 830-CONJEEVARAM | CRAO Approval Issue & Documented |  |  | User | Penix, Faith |  |  | 2018-06-20 | 0 |  |  | 2018-06-20 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Attach Build Notes ( as Protocol Doc ) |  |  | User | Przykucki, Anne |  |  | 2018-06-20 | 7 |  |  | 2018-06-27 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-06-20 | 7 |  |  | 2018-06-27 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Other |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-20 | 19 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-20 | 19 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-20 | 19 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Request Care Designations |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-20 | 19 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-20 | 19 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-21 | 18 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-21 | 18 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-21 | 18 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-06-21 | 18 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber |  |  | 2018-06-21 | 18 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-06-21 | 0 |  |  | 2018-06-13 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-06-21 | 18 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-06-21 | 0 |  |  | 2018-05-10 | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Henry, Robin |  |  | 2018-06-21 | 0 |  |  | 2018-06-21 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Assign to Analyst |  |  | User | Hess, Aaron |  |  | 2018-06-21 | 0 |  |  | 2018-06-20 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-06-21 | 18 |  |  |  | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Initial Feedback from CRAO to CTSU |  |  | User | Weathers, Sarah |  |  | 2018-06-21 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Make Updates |  |  | User | Weathers, Sarah |  |  | 2018-06-21 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-21 | 18 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-21 | 18 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-21 | 18 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-22 | 0 |  |  | 2018-06-22 | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-22 | 17 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 17 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 0 |  |  | 2018-05-31 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-06-22 | 17 |  |  |  | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-06-22 | 0 |  |  | 2018-05-10 | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-06-22 | 0 |  |  | 2018-05-07 | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Footnote Edits |  |  | User | Hess, Aaron |  |  | 2018-06-22 | 0 |  |  | 2018-06-20 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-06-22 | 0 |  |  | 2018-06-20 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hess, Aaron |  |  | 2018-06-22 | 0 |  |  | 2018-06-20 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-06-22 | 13 |  |  | 2018-07-05 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-06-22 | 0 |  |  | 2018-06-22 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-06-22 | 5 |  |  | 2018-06-27 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-06-22 | 5 |  |  | 2018-06-27 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-22 | 17 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-22 | 17 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-22 | 17 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-23 | 16 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-23 | 16 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-23 | 16 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Feedback from CTSU to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-06-23 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Initial Feedback from CTSU to CRAO |  |  | User | De Filippo, Julie |  |  | 2018-06-23 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142488 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-23 | 16 |  |  |  | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-06-23 | 16 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hess, Aaron |  |  | 2018-06-23 | 0 |  |  | 2018-06-20 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Initial feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-06-23 | 16 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-06-23 | 16 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-06-23 | 0 |  |  | 2018-06-22 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Weathers, Sarah |  |  | 2018-06-23 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00141300 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-23 | 16 |  |  |  | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-24 | 15 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-06-24 | 15 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-06-24 | 15 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-24 | 15 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-24 | 15 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-24 | 15 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-06-24 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-06-24 | 15 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | Acknowledge |  |  | User | Henry, Robin |  |  | 2018-06-24 | 15 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-06-24 | 11 |  |  | 2018-07-05 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Footnote Edits |  |  | User | Przykucki, Anne |  |  | 2018-06-24 | 2 |  |  | 2018-06-26 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne |  |  | 2018-06-24 | 2 |  |  | 2018-06-26 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-25 | 14 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-25 | 14 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-25 | 14 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-25 | 14 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-06-25 | 14 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-25 | 0 |  |  | 2018-06-21 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-25 | 14 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-06-25 | 14 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-25 | 14 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Care Designations completed |  |  | User | De Filippo, Julie |  |  | 2018-06-25 | 1 |  |  | 2018-06-26 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Confirm Calendar is correct and ready for financials |  |  | User | De Filippo, Julie |  |  | 2018-06-25 | 0 |  |  | 2018-06-14 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber |  |  | 2018-06-25 | 14 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-06-25 | 0 |  |  | 2018-05-09 | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-06-25 | 14 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Billing Calendar Received |  |  | User | Henry, Robin |  |  | 2018-06-25 | 14 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Final Budget |  |  | User | Henry, Robin |  |  | 2018-06-25 | 14 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-06-25 | 14 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Feasibility Approval Notice Received |  |  | User | Hodges, Lynda |  |  | 2018-06-25 | 0 |  |  | 2018-06-25 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Feasibility Approval Notice Received |  |  | User | LaVasseur, Kristen |  |  | 2018-06-25 | 0 |  |  | 2018-06-25 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Feasibility Approval Notice Received |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-25 | 0 |  |  | 2018-06-25 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | Feedback from CRAO to CTSU |  |  | User | Weathers, Sarah |  |  | 2018-06-25 | 0 |  |  | 2018-06-13 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-26 | 0 |  |  | 2018-06-26 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-26 | 0 |  |  | 2018-06-26 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-26 | 0 |  |  | 2018-06-26 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-06-26 | 13 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Confirm Calendar is correct and ready for financials |  |  | User | De Filippo, Julie |  |  | 2018-06-26 | 13 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-06-26 | 13 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | CRAO Approval Issue & Documented |  |  | User | Penix, Faith |  |  | 2018-06-26 | 0 |  |  | 2018-06-26 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Request Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-06-26 | 0 |  |  | 2018-06-26 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-27 | 12 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-27 | 12 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-06-27 | 12 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-27 | 12 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-27 | 12 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-27 | 12 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-06-27 | 12 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Confirm Calendar is correct and ready for financials |  |  | User | Farmer, Amber |  |  | 2018-06-27 | 12 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | PAF routed |  |  | User | Henry, Robin |  |  | 2018-06-27 | 12 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2018-06-27 | 0 |  |  | 2018-06-25 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2018-06-27 | 0 |  |  | 2018-06-27 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2018-06-27 | 0 |  |  | 2018-06-25 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda |  |  | 2018-06-27 | 0 |  |  | 2018-06-27 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda |  |  | 2018-06-27 | 0 |  |  | 2018-06-25 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda |  |  | 2018-06-27 | 0 |  |  | 2018-06-25 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-06-27 | 12 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | AME Calendaring Process Initiated |  |  | User | Huffman, Kate |  |  | 2018-06-27 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Submit Calendar Build Request and Docs to Nimblify |  |  | User | LaVasseur, Kristen |  |  | 2018-06-27 | 0 |  |  | 2018-06-25 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Submit Calendar Build Request and Docs to Nimblify |  |  | User | LaVasseur, Kristen |  |  | 2018-06-27 | 0 |  |  | 2018-06-25 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Assign to Analyst |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-27 | 1 |  |  | 2018-06-28 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne |  |  | 2018-06-27 | 0 |  |  | 2018-06-27 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Complete Calendar and Document Approval |  |  | User | Radenbaugh, Pauline |  |  | 2018-06-27 | 12 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-06-27 | 1 |  |  | 2018-06-28 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-06-27 | 12 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-28 | 0 |  |  | 2018-06-22 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-28 | 11 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-06-28 | 11 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-28 | 0 |  |  | 2018-06-26 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-28 | 0 |  |  | 2018-06-27 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 11 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-06-28 | 11 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Feasibility Approval Notice Received |  |  | User | Hess, Aaron |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Assign to Analyst |  |  | User | Hodges, Lynda |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-28 | 11 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142051 | Date Reconciled |  |  | User | Yunk, Jason |  |  | 2018-06-28 | 0 |  |  | 2018-06-28 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Intake Form Completed |  |  | Role | CTSU Coordinator |  |  | 2018-06-29 | 0 |  |  | 2018-06-29 | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-06-29 | 0 |  |  | 2018-06-25 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00126010 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-06-29 | 0 |  |  | 2018-06-05 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Planning Meeting Completed |  |  | User | Henry, Robin |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Initial Feedback from CRAO to CTSU |  |  | User | Hess, Aaron |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | CRAO Approval Issued & Documented |  |  | User | Hess, Aaron |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hess, Aaron |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-06-29 | 0 |  |  | 2018-06-28 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda |  |  | 2018-06-29 | 0 |  |  | 2018-06-27 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Initial Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | CRAO Approval Issued & Documented |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Initial Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Make Updates |  |  | User | Przykucki, Anne |  |  | 2018-06-29 | 10 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-06-29 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | CRAO Approval Issued & Documented |  |  | User | Weathers, Sarah |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Weathers, Sarah |  |  | 2018-06-29 | 10 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-06-29 | 0 |  |  | 2018-06-29 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Notify support team to activate interface |  |  | Role | CTSU Administrator |  |  | 2018-06-30 | 0 |  |  | 2018-06-25 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-06-30 | 0 |  |  | 2018-06-28 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00096782 | Next Scheduled Reconciliation |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00096782 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082007 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082896 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00088900 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00106445 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108610 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111185 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111923 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115761 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00117806 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121049 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123115 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123661 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124998 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125022 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125493 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00126010 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127136 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128325 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129652 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129716 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131837 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131840 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131953 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132020 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132173 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132200 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132700 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133286 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133290 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133684 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134040 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135268 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136152 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00137399 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138579 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140577 | Next Scheduled Reconciliation |  |  | User | Farmer, Amber |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Assign to Analyst |  |  | User | Hess, Aaron |  |  | 2018-06-30 | 0 |  |  | 2018-06-28 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron |  |  | 2018-06-30 | 0 |  |  | 2018-06-28 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Footnote Edits |  |  | User | Hodges, Lynda |  |  | 2018-06-30 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda |  |  | 2018-06-30 | 0 |  |  | 2018-06-28 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda |  |  | 2018-06-30 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Complete MCA / QCT |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-30 | 9 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-06-30 | 5 |  |  | 2018-07-05 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Complete MCA / QCT |  |  | User | Weathers, Sarah |  |  | 2018-06-30 | 2 |  |  | 2018-07-02 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Weathers, Sarah |  |  | 2018-06-30 | 2 |  |  | 2018-07-02 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Nimblify Build is Complete & Ready for Import |  |  | User | Weathers, Sarah |  |  | 2018-06-30 | 3 |  |  | 2018-07-03 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00077539 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00081173 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089260 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089615 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089664 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00095080 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00098496 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100452 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100501 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101426 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00104229 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00105982 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107927 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107954 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108880 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113391 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113496 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113845 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114593 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00114593 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114708 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115787 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118069 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118570 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119871 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122254 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122910 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123861 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124920 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125425 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125566 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125786 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125794 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127537 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127778 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128157 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128531 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128743 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129427 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129820 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129851 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130575 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133054 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133153 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133341 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133457 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134232 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134503 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134870 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134884 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134895 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134896 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135072 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135279 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135388 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136538 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136916 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136917 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136918 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138433 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140097 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140403 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-06-30 | 9 |  |  |  | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-01 | 8 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Complete Calendar and Document Approval |  |  | User | Hess, Aaron |  |  | 2018-07-01 | 0 |  |  | 2018-06-25 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Complete MCA / QCT |  |  | User | Hodges, Lynda |  |  | 2018-07-01 | 0 |  |  | 2018-06-29 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda |  |  | 2018-07-01 | 0 |  |  | 2018-06-29 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-07-01 | 8 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-07-01 | 1 |  |  | 2018-07-02 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-02 | 7 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-02 | 0 |  |  | 2018-06-27 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-02 | 0 |  |  | 2018-06-21 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-02 | 0 |  |  | 2018-06-25 | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 0 |  |  | 2018-06-28 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Amendment Requires Budget Revisions |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Create new OnCore Budget Version |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | OnCore Billing Calendar Completed |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 0 |  |  | 2018-07-02 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Revised Billing Grid Sent to Study Team |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 0 |  |  | 2018-07-02 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 0 |  |  | 2018-07-02 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-07-02 | 7 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Care Designations completed |  |  | User | Henry, Robin |  |  | 2018-07-02 | 7 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Other |  |  | User | Hodges, Lynda |  |  | 2018-07-02 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda |  |  | 2018-07-02 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Request Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-07-02 | 0 |  |  | 2018-06-27 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | OnCore Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 933-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-02 | 7 |  |  |  | N |  | 933-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 935-MIAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-02 | 7 |  |  |  | N |  | 935-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Attach Build Notes ( as Protocol Doc ) |  |  | User | Weathers, Sarah |  |  | 2018-07-02 | 3 |  |  | 2018-07-05 | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Weathers, Sarah |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107927 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113496 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119175 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119399 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123231 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128531 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133054 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134870 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134884 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134895 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134896 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136916 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136917 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136918 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 7 |  |  |  | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | Submit Update Request(s) |  |  | User | Yunk, Jason |  |  | 2018-07-02 | 0 |  |  | 2018-07-02 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-03 | 6 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-03 | 6 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Confirm interface activated |  |  | Role | CTSU Administrator |  |  | 2018-07-03 | 0 |  |  | 2018-06-26 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-07-03 | 2 |  |  | 2018-07-05 | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-03 | 2 |  |  | 2018-07-05 | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 6 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 6 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 0 |  |  | 2018-07-03 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Feedback from CRAO to CTSU |  |  | User | Hess, Aaron |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron |  |  | 2018-07-03 | 0 |  |  | 2018-07-02 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Nimblify Build is Complete & Ready for Import |  |  | User | Hess, Aaron |  |  | 2018-07-03 | 6 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne |  |  | 2018-07-03 | 6 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne |  |  | 2018-07-03 | 6 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-03 | 6 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-04 | 5 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-04 | 5 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Send welcome email to study teams |  |  | Role | CTSU Administrator |  |  | 2018-07-04 | 0 |  |  | 2018-06-27 | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-04 | 5 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-04 | 5 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-07-04 | 0 |  |  | 2018-07-02 | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-04 | 0 |  |  | 2018-07-02 | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-04 | 5 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-04 | 5 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-04 | 5 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-04 | 5 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-04 | 5 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-04 | 5 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-07-04 | 5 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 938-KWON | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-04 | 5 |  |  |  | N |  | 938-KWON |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 939-ASKARI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-04 | 5 |  |  |  | N |  | 939-ASKARI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 940-COMER | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-04 | 5 |  |  |  | N |  | 940-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-04 | 5 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | Assign to Analyst |  |  | User | Weathers, Sarah |  |  | 2018-07-04 | 0 |  |  | 2018-07-03 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-04 | 5 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-05 | 4 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-05 | 4 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron |  |  | 2018-07-05 | 4 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hess, Aaron |  |  | 2018-07-05 | 4 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-05 | 0 |  |  | 2018-07-05 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-05 | 4 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120726 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-05 | 4 |  |  |  | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-06 | 3 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-06 | 3 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-06 | 3 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-06 | 3 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-06 | 3 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-06 | 3 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-07-06 | 3 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Internal Budget Finished |  |  | User | Henry, Robin |  |  | 2018-07-06 | 3 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-06 | 3 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | Make Update(s) |  |  | User | van Dijk, Tim |  |  | 2018-07-06 | 0 |  |  | 2018-07-03 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | Re-Complete Calendar |  |  | User | van Dijk, Tim |  |  | 2018-07-06 | 0 |  |  | 2018-07-03 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-07 | 2 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-07 | 2 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-07 | 2 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-07 | 2 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-07 | 2 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-07 | 2 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-07 | 2 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-07 | 0 |  |  | 2018-05-10 | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-07 | 0 |  |  | 2018-07-05 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-07 | 0 |  |  | 2018-07-05 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-07 | 2 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-08 | 1 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-08 | 1 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-08 | 1 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-08 | 1 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-07-08 | 1 |  |  |  | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128173 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-07-08 | 1 |  |  |  | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-09 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-09 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-09 | 0 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-07-09 | 0 |  |  | 2018-06-27 | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-09 | 0 |  |  | 2018-06-27 | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-09 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-09 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Internal Budget Finished |  |  | User | De Filippo, Julie |  |  | 2018-07-09 | 0 |  |  | 2018-06-12 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-07-09 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | PAF routed |  |  | User | Henry, Robin |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | PI approved Budget |  |  | User | Henry, Robin |  |  | 2018-07-09 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Nimblify Build is Complete & Ready for Import |  |  | User | Hodges, Lynda |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | Make Update(s) |  |  | User | Radenbaugh, Pauline |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00095080 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-09 | 0 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-10 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-10 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-10 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-10 | 0 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-10 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-10 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082007 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-10 | 0 |  |  | 2018-04-17 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115761 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-10 | 0 |  |  | 2018-04-17 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-07-10 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-07-10 | 0 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-10 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 960-PARIKH | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-10 | 0 |  |  |  | N |  | 960-PARIKH |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114708 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-10 | 0 |  |  | 2018-01-25 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | Acknowledge |  |  | Role | CTSU Finance |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127136 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-11 | 0 |  |  | 2018-04-04 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133286 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-11 | 0 |  |  | 2017-12-20 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133290 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-11 | 0 |  |  | 2018-04-04 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-11 | 0 |  |  | 2018-05-15 | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-11 | 0 |  |  | 2018-05-09 | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Budget Negotiations |  |  | User | Henry, Robin |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hodges, Elise |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 730-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-11 | 0 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Initial Feedback from CRAO to CTSU |  |  | User | Weathers, Sarah |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Make Updates |  |  | User | Weathers, Sarah |  |  | 2018-07-11 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-11 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-12 | 0 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | PI approved Budget |  |  | User | De Filippo, Julie |  |  | 2018-07-12 | 0 |  |  | 2018-06-15 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00137399 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-12 | 0 |  |  | 2017-12-20 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142488 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-12 | 0 |  |  | 2017-12-18 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | PAF routed |  |  | User | Henry, Robin |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-12 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Initial feedback from CRAO to CTSU |  |  | User | Przykucki, Anne |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Make Updates |  |  | User | Przykucki, Anne |  |  | 2018-07-12 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-07-13 | 0 |  |  | 2018-06-21 | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-13 | 0 |  |  | 2018-06-21 | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00117806 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-13 | 0 |  |  | 2018-04-12 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Initial feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Weathers, Sarah |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140656 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-07-13 | 0 |  |  |  | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-13 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-14 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-14 | 0 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-14 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-14 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-14 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Initial feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-14 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-14 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Budget Negotiations |  |  | User | De Filippo, Julie |  |  | 2018-07-14 | 0 |  |  | 2018-06-21 | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | OnCore Budget Build |  |  | User | Farmer, Amber |  |  | 2018-07-14 | 0 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Initial Feedback from CRAO to CTSU |  |  | User | Hess, Aaron |  |  | 2018-07-14 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Make Updates |  |  | User | Hess, Aaron |  |  | 2018-07-14 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-14 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Przykucki, Anne |  |  | 2018-07-14 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-14 | 0 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-15 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-15 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-15 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-15 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-15 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Initial feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-15 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-15 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-07-15 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-15 | 0 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-15 | 0 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00114919 | Feedback from CRAO to CTSU |  |  | User | Weathers, Sarah |  |  | 2018-07-15 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-16 | 0 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hess, Aaron |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Initial Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Make Updates |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-16 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-16 | 0 |  |  |  | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00104229 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122910 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-16 | 0 |  |  | 2018-04-19 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129427 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-16 | 0 |  |  |  | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-17 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-17 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-17 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-17 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-17 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-17 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-17 | 0 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-17 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130757 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-17 | 0 |  |  | 2018-05-16 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130803 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-17 | 0 |  |  | 2018-05-16 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132173 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-17 | 0 |  |  |  | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-07-17 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 982-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-17 | 0 |  |  |  | N |  | 982-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119871 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-17 | 0 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-18 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Feedback from CRAO to CTSU |  |  | User | Hess, Aaron |  |  | 2018-07-18 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-18 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-19 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082896 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-19 | 0 |  |  | 2018-04-30 | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00106445 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-19 | 0 |  |  | 2018-04-10 | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-19 | 0 |  |  |  | N |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-19 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator |  |  | 2018-07-20 | 0 |  |  | 2018-06-29 | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Initial Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-07-20 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Make Updates |  |  | User | Hodges, Lynda |  |  | 2018-07-20 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1019-LUGOGO | Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-20 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-21 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-21 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-21 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-22 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-22 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-23 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-23 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-23 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-23 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-23 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129716 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-23 | 0 |  |  | 2018-04-23 | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-07-23 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-07-23 | 0 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-23 | 0 |  |  |  | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-23 | 0 |  |  |  | N |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-24 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-24 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-24 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-07-24 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-24 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-24 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-24 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-24 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance |  |  | 2018-07-24 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda |  |  | 2018-07-24 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1004-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-24 | 0 |  |  |  | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134503 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-24 | 0 |  |  |  | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-25 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-07-25 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-25 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-25 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-25 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-25 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Final Budget |  |  | User | Henry, Robin |  |  | 2018-07-25 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-26 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128325 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-26 | 0 |  |  | 2018-03-19 | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-26 | 0 |  |  |  | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-07-27 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-27 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | PAF routed |  |  | User | Henry, Robin |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | PAF routed |  |  | User | Henry, Robin |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066077 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-27 | 0 |  |  | 2018-03-23 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114593 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-27 | 0 |  |  | 2018-03-23 | N |  | 00114593 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129851 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-07-27 | 0 |  |  | 2018-03-23 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Initiate Post-Award Task List |  |  | User | Yunk, Jason |  |  | 2018-07-27 | 0 |  |  |  | N |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-28 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142051 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason |  |  | 2018-07-28 | 0 |  |  |  | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-28 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-07-29 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-07-30 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-07-30 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132700 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-07-30 | 0 |  |  | 2018-05-21 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-07-31 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-31 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-07-31 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-07-31 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1027-JAYASUNDERA | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-01 | 0 |  |  |  | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-01 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089664 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-01 | 0 |  |  | 2018-02-28 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113845 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-01 | 0 |  |  | 2018-02-28 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140097 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-01 | 0 |  |  | 2018-02-28 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-02 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-02 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-02 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-08-02 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1028-BAPTIST | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-02 | 0 |  |  |  | N |  | 1028-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130575 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-02 | 0 |  |  | 2017-12-08 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133153 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-02 | 0 |  |  | 2017-12-08 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133341 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-02 | 0 |  |  | 2017-12-08 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140403 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-02 | 0 |  |  | 2017-12-08 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-02 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-02 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-03 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-03 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-03 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-03 | 0 |  |  |  | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-04 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-04 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-04 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-04 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-04 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-05 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-05 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-05 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-05 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-08-05 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-05 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-05 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-06 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-06 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-06 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-06 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-08-06 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-08-06 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance |  |  | 2018-08-06 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00096782 | Quarterly Finance Meeting |  |  | Role | CTSU Finance |  |  | 2018-08-07 | 0 |  |  |  | N |  | 00096782 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-07 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-07 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-07 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-07 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-07 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135279 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-07 | 0 |  |  |  | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-08 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-08 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-08 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-08-08 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-08 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-08 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-08-09 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-08-09 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-09 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-09 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-08-09 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-09 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-09 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-09 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Initiate Post-Award Task List |  |  | User | Farmer, Amber |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-10 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-10 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-11 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-11 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-11 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-12 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-12 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-12 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-08-12 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-13 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-13 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance |  |  | 2018-08-13 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-13 | 0 |  |  |  | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115787 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-13 | 0 |  |  | 2018-04-10 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124920 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-13 | 0 |  |  | 2018-04-10 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-14 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-14 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-14 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-14 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-14 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-14 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108610 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-14 | 0 |  |  | 2018-05-14 | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140577 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-14 | 0 |  |  | 2018-05-14 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-15 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-15 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-15 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00099421 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-18 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00109151 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-18 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119527 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-18 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124998 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-14 | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127612 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-18 | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131329 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-18 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134236 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-15 | 0 |  |  | 2018-05-18 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1063-GEWURZ-SINGER | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-15 | 0 |  |  |  | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1067-MIAN | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-15 | 0 |  |  |  | N |  | 1067-MIAN |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125425 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-15 | 0 |  |  | 2018-02-14 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-16 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-16 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-16 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-08-16 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123115 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-16 | 0 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123661 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-16 | 0 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136152 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-16 | 0 |  |  |  | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-17 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-08-17 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance |  |  | 2018-08-17 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00094631 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-17 | 0 |  |  | 2018-05-18 | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134035 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-17 | 0 |  |  | 2018-05-18 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1070-BELLOLI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-17 | 0 |  |  |  | N |  | 1070-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Calendar Released |  |  | Role | CTSU Finance |  |  | 2018-08-18 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-18 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-18 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00116976 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-18 | 0 |  |  | 2018-05-18 | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120883 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-18 | 0 |  |  | 2018-05-18 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134443 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-18 | 0 |  |  | 2018-05-18 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134444 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-18 | 0 |  |  | 2018-05-18 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 582-SCHIOPU | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-18 | 0 |  |  | 2018-05-18 | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-19 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-19 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-19 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-20 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-20 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-20 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance |  |  | 2018-08-20 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089260 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00098496 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101426 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107954 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113391 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125566 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128157 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136538 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-20 | 0 |  |  | 2018-04-02 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-21 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | PAN Released |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-21 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129652 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-21 | 0 |  |  | 2018-05-21 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131840 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-21 | 0 |  |  | 2018-05-21 | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-21 | 0 |  |  |  | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 974-JOHNSON | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-21 | 0 |  |  |  | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-21 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-21 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-22 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance |  |  | 2018-08-22 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-22 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-22 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-22 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-22 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-23 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-23 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-23 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-23 | 0 |  |  |  | N |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-23 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-23 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 999-ELSE | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-08-23 | 0 |  |  |  | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123861 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-23 | 0 |  |  | 2018-03-05 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135388 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-23 | 0 |  |  | 2018-03-05 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-23 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-24 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00077539 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-24 | 0 |  |  |  | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00105982 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-08-24 | 0 |  |  |  | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-25 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-25 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-25 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125493 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-25 | 0 |  |  | 2018-05-25 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133684 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-08-25 | 0 |  |  | 2018-05-25 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-26 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-26 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-27 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-27 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-08-27 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-27 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-28 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-28 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason |  |  | 2018-08-28 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-08-29 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-08-29 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-08-29 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-08-30 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1084-LEE | PAN Released |  |  | Role | CTSU Finance |  |  | 2018-08-30 | 0 |  |  |  | N |  | 1084-LEE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-08-31 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-09-01 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-09-01 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-09-02 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-09-03 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-03 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-03 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-03 | 0 |  |  |  | N |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-03 | 0 |  |  |  | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-04 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-04 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-09-04 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1108-SCHIOPU | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-04 | 0 |  |  |  | N |  | 1108-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-04 | 0 |  |  |  | N |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-09-05 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-05 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Final Budget |  |  | Role | CTSU Finance |  |  | 2018-09-05 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1113-SHAH | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-05 | 0 |  |  |  | N |  | 1113-SHAH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-09-06 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-09-07 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-09-07 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | PAF routed |  |  | Role | CTSU Finance |  |  | 2018-09-07 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | OnCore Budget Build |  |  | Role | CTSU Finance |  |  | 2018-09-08 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-09-08 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Calendar Released |  |  | User | Oliver, Amy |  |  | 2018-09-09 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-10 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00126010 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-10 | 0 |  |  | 2018-05-18 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1122-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-10 | 0 |  |  |  | N |  | 1122-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-09-11 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132020 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-11 | 0 |  |  | 2018-05-15 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134040 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-11 | 0 |  |  | 2018-05-15 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135268 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-11 | 0 |  |  | 2018-05-15 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122254 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-11 | 0 |  |  |  | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator |  |  | 2018-09-12 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134997 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-12 | 0 |  |  | 2018-06-13 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-09-13 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111185 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-13 | 0 |  |  | 2018-06-19 | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111923 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-13 | 0 |  |  | 2018-06-19 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131837 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-13 | 0 |  |  | 2018-06-19 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132200 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-13 | 0 |  |  | 2018-06-19 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134933 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-13 | 0 |  |  |  | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator |  |  | 2018-09-14 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-14 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1129-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-14 | 0 |  |  |  | N |  | 1129-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134232 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-14 | 0 |  |  | 2018-06-15 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121049 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-15 | 0 |  |  |  | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125022 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-15 | 0 |  |  |  | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131953 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-15 | 0 |  |  |  | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138579 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-15 | 0 |  |  |  | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118570 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-15 | 0 |  |  | 2018-06-15 | N |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125786 | Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-15 | 0 |  |  | 2018-06-15 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00102868 | Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-09-18 | 0 |  |  | 2018-05-15 | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-20 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1140-HIGGINS | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-20 | 0 |  |  |  | N |  | 1140-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance |  |  | 2018-09-21 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | PAN Released |  |  | User | Oliver, Amy |  |  | 2018-09-21 | 0 |  |  |  | N |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089615 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-22 | 0 |  |  |  | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118069 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-22 | 0 |  |  |  | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125794 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-22 | 0 |  |  |  | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128743 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-22 | 0 |  |  |  | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133457 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-22 | 0 |  |  |  | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138433 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-09-22 | 0 |  |  |  | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00095080 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-09 | 0 |  |  |  | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115761 | Next Quarterly Finance Meeting |  |  | Role | CTSU Finance |  |  | 2018-10-10 | 0 |  |  |  | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082007 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-10 | 0 |  |  |  | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114708 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-10 | 0 |  |  |  | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127136 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-11 | 0 |  |  |  | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133286 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-11 | 0 |  |  |  | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133290 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-11 | 0 |  |  |  | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00137399 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-12 | 0 |  |  |  | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142488 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-12 | 0 |  |  |  | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00117806 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-13 | 0 |  |  |  | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122910 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-16 | 0 |  |  |  | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130757 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-17 | 0 |  |  |  | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130803 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-17 | 0 |  |  |  | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132173 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-17 | 0 |  |  |  | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119871 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-17 | 0 |  |  |  | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082896 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-19 | 0 |  |  |  | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00106445 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-19 | 0 |  |  |  | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129716 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-23 | 0 |  |  |  | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128325 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-26 | 0 |  |  |  | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066077 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-27 | 0 |  |  |  | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114593 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-27 | 0 |  |  |  | N |  | 00114593 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129851 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-10-27 | 0 |  |  |  | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132700 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-10-30 | 0 |  |  |  | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089664 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-01 | 0 |  |  |  | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113845 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-01 | 0 |  |  |  | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140097 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-01 | 0 |  |  |  | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130575 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-02 | 0 |  |  |  | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133153 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-02 | 0 |  |  |  | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133341 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-02 | 0 |  |  |  | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140403 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-02 | 0 |  |  |  | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00096782 | Next Quarterly Finance Meeting |  |  | Role | CTSU Finance |  |  | 2018-11-07 | 0 |  |  |  | N |  | 00096782 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135279 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-07 | 0 |  |  |  | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115787 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-13 | 0 |  |  |  | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124920 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-13 | 0 |  |  |  | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108610 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-14 | 0 |  |  |  | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140577 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-14 | 0 |  |  |  | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00099421 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00109151 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119527 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124998 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127612 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131329 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134236 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125425 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-15 | 0 |  |  |  | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123115 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-16 | 0 |  |  |  | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123661 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-16 | 0 |  |  |  | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136152 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-16 | 0 |  |  |  | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00094631 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-17 | 0 |  |  |  | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134035 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-17 | 0 |  |  |  | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00116976 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-18 | 0 |  |  |  | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120883 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-18 | 0 |  |  |  | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134443 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-18 | 0 |  |  |  | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134444 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-18 | 0 |  |  |  | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 582-SCHIOPU | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-18 | 0 |  |  |  | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089260 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00098496 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101426 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107954 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113391 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125566 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128157 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136538 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-20 | 0 |  |  |  | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129652 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-21 | 0 |  |  |  | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131840 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-21 | 0 |  |  |  | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123861 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-23 | 0 |  |  |  | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135388 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-11-23 | 0 |  |  |  | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125493 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-25 | 0 |  |  |  | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133684 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-11-25 | 0 |  |  |  | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00126010 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-10 | 0 |  |  |  | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132020 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-11 | 0 |  |  |  | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134040 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-11 | 0 |  |  |  | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135268 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-11 | 0 |  |  |  | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134997 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-12 | 0 |  |  |  | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111185 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-13 | 0 |  |  |  | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111923 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-13 | 0 |  |  |  | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131837 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-13 | 0 |  |  |  | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132200 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-13 | 0 |  |  |  | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134232 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-12-14 | 0 |  |  |  | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118570 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-12-15 | 0 |  |  |  | N |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125786 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason |  |  | 2018-12-15 | 0 |  |  |  | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00102868 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber |  |  | 2018-12-18 | 0 |  |  |  | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | CRAO Approval Issue & Documented |  |  | Role | CRAO | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Complete SVS & Pricing List ( Built & Coded ) |  |  | Role | CRAO | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Make Updates |  |  | Role | CRAO | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Request Care Designations |  |  | Role | CRAO | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Footnote Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | Role | CRAO | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Request Care Designations |  |  | Role | CRAO | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Request Care Designations |  |  | Role | CRAO | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | Role | CRAO | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Update RSH Source in MBECT |  |  | Role | CRAO | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Footnote Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 503-JAYASUNDERA | Update RSH Source in MBECT |  |  | Role | CRAO | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Feedback from CRAO to CTSU |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Initial feedback from CRAO to CTSU |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Make Updates |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Request Care Designations |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Update RSH Source in MBECT |  |  | Role | CRAO | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Footnote Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment INFUSIONS Checklist & Process - 00115761 | Update RSH Source in MBECT |  |  | Role | CRAO | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Footnote Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Other |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Visit Tolerance Edits |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | ** Visits : Addition or Removal of Time Points |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Assign to Analyst |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Request Care Designations |  |  | Role | CRAO | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Feasibility Approval Notice Received |  |  | Role | CRAO | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00125022 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Feasibility Approval Notice Received |  |  | Role | CRAO | [6 empty] | 2017-06-29 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Nimblify Build is Complete & Ready for Import |  |  | Role | CRAO | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00089664 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO | [6 empty] | 2017-04-21 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Nimblify Build is Complete & Ready for Import |  |  | Role | CRAO | [6 empty] | 2017-03-15 | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00105810 | Submit Calendar Build Request and Docs to Nimblify |  |  | Role | CRAO | [6 empty] | 2017-03-03 | N |  | 00105810 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Nimblify Build is Complete & Ready for Import |  |  | Role | CRAO | [6 empty] | 2017-02-09 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Sponsor Reach out |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | UFA Completed |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Confirm interface activated |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00081173 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Confirm interface activated |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-11 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-24 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Notify study team to start validation |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-11 | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [6 empty] | 2018-01-29 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Check-in on validation progress |  |  | Role | CTSU Administrator | [6 empty] | 2018-03-05 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-01-29 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-01-29 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Confirm interface activated |  |  | Role | CTSU Administrator | [6 empty] | 2018-03-06 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [6 empty] | 2018-03-05 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [6 empty] | 2018-01-29 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Notify study team to start validation |  |  | Role | CTSU Administrator | [6 empty] | 2018-01-29 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [6 empty] | 2018-03-05 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [6 empty] | 2018-03-06 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00100501 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Confirm interface activated |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Notify study team to start validation |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Confirm interface activated |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-11 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Notify study team to start validation |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-11 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Confirm interface activated |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-14 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-11 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Notify study team to start validation |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-08 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-11 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-14 | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Notify study team to start validation |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-04 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Check-in on validation progress |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-20 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-20 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-20 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Confirm interface activated |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-20 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Notify study team to start validation |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-16 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [6 empty] | 2018-04-20 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Confirm interface activated |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Notify study team to start validation |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | CTSU Admin validation completed |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-23 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Check-in on validation progress |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Confirm budget build completed (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-23 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Confirm calendar released (see details in Migration: Financials) |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-23 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Confirm interface activated |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Confirm study team validation complete |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Go-live readiness confirmed (accounts provisioned, calendar and budget completed, scripted migration successful) |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Notify study team to start validation |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Notify support team to activate interface |  |  | Role | CTSU Administrator | [6 empty] | 2018-05-23 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Send "One week to go-live" reminder to study teams |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Send welcome email to study teams |  |  | Role | CTSU Administrator | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129716 | FDA Approval |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Request Research Pharmacy Budget |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Sponsor Reach out |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | UFA Completed |  |  | Role | CTSU Administrator | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Feasibility approved/CRAO Notified |  |  | Role | CTSU Administrator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Feasibility w/Documents received |  |  | Role | CTSU Administrator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Open to Accrual |  |  | Role | CTSU Administrator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | PI Signoff in OnCore |  |  | Role | CTSU Administrator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | IRB Amendment Approved in eRRM |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-12 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | IRB Amendment Submitted in eRRM |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | PI Signoff in OnCore |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Intake Form Completed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00137953 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2016-04-21 | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Intake Form Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1019-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1033-CAGNOLI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1048-KNIGHT | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1048-KNIGHT |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1072-KHAN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1074-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1074-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1098-BELL | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1098-BELL |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1104-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1110-ASKARI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149248 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1141-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1141-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 410-PAULUS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 410-PAULUS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 432-JAYASUNDERA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 432-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 461-CHOPRA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 461-CHOPRA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 465-LIPSON | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 521-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 536-NAGARAJA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 537-YUNG | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 537-YUNG |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-20 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 582-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 610-WHITE | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 615-ASKARI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 626-SCHIMPF | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 626-SCHIMPF |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 684-CHEN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 684-CHEN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 692-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 702-BESIRLI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 717-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 717-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 756-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 756-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 784-LUGOGO | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 820-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 831-RUBENSTEIN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 831-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 841-ORAL | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00145089 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 869-MMEJE | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 869-MMEJE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 872-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 872-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 878-MCCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 878-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Intake Form Completed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-26 | N |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 916-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 979-MCCUNE | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 989-BELLOLI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 989-BELLOLI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 998-JIA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Intake Form Completed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-08 | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 00148187 | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-11 | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1004-HIGGINS | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-18 | N |  | 1004-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-03 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-03 | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1011-POP-BUSUI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-07 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1019-LUGOGO | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1019-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1024-BAPTIST | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1027-JAYASUNDERA | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [6 empty] | 2018-07-02 | N |  | 1027-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-11 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-11 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-11 | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1033-CAGNOLI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-25 | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1063-GEWURZ-SINGER | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 1063-GEWURZ-SINGER |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-29 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-29 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-29 | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1072-KHAN | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-22 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-22 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-22 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-22 | N |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 1104-CONJEEVARAM | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149233 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-02 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 12-HIGGINS | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-08 | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-16 | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 313-CONJEEVARAM | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 313-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-08-02 | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-12 | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 370-LOK | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 370-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-08-02 | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-12 | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 371-LOK | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-05 | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 458-HERMAN | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 458-HERMAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 462-AUCHUS | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00148920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-03 | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-04 | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 473-MOROI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 482-LUGOGO | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-25 | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 503-JAYASUNDERA | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-09 | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-09 | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 518-HIGGINS | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 518-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-04 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-04 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 521-CONJEEVARAM | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-11 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-12 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-12 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-12 | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 536-NAGARAJA | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-17 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-17 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-12 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-12 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 560-BAPTIST | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-06 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-07 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-28 | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 595-BAPTIST | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-14 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-14 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-14 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-22 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-22 | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 596-BELL | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-09 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-03 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-03 | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 609-SHAH | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-17 | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-16 | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-16 | N |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 610-WHITE | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 610-WHITE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-20 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-20 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-20 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-27 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 615-ASKARI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-19 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-20 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-20 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 616-YEVZLIN | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-06 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 625-DEMIRCI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-07 | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 638-LUGOGO | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 638-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-08 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-09 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-09 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-26 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 641-SCHIOPU | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-30 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-22 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-22 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 689-LUGOGO | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-22 | N |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-12 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-12 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-17 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-27 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-27 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 696-LOK | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-26 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-26 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-26 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-27 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 697-LOK | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-12 | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 702-BESIRLI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-01 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-14 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-14 | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 730-SCHIOPU | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-02 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-02 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 792-NELSON | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-02 | N |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 818-MOROI | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-29 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-29 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-29 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-18 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-18 | N |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 830-CONJEEVARAM | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00146064 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-12 | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 833-SCHIOPU | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 833-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-04 | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-04 | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 834-LUGOGO | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 834-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-28 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | Sponsor Budget |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | Sponsor Contract |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 842-ORAL | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-20 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-20 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-20 | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 974-JOHNSON | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-11 | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-23 | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-23 | N |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 979-MCCUNE | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 979-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | Informed Consent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-30 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-21 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-21 | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 998-JIA | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | Informed Consent |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | Initial contact with sponsor |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | Investigational Drug Brochure / Investigator's Brochure |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | Protocol (and any approved Amendments) |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-29 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | Sponsor Budget |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-20 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | Sponsor Contract |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-20 | N |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Core Sponsor Documents for Study Feasibility & Start Up - General - 999-ELSE | U-M Planning Questionnaire |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-30 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-23 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-04-07 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-12 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-10 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-01 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-11 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-22 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-10 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-13 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-10 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-10 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-10 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125566 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-28 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-22 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-09 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-06 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-07 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-14 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-08 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-23 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-19 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-08-09 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-15 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-06 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-14 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-13 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-08 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-07 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-13 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-23 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-13 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-26 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Contract Executed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129820 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-05-31 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-06-06 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-06 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-07-20 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-08 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-27 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-31 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-26 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-19 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-19 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-19 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | IRB Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-08-24 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-28 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-05 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-08 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-08 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-08 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-08 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-29 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-09-05 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-30 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-03 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-31 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-27 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-05 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-10 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-20 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-03 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-15 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-03 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-18 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-22 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-07 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-19 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-03 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-12 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-23 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | FDA Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-20 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-19 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-19 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-02-23 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-10 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-13 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-03 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Contract Executed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | IRB Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | MiChart Verifications |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Other Personnel Notified |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Study Files Established |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-19 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-26 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-17 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-15 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | IRB Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-19 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-02 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | IRB Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Contract Executed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-19 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-19 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-19 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-19 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-19 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Contract Executed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | IRB Approval |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | MiChart Verifications |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Other Personnel Notified |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Study Files Established |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Adequate Equipment and Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Contract Executed |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | FDA Approval |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | IRB Approval |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Investigational Drug/Device Supplies Available |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | MiChart Verifications |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Other Personnel Notified |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Project Award Notice (PAN) Received |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Provisions for Support and Services Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Sponsor/Organizing Group Approval Granted for Initiation of Study |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Study Files Established |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Study Team Roles/Responsibilities Finalized |  |  | Role | CTSU Coordinator | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-18 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Intake Form Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-07 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-14 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-29 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-11-27 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 278-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Intake Form Completed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-06 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2018-01-13 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-10-18 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [6 empty] | 2017-12-09 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Planning Meeting Request Sent |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Sponsor Reach out |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | UFA Completed |  |  | Role | CTSU Coordinator | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | IRB Application Submitted |  |  | Role | CTSU Coordinator | [7 empty] | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00096782 | Comments |  |  | Role | CTSU Finance | [7 empty] | N |  | 00096782 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135919 | Comments |  |  | Role | CTSU Finance | [7 empty] | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135919 | Next Quarterly Finance Meeting |  |  | Role | CTSU Finance | [7 empty] | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135919 | Quarterly Finance Meeting |  |  | Role | CTSU Finance | [7 empty] | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Final Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PAF routed |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 371-LOK | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 371-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Final Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | PAF routed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | PAN Released |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00097353 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00114919 | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Final Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | PAF routed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | PAN Released |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 00148187 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 00148187 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1054-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 439-KHANNA | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 479-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 479-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 486-COMER | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 486-COMER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Final Budget |  |  | Role | CTSU Finance | [6 empty] | 2017-10-27 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Internal Budget Finished |  |  | Role | CTSU Finance | [6 empty] | 2017-10-27 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | PAF routed |  |  | Role | CTSU Finance | [6 empty] | 2017-10-27 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | PI approved Budget |  |  | Role | CTSU Finance | [6 empty] | 2017-10-27 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 625-DEMIRCI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 708-BESIRLI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 880-TAPPER | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 894-SUN | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 894-SUN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Final Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | PAF routed |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | PAN Released |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - ADMIN-ACD | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | ADMIN-ACD |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00107954 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00111923 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00118570 | Initiate Updates |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00118570 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00118570 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00118570 | Review & Release Calendar |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125786 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127537 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129851 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133286 | Initiate Updates |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133286 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133286 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133286 | Review & Release Calendar |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133684 | Initiate Updates |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133684 | Notify Niyati Updated Calendar was Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133684 | Questions |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133684 | Review & Release Calendar |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00104229 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | AME Calendaring Process Initiated |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | CTSU finance respond |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Calendar and budget have been released ready for RPE import |  |  | Role | CTSU Finance | [7 empty] | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Calendar and budget have been released ready for RPE import |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Confirm Calendar is correct and ready for financials |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Initial feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | CTSU finance respond |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Calendar and budget have been released ready for RPE import |  |  | Role | CTSU Finance | [7 empty] | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Calendar and budget have been released ready for RPE import |  |  | Role | CTSU Finance | [7 empty] | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Initial feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | CTSU finance respond |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Calendar and budget have been released ready for RPE import |  |  | Role | CTSU Finance | [7 empty] | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Initial Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Feedback from CTSU to CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Acknowledge |  |  | Role | CTSU Finance | [7 empty] | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Brain CT/MRI - 00126010 2 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00098496 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00101426 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00107927 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00111185 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00114708 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123117 | Submit Update Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00123661 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00126010 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | Submit Update Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00129427 | Submit Update Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130575 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | Submit Update Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133341 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00133457 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134884 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | Acknowledge |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | Submit Update Request(s) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 2 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136916 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136917 2 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136918 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 337-MIAN | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 346-BAPTIST | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 641-SCHIOPU | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Request(s) to Add Unscheduled Procedure(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Acknowledge |  |  | Role | CTSU Finance | [6 empty] | 2017-05-02 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00082007 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V1 - 00115761 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Budget Build Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance | [6 empty] | 2017-11-29 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Calendar Released |  |  | Role | CTSU Finance | [6 empty] | 2017-12-01 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Department Reach out |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [6 empty] | 2017-11-27 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00077539 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00081173 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00082896 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089615 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Calendar Released |  |  | Role | CTSU Finance | [6 empty] | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [6 empty] | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | SAPOC Changed |  |  | Role | CTSU Finance | [6 empty] | 2017-12-01 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00089664 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [6 empty] | 2017-12-12 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095080 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Budget Build Completed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-11 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Calendar Released |  |  | Role | CTSU Finance | [6 empty] | 2018-03-11 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-11 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | SAPOC Changed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-11 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00098496 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-06 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-06 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Budget Build Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance | [6 empty] | 2017-11-08 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Calendar Released |  |  | Role | CTSU Finance | [6 empty] | 2017-11-10 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Department Reach out |  |  | Role | CTSU Finance | [6 empty] | 2017-10-24 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [6 empty] | 2017-11-06 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [6 empty] | 2017-11-06 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Sponsor contact info received |  |  | Role | CTSU Finance | [6 empty] | 2017-11-06 | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100452 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00100501 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00103411 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00104229 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Budget Build Completed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Calendar Released |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Department Reach out |  |  | Role | CTSU Finance | [6 empty] | 2017-10-25 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Migration Meeting held |  |  | Role | CTSU Finance | [6 empty] | 2017-11-13 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [6 empty] | 2017-11-13 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Sponsor contact info received |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00105982 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00106445 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00109151 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00113845 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00114708 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00115787 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00116976 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00117806 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00118069 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119871 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120726 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-22 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-22 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Budget Build Completed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-28 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance | [6 empty] | 2018-03-28 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Calendar Released |  |  | Role | CTSU Finance | [6 empty] | 2018-04-15 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [6 empty] | 2018-03-30 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [6 empty] | 2018-03-26 | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121481 2 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00125493 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00127612 | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Access to all PAFs confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Access to budget/contract confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Access to shadow system documents confirmed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | CRAO-CTSU Finance Calendar Meeting |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Department Reach out |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Finance Validation Checklist Completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Last Payment Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Last Visits Reconciled by Department |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Migration Meeting held |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Migration Meeting scheduled |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Pending/Outstanding Items Received from Department (attach as doc) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Received completed calendar from CRAO |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | SAPOC Changed |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Sponsor contact info received |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 852-ESWARAN | Transition Checklist signed by department |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00110175 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-10-23 | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General - 00122910 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-10-16 | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00066148 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-05-10 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00077539 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082896 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00088900 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-22 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089664 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-11-27 | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095152 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-02-12 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-02-19 | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00102868 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00103411 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00103411 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104229 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-08 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00104608 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00104608 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00105982 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-11-22 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00106445 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00108610 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-02-05 | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-01 | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-22 | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-04-02 | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115787 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-04 | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00117806 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-08 | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-22 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-02-05 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120029 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00120029 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120726 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2017-12-22 | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-01-29 | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121049 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121107 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00121107 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123115 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123117 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00123661 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124133 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00124998 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Start financials migration (track details in Migration: Financials) |  |  | Role | CTSU Finance | [6 empty] | 2018-03-26 | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00108880 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-31 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-03-24 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125022 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-03-09 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125425 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-04-18 | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125786 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-05-12 | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00125794 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-05-05 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00126010 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-07-19 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127136 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-12-12 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00127537 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-05-05 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128157 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-06-07 | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128531 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-10-20 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00128743 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-10-20 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129427 | Budget Finalized |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00129851 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-04-05 | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130575 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-12-13 | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00130757 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-08-01 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131329 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-10-20 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131837 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-06-12 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00131953 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-11-19 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132020 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-11-01 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132200 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-08-18 | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00132700 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-11-08 | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133153 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-10-20 | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00133286 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-12-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134035 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-10-20 | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134040 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134236 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-10-10 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00134884 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-04-10 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00135388 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-03 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00136538 | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-12-13 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 110-SCHIOPU | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-12-12 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 155-ORAL | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-03-09 | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 179-LUGOGO | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-18 | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 190-SCHIOPU | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-11-19 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-19 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 251-COMER | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-10 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 278-CONJEEVARAM | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-11-09 | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 282-POP-BUSUI | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-11-09 | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 325-AUCHUS | Budget Finalized |  |  | Role | CTSU Finance | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 332-BELLOLI | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-19 | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 336-KHANNA | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-01-19 | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 341-STOFFEL | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-02-03 | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 346-BAPTIST | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-05-16 | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 359-SMITH | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2017-12-15 | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 403-HIGGINS | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-03-09 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 404-HIGGINS | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-03-09 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 428-LAW | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-03-28 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 453-VLISIDES | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-04-10 | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 521-CONJEEVARAM | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-06-01 | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 560-BAPTIST | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-05-24 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 615-ASKARI | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-02-02 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 623-TAPPER | Budget Finalized |  |  | Role | CTSU Finance | [7 empty] | N |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 842-ORAL | Budget Finalized |  |  | Role | CTSU Finance | [6 empty] | 2018-06-15 | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00123861 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124712 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124712 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125425 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125566 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125786 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125794 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126215 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [6 empty] | 2017-09-21 | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127136 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127356 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [6 empty] | 2017-08-10 | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127537 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128157 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128531 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128743 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129652 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129851 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130575 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 10-JAYASUNDERA | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 10-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 111-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 111-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 131-LUGOGO | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 131-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 142-FLAHERTY | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 142-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 188-RUBENSTEIN | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 188-RUBENSTEIN |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 2-MARSH | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 2-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 201-MCCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 201-MCCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 242-AS-SANIE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 242-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 246-AS-SANIE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 246-AS-SANIE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 255-LOK | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 255-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 261-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 261-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 263-DELMONTE | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 30-FLAHERTY | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 30-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 33-FLAHERTY | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 34-MARSH | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 34-MARSH |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Final Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PAF routed |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [6 empty] | 2017-12-13 | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [6 empty] | 2018-03-20 | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 71-RICE | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 77-CONJEEVARAM | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 77-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 81-HIGGINS | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 81-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 86-AUCHUS | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [6 empty] | 2017-09-21 | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 87-ORAL | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 9-JAYASUNDERA | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 9-JAYASUNDERA |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 91-ELSE | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 91-ELSE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 92-AUCHUS | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | 92-AUCHUS |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 96-BESIRLI | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Billing Calendar Received |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Budget Negotiations |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Calendar Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Care Designations completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Created CTRF & "Notify ORSP" |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Final Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Internal Budget Finished |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | OnCore Budget Build |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | PAF routed |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | PAN Released |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | PI approved Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Planning Meeting Completed |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-3 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | FONTANA-3 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Request MCRU Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Request Research Pharmacy Budget |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SCHIOPU-1 | Initiate Post-Award Task List |  |  | Role | CTSU Finance | [7 empty] | N |  | SCHIOPU-1 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Footnote Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Other Request(s) |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Request for Clarification |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Request to Rename for Clarity |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Structural Edits |  |  | Role | CTSU Finance | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Billing Calendar Received |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Care Designations completed |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 0014292 | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 547-TAPPER | Request Research Pharmacy Budget |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 547-TAPPER |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 643-LUGOGO | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 643-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | Created CTRF & "Notify ORSP" |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | PAF routed |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 888-TURGEON | PAN Released |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Feedback from CTSU to CRAO |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Initial Feedback from CTSU to CRAO |  |  | User | De Filippo, Julie | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Amendment Requires Budget Revisions |  |  | User | Farmer, Amber | [7 empty] | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Amendment Requires Contract Amendment |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Cloned Current PAF |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Contract Executed |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Create new OnCore Budget Version |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | PAF Complete |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | PI Signed PAF |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Ame00077540 - 00129716 | Sent Budget to Sponsor for Revisions |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | IRB Amendment Submitted in eRRM |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Study Team Approves OnCore Billing Grid |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Create new OnCore Budget Version |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Create new OnCore Budget Version |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | IRB Amendment Approved in eRRM |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Study Team Contacted to Approve Amendment Change |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | CRAO Amendment Task List Completed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066148 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066148 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber | [7 empty] | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066148 | Quarterly Finance Meeting |  |  | User | Farmer, Amber | [6 empty] | 2018-04-10 | N |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082007 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00082896 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00082896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00088900 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00088900 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber | [7 empty] | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00088900 | Quarterly Finance Meeting |  |  | User | Farmer, Amber | [6 empty] | 2018-04-10 | N |  | 00088900 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00094631 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00099421 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00102868 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00106445 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00106445 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108610 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00108610 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00109151 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111185 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00111185 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00111923 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115761 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00116976 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00117806 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00117806 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119527 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120883 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121049 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121481 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121481 | Next Quarterly Finance Meeting |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00121481 | Quarterly Finance Meeting |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123115 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123661 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00123661 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124998 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00124998 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125022 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125493 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00126010 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127136 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127612 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128325 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129652 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129716 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130757 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130803 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131329 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131837 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131840 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00131953 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132020 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132173 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132200 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00132700 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00132700 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133286 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133290 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133684 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134035 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134040 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134236 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134443 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134444 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134933 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134997 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135268 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136152 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00137399 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138579 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140577 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142488 | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 582-SCHIOPU | Comments |  |  | User | Farmer, Amber | [7 empty] | N |  | 582-SCHIOPU |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00082356 | Questions |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00089260 | Questions |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | CTSU finance respond |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | Calendar and budget have been released ready for RPE import |  |  | User | Farmer, Amber | [7 empty] | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Feedback from CTSU to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Calendar and budget have been released ready for RPE import |  |  | User | Farmer, Amber | [7 empty] | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | CTSU finance respond |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Calendar and budget have been released ready for RPE import |  |  | User | Farmer, Amber | [7 empty] | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Feedback from CTSU to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | CTSU finance respond |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Feedback from CTSU to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Initial feedback from CTSU to CRAO |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00066148 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00066148 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00134444 | ** Other Request(s) |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Access to budget/contract confirmed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | CRAO-CTSU Finance Calendar Meeting |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Finance Validation Checklist Completed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Last Payment Reconciled by Department |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Last Visits Reconciled by Department |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Migration Meeting held |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Received completed calendar from CRAO |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | SAPOC Changed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Sponsor contact info received |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Transition Checklist signed by department |  |  | User | Farmer, Amber | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00119527 | SAPOC Changed |  |  | User | Farmer, Amber | [6 empty] | 2018-02-09 | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Access to budget/contract confirmed |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00120883 | Access to shadow system documents confirmed |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | SAPOC Changed |  |  | User | Farmer, Amber | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00124133 | Pending/Outstanding Items Received from Department (attach as doc) |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | OnCore Budget Build |  |  | User | Farmer, Amber | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 147-SCHIOPU | Initiate Post-Award Task List |  |  | User | Farmer, Amber | [6 empty] | 2017-11-01 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Initiate Post-Award Task List |  |  | User | Farmer, Amber | [7 empty] | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Initiate Post-Award Task List |  |  | User | Farmer, Amber | [6 empty] | 2017-12-13 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00110175 | Nimblify Build is Complete & Ready for Import |  |  | User | Greene, Paula | [7 empty] | N |  | 00110175 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 326-HIGGINS | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 327-HIGGINS | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 332-BELLOLI | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 336-KHANNA | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 337-MIAN | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 338-MIAN | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 341-STOFFEL | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 346-BAPTIST | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00137399 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1011-POP-BUSUI | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Billing Calendar Received |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Care Designations completed |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | PI approved Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1015-KHANNA | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 1015-KHANNA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Billing Calendar Received |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Care Designations completed |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Planning Meeting Completed |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1016-WOODWARD | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 1016-WOODWARD |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 1024-BAPTIST | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 325-AUCHUS | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 403-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 404-HIGGINS | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 463-NAGARAJA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 560-BAPTIST | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 595-BAPTIST | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 596-BELL | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 609-SHAH | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 616-YEVZLIN | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 818-MOROI | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Billing Calendar Received |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Care Designations completed |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Final Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 839-NAGARAJA | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 839-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 842-ORAL | Planning Meeting Completed |  |  | User | Henry, Robin | [7 empty] | Y |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Billing Calendar Received |  |  | User | Henry, Robin | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Care Designations completed |  |  | User | Henry, Robin | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 995-NAGARAJA | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 995-NAGARAJA |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | AME Calendaring Process Initiated |  |  | User | Henry, Robin | [6 empty] | 2017-11-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | AME Calendaring Process Initiated |  |  | User | Henry, Robin | [6 empty] | 2017-11-02 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | AME Calendaring Process Initiated |  |  | User | Henry, Robin | [6 empty] | 2017-11-02 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Henry, Robin | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00128173 | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Final Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | PAF routed |  |  | User | Henry, Robin | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 11-HIGGINS | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 110-SCHIOPU | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 170-SCHIOPU | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 190-SCHIOPU | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 203-ELSE | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-HIGGINS | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 205-KHANNA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Budget Negotiations |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | PAN Released |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Budget Negotiations |  |  | User | Henry, Robin | [6 empty] | 2017-03-28 | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Created CTRF & "Notify ORSP" |  |  | User | Henry, Robin | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - FONTANA-1 | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Request MCRU Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - SLS-III | Request Research Pharmacy Budget |  |  | User | Henry, Robin | [7 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Footnote Edits |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Other |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Visit Tolerance Edits |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00125566 | ** Visits : Addition or Removal of Time Points |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 235-SUGAR | Request Care Designations |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Other |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Visit Tolerance Edits |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | ** Visits : Addition or Removal of Time Points |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 251-COMER | Update RSH Source in MBECT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Feasibility Approval Notice Received 04/17/17 |  |  | User | Hess, Aaron | [6 empty] | 2017-04-17 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | Complete MCA / QCT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify |  |  | User | Hess, Aaron | [6 empty] | 2017-06-30 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Complete MCA / QCT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-KHANNA | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 332-BELLOLI | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron | [7 empty] | N |  | 00136152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 625-DEMIRCI | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron | [6 empty] | 2018-03-29 | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron | [6 empty] | 2018-04-19 | N |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 696-LOK | Complete MCA / QCT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00144015 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 697-LOK | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron | [6 empty] | 2018-04-19 | N |  | 00144716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron | [7 empty] | N |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 708-BESIRLI | Complete MCA / QCT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00113212 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 71-RICE | CRAO Approval Issue & Documented |  |  | User | Hess, Aaron | [6 empty] | 2018-01-29 | N |  | 00134857 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | CRAO Approval Issued & Documented |  |  | User | Hess, Aaron | [7 empty] | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hess, Aaron | [7 empty] | N |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1072-KHAN | Complete MCA / QCT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 1072-KHAN |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Attach Build Notes ( as Protocol Doc ) |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | CRAO Approval Issued & Documented |  |  | User | Hess, Aaron | [7 empty] | N |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Feedback from CRAO to CTSU |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 12-HIGGINS | Initial Feedback from CRAO to CTSU |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00144406 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | CRAO Approval Issued & Documented |  |  | User | Hess, Aaron | [7 empty] | N |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Feedback from CRAO to CTSU |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 998-JIA | Initial Feedback from CRAO to CTSU |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00147422 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 999-ELSE | Complete MCA / QCT |  |  | User | Hess, Aaron | [7 empty] | Y |  | 00149238 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | Assign to Analyst |  |  | User | Hess, Aaron | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | Make Update(s) |  |  | User | Hess, Aaron | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00136538 | Re-Complete Calendar |  |  | User | Hess, Aaron | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Footnote Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Other |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Request Care Designations |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Footnote Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Other |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Complete Calendar and Document Approval |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Request Care Designations |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00134443 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136916 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Other |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 784-LUGOGO | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00143569 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Other |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Initial feedback from CRAO to CTSU |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Footnote Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Other |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Complete Calendar ( ie. Ready for Financials ) |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Initial feedback from CRAO to CTSU |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Request Care Designations |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00124133 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00124133 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Other |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00125786 | Send questions to CTSU finance |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Visit Tolerance Edits |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | ** Visits : Addition or Removal of Time Points |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00129716 | Update RSH Source in MBECT |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [6 empty] | 2017-12-07 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 205-HIGGINS | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 351-HIGGINS | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 465-LIPSON | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00137724 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 530-STOFFEL | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 689-LUGOGO | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00142303 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 730-SCHIOPU | CRAO Approval Issue & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00147950 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 792-NELSON | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00144558 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | CRAO Approval Issued & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 00097353 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00097353 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | CRAO Approval Issued & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1011-POP-BUSUI | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hodges, Lynda | [7 empty] | N |  | 1011-POP-BUSUI |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | CRAO Approval Issued & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Initial Feedback from CRAO to CTSU |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1033-CAGNOLI | Make Updates |  |  | User | Hodges, Lynda | [7 empty] | Y |  | 00148048 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | CRAO Approval Issued & Documented |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 974-JOHNSON | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Hodges, Lynda | [7 empty] | N |  | 00149131 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Initiate CRAO Amendment Task List |  |  | User | Huffman, Kate | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00123861 | MiChart Verifications |  |  | User | Huffman, Kate | [6 empty] | 2017-05-18 | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 00124920 | FDA Approval |  |  | User | Huffman, Kate | [7 empty] | Y |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Other Request(s) |  |  | User | LaVasseur, Kristen | [6 empty] | 2017-04-12 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Assign to Analyst |  |  | User | LaVasseur, Kristen | [6 empty] | 2017-04-12 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Make Update(s) |  |  | User | LaVasseur, Kristen | [6 empty] | 2017-04-12 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Submit Update Request(s) |  |  | User | LaVasseur, Kristen | [6 empty] | 2017-04-12 | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | OnCore Billing Calendar Completed |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Revised Billing Grid Sent to Study Team |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Footnote Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Other |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Visit Tolerance Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00108880 | ** Visits : Addition or Removal of Time Points |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Footnote Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Other |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Visit Tolerance Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 155-ORAL | ** Visits : Addition or Removal of Time Points |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Other |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | ** Visit Tolerance Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Send questions to CTSU finance |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Footnote Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Other |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | ** Visit Tolerance Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Initial feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Send questions to CTSU finance |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00131837 | Update RSH Source in MBECT |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Footnote Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Other |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Visit Tolerance Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | ** Visits : Addition or Removal of Time Points |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-06-04 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Initial feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Footnote Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Other |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Visit Tolerance Edits |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process- Rescreen visits - 00099421 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00108880 | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-09-18 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00131837 | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-08-15 | N |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 110-SCHIOPU | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-09-08 | N |  | 00134444 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 140-CHUNG | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-08-03 | N |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 147-SCHIOPU | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-02-23 | N |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 203-ELSE | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00132173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 263-DELMONTE | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00137580 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 336-KHANNA | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133684 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-09-22 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 350-HIGGINS | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 428-LAW | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-11-16 | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 463-NAGARAJA | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00141927 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-07-02 | N |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 482-LUGOGO | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00146265 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-02-26 | N |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 560-BAPTIST | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00142488 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Attach Build Notes ( as Protocol Doc ) |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 602-MENEES | Nimblify Build is Complete & Ready for Import |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 609-SHAH | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [7 empty] | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 615-ASKARI | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-01-17 | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 641-SCHIOPU | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-05-23 | N |  | 00142947 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | CRAO Approval Issue & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2017-08-09 | N |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 94-AUCHUS | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | CRAO Approval Issued & Documented |  |  | User | Munasinghe, Sadeepa | [6 empty] | 2018-06-21 | N |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Initial Feedback from CRAO to CTSU |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 888-TURGEON | Make Updates |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00141420 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | Assign to Analyst |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127136 2 | Re-Complete Calendar |  |  | User | Munasinghe, Sadeepa | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | OnCore Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | CRAO Amendment Task List Completed |  |  | User | Oliver, Amy | [6 empty] | 2018-04-23 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | OnCore Calendar Released |  |  | User | Oliver, Amy | [6 empty] | 2018-04-23 | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | OnCore Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | OnCore Calendar Released |  |  | User | Oliver, Amy | [6 empty] | 2018-04-23 | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | OnCore Calendar Released |  |  | User | Oliver, Amy | [6 empty] | 2018-06-22 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | CRAO Amendment Task List Completed |  |  | User | Oliver, Amy | [6 empty] | 2018-06-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | OnCore Calendar Released |  |  | User | Oliver, Amy | [6 empty] | 2018-06-22 | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | OnCore Calendar Released |  |  | User | Oliver, Amy | [6 empty] | 2018-04-23 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | OnCore Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | PAN Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 350-HIGGINS | Request MCRU Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 140-CHUNG | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00133613 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Budget Negotiations |  |  | User | Oliver, Amy | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Planning Meeting Completed |  |  | User | Oliver, Amy | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 420-HAN | Request Research Pharmacy Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 420-HAN |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Budget Negotiations |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Final Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Internal Budget Finished |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | PAF routed |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | PI approved Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 530-STOFFEL | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00134933 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | PAN Released |  |  | User | Oliver, Amy | [6 empty] | 2018-02-07 | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Billing Calendar Received |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Budget Negotiations |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Care Designations completed |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 602-MENEES | Request Research Pharmacy Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139784 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 623-TAPPER | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00141457 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 721-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 721-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 722-HIGGINS | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 722-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00101092 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113391 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00113496 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119175 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00119399 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123231 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00123861 | Questions |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128157 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132020 | Notify Niyati Updated Calendar was Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00132020 | Review & Release Calendar |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119399 2 | Acknowledge |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | Calendar and budget have been released ready for RPE import |  |  | User | Oliver, Amy | [7 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119871 | Calendar and budget have been released ready for RPE import |  |  | User | Oliver, Amy | [7 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00123115 | Calendar and budget have been released ready for RPE import |  |  | User | Oliver, Amy | [7 empty] | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00133286 | Calendar and budget have been released ready for RPE import |  |  | User | Oliver, Amy | [7 empty] | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Calendar and budget have been released ready for RPE import |  |  | User | Oliver, Amy | [7 empty] | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00094631 | Transition Checklist signed by department |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00095152 | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 00095152 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00099421 | Transition Checklist signed by department |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00121049 | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: Financials V2 - 00123117 | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 00123117 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00122254 | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-09-21 | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00124920 | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-08-01 | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00125022 | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-12-14 | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00127505 | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-09-21 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | PAF routed |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00129427 | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00130793 | PAN Released |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Budget Negotiations |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Final Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | Internal Budget Finished |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 155-ORAL | PI approved Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [7 empty] | N |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Request MCRU Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 180-HOFF | Request Research Pharmacy Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00129450 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 211-HIGGINS | PAF routed |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 23-GUPTA | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-10-30 | N |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | Calendar Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | PAN Released |  |  | User | Oliver, Amy | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-11-01 | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 56-RAO | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2017-12-19 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Final Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Internal Budget Finished |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | PI approved Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Planning Meeting Completed |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Request MCRU Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 69-KHANNA | Request Research Pharmacy Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 70-LUGOGO | Request MCRU Budget |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 76-KHANNA | Created CTRF & "Notify ORSP" |  |  | User | Oliver, Amy | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - PLT-INF24-001 | Initiate Post-Award Task List |  |  | User | Oliver, Amy | [6 empty] | 2018-01-03 | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Other |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Visit Tolerance Edits |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | ** Visits : Addition or Removal of Time Points |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Feedback from CRAO to CTSU |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Initial feedback from CRAO to CTSU |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Make Updates |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134236 | Update RSH Source in MBECT |  |  | User | Penix, Faith | [7 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 820-CONJEEVARAM | CRAO Approval Issue & Documented |  |  | User | Penix, Faith | [7 empty] | N |  | 830-CONJEEVARAM |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | CRAO Approval Issued & Documented |  |  | User | Penix, Faith | [7 empty] | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Penix, Faith | [7 empty] | N |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Feedback from CRAO to CTSU |  |  | User | Penix, Faith | [7 empty] | Y |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Initial Feedback from CRAO to CTSU |  |  | User | Penix, Faith | [7 empty] | Y |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 916-HIGGINS | Make Updates |  |  | User | Penix, Faith | [7 empty] | Y |  | 00144409 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Ame00077540 Checklist & Process - 00129716 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00066077 | Request Care Designations |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Footnote Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00098496 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101092 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00119175 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Footnote Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00120883 | Request Care Designations |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Request Care Designations |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136918 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00140403 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Import + Michiganize & Export Billing Grid for Determining Care Designations |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Initial feedback from CRAO to CTSU |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Make Updates |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Send questions to CTSU finance |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00119527 | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne | [7 empty] | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Other |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Visit Tolerance Edits |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | ** Visits : Addition or Removal of Time Points |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne | [7 empty] | N |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Send questions to CTSU finance |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00139005 | Update RSH Source in MBECT |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00139005 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 0014292 | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne | [7 empty] | N |  | 00142925 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 56-RAO | Make Updates |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 818-MOROI | CRAO Approval Issue & Documented |  |  | User | Przykucki, Anne | [7 empty] | N |  | 00145612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | CRAO Approval Issued & Documented |  |  | User | Przykucki, Anne | [7 empty] | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1024-BAPTIST | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Przykucki, Anne | [7 empty] | N |  | 1024-BAPTIST |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | CRAO Approval Issued & Documented |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Initial Feedback from CRAO to CTSU |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 880-TAPPER | Make Updates |  |  | User | Przykucki, Anne | [7 empty] | Y |  | 00146686 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00107954 2 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 2 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00113391 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128157 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128173 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00128743 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Footnote Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Other |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Visit Tolerance Edits |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | ** Visits : Addition or Removal of Time Points |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Request Care Designations |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Update RSH Source in MBECT |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00134040 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126010 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127356 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00127356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00127505 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128157 | Make Updates |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128173 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Assign to Analyst |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-18 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Complete MCA / QCT |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-27 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-19 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00128743 | Make Updates |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00129427 2 | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-07-19 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 155-ORAL | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 211-HIGGINS | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00128325 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 235-SUGAR | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Make Updates |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 439-KHANNA | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00146135 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 70-LUGOGO | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00134040 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 842-ORAL | CRAO Approval Issue & Documented |  |  | User | Radenbaugh, Pauline | [7 empty] | N |  | 00144255 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Assign to Analyst |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-21 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-21 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Complete Calendar ( ie. Flag as Ready for Financials ) |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-21 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00100501 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-21 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Acknowledge |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-24 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Assign to Analyst |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-24 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-24 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Complete Calendar ( ie. Flag as Ready for Financials ) |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-24 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Migration - 00125493 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar |  |  | User | Radenbaugh, Pauline | [6 empty] | 2017-04-24 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | Make Update(s) |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | Re-Complete Calendar |  |  | User | Radenbaugh, Pauline | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 309-MOROI | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 309-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 351-HIGGINS | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Billing Calendar Received |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Budget Negotiations |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Care Designations completed |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 435-MOROI | PAF routed |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 435-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Billing Calendar Received |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Budget Negotiations |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Care Designations completed |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Planning Meeting Completed |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 447-RAO | Request Research Pharmacy Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 447-RAO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | Created CTRF & "Notify ORSP" |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | Acknowledge |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Budget Negotiations |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | Internal Budget Finished |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00108880 | PI approved Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Initiate Post-Award Task List |  |  | User | VanderElzen, Liz | [6 empty] | 2017-09-21 | N |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 00126010 | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Calendar Released |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Final Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | PAF routed |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 179-LUGOGO | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 235-SUGAR | Request Research Pharmacy Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 251-COMER | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 282-POP-BUSUI | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Planning Meeting Completed |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 46-HIGGINS | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 49-MARTINEZ | Request MCRU Budget |  |  | User | VanderElzen, Liz | [7 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | Assign to Analyst |  |  | User | Weathers, Sarah | [6 empty] | 2018-05-24 | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | CRAO Approval Issued & Documented |  |  | User | Weathers, Sarah | [7 empty] | N |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build V2 - 1054-LOK | CRAO verifies Study is BC Exempt; OCST can add NB to study title: Date means Yes; NA means No |  |  | User | Weathers, Sarah | [7 empty] | Y |  | 00148088 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [7 empty] | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | OnCore Calendar Released |  |  | User | Yunk, Jason | [7 empty] | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [7 empty] | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | OnCore Calendar Released |  |  | User | Yunk, Jason | [7 empty] | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Amendment Requires Budget Revisions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [7 empty] | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Cloned Current PAF |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Contract Executed |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Create new OnCore Budget Version |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | PAF Complete |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | PI Signed PAF |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Sent Budget to Sponsor for Revisions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00104229 | Study Team Contacted to Approve Amendment Change |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Create new OnCore Budget Version |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [6 empty] | 2018-05-04 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | OnCore Calendar Released |  |  | User | Yunk, Jason | [6 empty] | 2018-05-21 | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Sent Budget to Sponsor for Revisions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [6 empty] | 2018-04-17 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | OnCore Calendar Released |  |  | User | Yunk, Jason | [6 empty] | 2018-05-01 | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [7 empty] | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | OnCore Calendar Released |  |  | User | Yunk, Jason | [7 empty] | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Create new OnCore Budget Version |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | OnCore Calendar Released |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123231 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Create new OnCore Budget Version |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | IRB Amendment Submitted in eRRM |  |  | User | Yunk, Jason | [6 empty] | 2018-03-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | OnCore Billing Calendar Completed |  |  | User | Yunk, Jason | [6 empty] | 2018-03-12 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Revised Billing Grid Sent to Study Team |  |  | User | Yunk, Jason | [6 empty] | 2018-03-16 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Study Team Approves OnCore Billing Grid |  |  | User | Yunk, Jason | [6 empty] | 2018-03-16 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Initiate CRAO Amendment Task List |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Amendment Requires Budget Revisions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Amendment Requires Contract Amendment |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | CRAO Amendment Task List Completed |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Cloned Current PAF |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Contract Executed |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Create new OnCore Budget Version |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | IRB Amendment Approved in eRRM |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | OnCore Calendar Released |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | PAF Complete |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | PI Signed PAF |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Sent Budget to Sponsor for Revisions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - Ame00075196 | Study Team Contacted to Approve Amendment Change |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00066077 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00077539 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00077539 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-05-24 | N |  | 00077539 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00081173 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00081173 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-01-11 | N |  | 00081173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089260 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089615 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089615 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00089664 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00089664 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00095080 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00098496 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100452 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100452 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100452 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00100452 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100501 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00100501 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-01-11 | N |  | 00100501 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101092 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101092 | Date Reconciled |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101092 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101092 | Next Scheduled Reconciliation |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101092 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00101092 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00101426 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00104229 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00104229 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-16 | N |  | 00104229 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00105982 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00105982 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-05-24 | N |  | 00105982 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107927 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107927 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00107927 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00107954 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108880 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108880 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00108880 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-21 | N |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113391 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113496 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113496 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00113845 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114593 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00114593 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00114708 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00115787 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00115787 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118069 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118069 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00118570 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00118570 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119175 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119399 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00119871 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00120726 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00120726 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122254 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00122910 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00122910 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123231 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00123861 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00123861 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00124920 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125425 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125566 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125786 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00125786 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125794 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00125794 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00125794 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127537 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127537 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127537 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-01-11 | N |  | 00127537 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127778 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00127778 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128157 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128173 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128173 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128173 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-21 | N |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128531 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128531 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128743 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00128743 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129427 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129427 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-16 | N |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129820 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129820 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129820 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-21 | N |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00129851 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00129851 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00130575 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133054 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133054 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00133054 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133153 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133341 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133457 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00133457 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134232 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134503 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134503 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-24 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134870 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134870 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00134870 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134884 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134884 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134895 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134895 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134896 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00134896 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135072 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135072 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135072 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135279 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00135388 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136538 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136916 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136916 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00136916 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136917 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136917 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136918 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00136918 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-04-02 | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138433 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00138433 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [6 empty] | 2018-06-22 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140097 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00140097 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140403 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00140403 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140656 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140656 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00140656 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00140656 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00141300 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00141300 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00141300 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00141300 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142051 | Comments |  |  | User | Yunk, Jason | [7 empty] | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142051 | Next Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Post-Award - 00142051 | Quarterly Finance Meeting |  |  | User | Yunk, Jason | [7 empty] | N |  | 00142051 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 331-FLAHERTY | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 331-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 347-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 347-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award - 348-CHEY | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | N |  | 348-CHEY |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 380-LOK | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 380-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 397-HODISH | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 397-HODISH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 428-LAW | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135072 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 430-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 430-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 440-LOK | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 440-LOK |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 453-VLISIDES | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 473-MOROI | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 473-MOROI |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 477-HIGGINS | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 477-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 478-LUGOGO | Calendar Released |  |  | User | Yunk, Jason | [7 empty] | Y |  | 478-LUGOGO |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 492-SMITH | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 492-SMITH |  |  |  | CTSU - Ambulatory and Chronic Disease
CTSU Pre-Award v2 - 557-HAN | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | N |  | 00147889 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00108880 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00108880 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00124920 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00124920 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125022 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125425 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00125425 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00125566 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00126010 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00126010 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00127136 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00127136 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128173 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00128173 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00128743 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00128743 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129427 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129652 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00129652 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129716 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00129716 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00129820 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00129820 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130575 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00130575 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00130793 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131329 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00131329 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131837 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00131953 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133290 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00133341 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00133341 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - 00134035 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendar & Budget Retrofit - PLT-INF24-001 | Questions |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00082356 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00082356 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00101426 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00111923 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Acknowledge |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00129427 | Provide PI-Determined Care Designations ( +/- Feedback ) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00129427 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00098496 | AME Calendaring Process Initiated; tracked protocol and summary of changes uploaded |  |  | User | Yunk, Jason | [7 empty] | N |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | ** Request(s) to Add Unscheduled Procedure(s) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | Acknowledge |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00127505 | Submit Update Request(s) |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00127505 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | Acknowledge |  |  | User | Yunk, Jason | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | Acknowledge |  |  | User | Yunk, Jason | [7 empty] | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | Submit Update Request(s) |  |  | User | Yunk, Jason | [6 empty] | 2018-03-30 | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 112-FLAHERTY | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Pre-Award Financial - 44-MCUNE | OnCore Budget Build |  |  | User | Yunk, Jason | [7 empty] | N |  | 44-MCUNE |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00123231 2 | ** Other |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00123231 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Assign to Analyst |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Complete MCA / QCT |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Complete SVS & Pricing List ( Built & Coded ) |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130757 | Nimblify Build is Complete & Ready for Import |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 251-COMER | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 327-HIGGINS | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian | [7 empty] | N |  | 00136918 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 46-HIGGINS | CRAO Approval Issue & Documented |  |  | User | Zahs, Brian | [7 empty] | N |  | 00136538 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00128531 | Assign to Analyst |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00128531 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | Assign to Analyst |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | Make Update(s) |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00130757 | Re-Complete Calendar |  |  | User | Zahs, Brian | [7 empty] | Y |  | 00130757 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Footnote Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Confirm Materials and Required Details ( Summary & Supporting Documents ) |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment CEP304DOC - 282-POP-BUSUI | Update RSH Source in MBECT |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Footnote Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00089260 | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00089260 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Footnote Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00133153 | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Items/Services : Addition or Removal of Procedures / Events |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 00136917 | Update RSH Source in MBECT |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00136917 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Footnote Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Items/Services : Updates to Activity for Existing Procedures / Events |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Visit Tolerance Edits |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process - 190-SCHIOPU | ** Visits : Addition or Removal of Time Points |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment Checklist & Process V2 - 00102868 | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Amendment due to migration - 00119527 | Complete Calendar and Document Approval |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | ** Other |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : CTA Amendment 1: Checklist & Process - 00125493 | Update RSH Source in MBECT |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00130793 | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00130793 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00133153 | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00133153 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00134884 | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00134884 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 112-FLAHERTY | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | Y |  | 112-FLAHERTY |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 170-SCHIOPU | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00134035 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 179-LUGOGO | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00135268 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | Assign to Analyst |  |  | User | van Dijk, Tim | [6 empty] | 2017-06-30 | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 190-SCHIOPU | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 325-AUCHUS | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00131840 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 337-MIAN | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 338-MIAN | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00133457 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 341-STOFFEL | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 403-HIGGINS | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00134895 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 404-HIGGINS | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00134896 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 453-VLISIDES | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00135919 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 49-MARTINEZ | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 536-NAGARAJA | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00138579 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 595-BAPTIST | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00141446 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 596-BELL | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00143380 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 616-YEVZLIN | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00144763 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 692-HIGGINS | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 692-HIGGINS |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 702-BESIRLI | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00142246 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - SLS-III | CRAO Approval Issue & Documented |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | Assign to Analyst |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | Make Update(s) |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - 00138433 | Re-Complete Calendar |  |  | User | van Dijk, Tim | [7 empty] | N |  | 00138433 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Cloned Current PAF | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Contract Executed | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Create new OnCore Budget Version | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Initiate CRAO Amendment Task List | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | PAF Complete | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | PI Signed PAF | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00095080 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Cloned Current PAF | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Contract Executed | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Create new OnCore Budget Version | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | PAF Complete | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | PI Signed PAF | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00098496 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Cloned Current PAF | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Contract Executed | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Create new OnCore Budget Version | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | PAF Complete | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | PI Signed PAF | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00101426 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00101426 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Amendment Requires Budget Revisions | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Amendment Requires Contract Amendment | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | CRAO Amendment Task List Completed | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Cloned Current PAF | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Contract Executed | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Create new OnCore Budget Version | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | IRB Amendment Approved in eRRM | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | IRB Amendment Submitted in eRRM | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | OnCore Calendar Released | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | PAF Complete | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | PI Signed PAF | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Revised Billing Grid Sent to Study Team | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Sent Budget to Sponsor for Revisions | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Study Team Approves OnCore Billing Grid | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00102868 | Study Team Contacted to Approve Amendment Change | [11 empty] | N |  | 00102868 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Cloned Current PAF | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Contract Executed | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | PAF Complete | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | PI Signed PAF | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00107954 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00107954 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Cloned Current PAF | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Contract Executed | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Create new OnCore Budget Version | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Initiate CRAO Amendment Task List | [10 empty] | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | OnCore Billing Calendar Change Needed | [10 empty] | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | OnCore Billing Calendar Completed | [10 empty] | 2017-12-22 | N |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | PAF Complete | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | PI Signed PAF | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00111923 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00111923 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113391 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00113391 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Amendment Requires Budget Revisions | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Amendment Requires Contract Amendment | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | CRAO Amendment Task List Completed | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Cloned Current PAF | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Contract Executed | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Create new OnCore Budget Version | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | IRB Amendment Approved in eRRM | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | IRB Amendment Submitted in eRRM | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Initiate CRAO Amendment Task List | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | OnCore Billing Calendar Change Needed | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | OnCore Billing Calendar Completed | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | OnCore Calendar Released | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | PAF Complete | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | PI Signed PAF | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Revised Billing Grid Sent to Study Team | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Sent Budget to Sponsor for Revisions | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Study Team Approves OnCore Billing Grid | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00113496 | Study Team Contacted to Approve Amendment Change | [11 empty] | N |  | 00113496 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119175 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00119175 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | CRAO Amendment Task List Completed | [11 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Initiate CRAO Amendment Task List | [11 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | OnCore Billing Calendar Change Needed | [11 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | OnCore Billing Calendar Completed | [11 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Revised Billing Grid Sent to Study Team | [11 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00119399 | Study Team Approves OnCore Billing Grid | [11 empty] | Y |  | 00119399 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Cloned Current PAF | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Contract Executed | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | PAF Complete | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | PI Signed PAF | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00120883 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | CRAO Amendment Task List Completed | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Cloned Current PAF | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Contract Executed | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | OnCore Calendar Released | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Study Team Approves OnCore Billing Grid | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00121049 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00121049 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Cloned Current PAF | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Contract Executed | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Create new OnCore Budget Version | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | PAF Complete | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | PI Signed PAF | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00122254 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00122254 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | CRAO Amendment Task List Completed | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Cloned Current PAF | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Contract Executed | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Create new OnCore Budget Version | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | IRB Amendment Approved in eRRM | [10 empty] | 2018-06-11 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | OnCore Billing Calendar Change Needed | [10 empty] | 2018-04-25 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | OnCore Calendar Released | [10 empty] | 2018-06-24 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | PAF Complete | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | PI Signed PAF | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Study Team Approves OnCore Billing Grid | [10 empty] | 2018-04-24 | N |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00123115 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00123115 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | CRAO Amendment Task List Completed | [10 empty] | 2018-06-22 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Contract Executed | [10 empty] | 2018-04-24 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | Create new OnCore Budget Version | [10 empty] | 2018-06-22 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125493 | IRB Amendment Approved in eRRM | [10 empty] | 2018-04-04 | N |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | CRAO Amendment Task List Completed | [10 empty] | 2018-04-23 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Cloned Current PAF | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Contract Executed | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Create new OnCore Budget Version | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | IRB Amendment Approved in eRRM | [10 empty] | 2018-04-17 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | OnCore Calendar Released | [10 empty] | 2018-04-23 | N |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | PAF Complete | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | PI Signed PAF | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00125566 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00125566 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Cloned Current PAF | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Contract Executed | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Create new OnCore Budget Version | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | PAF Complete | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | PI Signed PAF | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00128157 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00128157 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Cloned Current PAF | [11 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Contract Executed | [11 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | PAF Complete | [11 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | PI Signed PAF | [11 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00130803 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00130803 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Cloned Current PAF | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Contract Executed | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | PAF Complete | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | PI Signed PAF | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Received Protocol Amendment | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131837 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00131837 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Cloned Current PAF | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Contract Executed | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Initiate CRAO Amendment Task List | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | PAF Complete | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | PI Signed PAF | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00131953 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00131953 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | CRAO Amendment Task List Completed | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Cloned Current PAF | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Contract Executed | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Create new OnCore Budget Version | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | IRB Amendment Submitted in eRRM | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Initiate CRAO Amendment Task List | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | OnCore Billing Calendar Change Needed | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | OnCore Billing Calendar Completed | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | OnCore Calendar Released | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | PAF Complete | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | PI Signed PAF | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Revised Billing Grid Sent to Study Team | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132020 | Study Team Approves OnCore Billing Grid | [11 empty] | Y |  | 00132020 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Amendment Requires Budget Revisions | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Amendment Requires Contract Amendment | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | CRAO Amendment Task List Completed | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Cloned Current PAF | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Contract Executed | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Create new OnCore Budget Version | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | IRB Amendment Approved in eRRM | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | IRB Amendment Submitted in eRRM | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Initiate CRAO Amendment Task List | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | OnCore Billing Calendar Completed | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | OnCore Calendar Released | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | PAF Complete | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | PI Signed PAF | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Received Protocol Amendment | [11 empty] | Y |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Revised Billing Grid Sent to Study Team | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Sent Budget to Sponsor for Revisions | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Study Team Approves OnCore Billing Grid | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00132200 | Study Team Contacted to Approve Amendment Change | [11 empty] | N |  | 00132200 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | CRAO Amendment Task List Completed | [10 empty] | 2018-06-22 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Cloned Current PAF | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Contract Executed | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Create new OnCore Budget Version | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | IRB Amendment Approved in eRRM | [10 empty] | 2018-06-15 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | IRB Amendment Submitted in eRRM | [10 empty] | 2018-04-03 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Initiate CRAO Amendment Task List | [10 empty] | 2018-04-17 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | OnCore Billing Calendar Change Needed | [10 empty] | 2018-04-17 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | OnCore Billing Calendar Completed | [11 empty] | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | OnCore Calendar Released | [10 empty] | 2018-06-22 | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | PAF Complete | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | PI Signed PAF | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Revised Billing Grid Sent to Study Team | [11 empty] | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Study Team Approves OnCore Billing Grid | [11 empty] | N |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00133286 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00133286 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | CRAO Amendment Task List Completed | [10 empty] | 2018-03-21 | N |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Cloned Current PAF | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Contract Executed | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | PAF Complete | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | PI Signed PAF | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134232 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00134232 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Cloned Current PAF | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Contract Executed | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Create new OnCore Budget Version | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | IRB Amendment Submitted in eRRM | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | OnCore Billing Calendar Change Needed | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | OnCore Billing Calendar Completed | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | OnCore Calendar Released | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | PAF Complete | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | PI Signed PAF | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Received Protocol Amendment | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Revised Billing Grid Sent to Study Team | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134236 | Study Team Approves OnCore Billing Grid | [11 empty] | Y |  | 00134236 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Cloned Current PAF | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Contract Executed | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | PAF Complete | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | PI Signed PAF | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134443 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00134443 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | CRAO Amendment Task List Completed | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Initiate CRAO Amendment Task List | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | OnCore Billing Calendar Change Needed | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | OnCore Billing Calendar Completed | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Revised Billing Grid Sent to Study Team | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Study Team Approves OnCore Billing Grid | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00134997 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00134997 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | CRAO Amendment Task List Completed | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Cloned Current PAF | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Contract Executed | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Create new OnCore Budget Version | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | PAF Complete | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | PI Signed PAF | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment - 00135279 | Study Team Contacted to Approve Amendment Change | [11 empty] | Y |  | 00135279 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Amendment Requires Budget Revisions | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Amendment Requires Contract Amendment | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | CRAO Amendment Task List Completed | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Cloned Current PAF | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Contract Executed | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Create new OnCore Budget Version | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | IRB Amendment Approved in eRRM | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | IRB Amendment Submitted in eRRM | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Initiate CRAO Amendment Task List | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | OnCore Billing Calendar Change Needed | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | OnCore Billing Calendar Completed | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | OnCore Calendar Released | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | PAF Complete | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | PI Signed PAF | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Revised Billing Grid Sent to Study Team | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Sent Budget to Sponsor for Revisions | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Study Team Approves OnCore Billing Grid | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment 1. Replacement of the Per Subject Budget/pay schedule- 00125022 | Study Team Contacted to Approve Amendment Change | [11 empty] | N |  | 00125022 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Amendment Requires Budget Revisions | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Amendment Requires Contract Amendment | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Cloned Current PAF | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Contract Executed | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Create new OnCore Budget Version | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | PAF Complete | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | PI Signed PAF | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment INFUSION - 00115761 | Sent Budget to Sponsor for Revisions | [11 empty] | Y |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | CRAO Amendment Task List Completed | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Cloned Current PAF | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Contract Executed | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Create new OnCore Budget Version | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | IRB Amendment Approved in eRRM | [11 empty] | Y |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | PAF Complete | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | PI Signed PAF | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Sent Budget to Sponsor for Revisions | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment vE- 00133290 | Study Team Contacted to Approve Amendment Change | [11 empty] | N |  | 00133290 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Amendment Requires Budget Revisions | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Amendment Requires Contract Amendment | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Cloned Current PAF | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Contract Executed | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Create new OnCore Budget Version | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | IRB Amendment Approved in eRRM | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | IRB Amendment Submitted in eRRM | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | OnCore Billing Calendar Completed | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | OnCore Calendar Released | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | PAF Complete | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | PI Signed PAF | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Revised Billing Grid Sent to Study Team | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Sent Budget to Sponsor for Revisions | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Study Team Approves OnCore Billing Grid | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
ACD Amendment-Rescreening- 00099421 | Study Team Contacted to Approve Amendment Change | [11 empty] | N |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
BC : Initial Build - PLT-INF24-001 | Assign to Analyst | [11 empty] | Y |  | 00135388 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Acknowledge | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Assign to Analyst | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Attach Build Notes ( as Protocol Doc ) | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | CRAO Approval Issue & Documented | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Complete Calendar ( ie. Ready for Financials ) | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Complete MCA / QCT | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Complete SVS & Pricing List ( Built & Coded ) | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Feasibility Approval Notice Received | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Import + Michiganize & Export Billing Grid for Determining Care Designations | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Make Updates | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Nimblify Build is Complete & Ready for Import | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Submit Calendar Build Request and Docs to Nimblify | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Initial Calendar Build - 00126215 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | [11 empty] | N |  | 00126215 |  |  |  | CTSU - Ambulatory and Chronic Disease
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Re-Complete Calendar | [11 empty] | Y |  | 00066077 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Start timeline (2 weeks before study go-live date) | [11 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Update on subject data collection status - see communications | [11 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00082007 | Update on training status - see communications | [11 empty] | N |  | 00082007 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00089615 | Update on training status - see communications | [11 empty] | Y |  | 00089615 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00094631 | Update on training status - see communications | [11 empty] | Y |  | 00094631 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Start timeline (2 weeks before study go-live date) | [10 empty] | 2018-01-12 | N |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00095080 | Update on training status - see communications | [11 empty] | Y |  | 00095080 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00098496 | Update on training status - see communications | [11 empty] | Y |  | 00098496 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00099421 | Update on training status - see communications | [11 empty] | Y |  | 00099421 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00109151 | Update on training status - see communications | [11 empty] | Y |  | 00109151 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Start timeline (2 weeks before study go-live date) | [11 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Update on subject data collection status - see communications | [11 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00111675 | Update on training status - see communications | [11 empty] | N |  | 00111675 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00113845 | Update on training status - see communications | [11 empty] | Y |  | 00113845 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00114708 | Update on training status - see communications | [11 empty] | Y |  | 00114708 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Start timeline (2 weeks before study go-live date) | [11 empty] | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Update on subject data collection status - see communications | [11 empty] | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00115761 | Update on training status - see communications | [11 empty] | N |  | 00115761 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00116976 | Update on training status - see communications | [11 empty] | Y |  | 00116976 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00118069 | Update on training status - see communications | [11 empty] | Y |  | 00118069 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119527 | Update on training status - see communications | [11 empty] | Y |  | 00119527 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Start timeline (2 weeks before study go-live date) | [11 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Update on subject data collection status - see communications | [11 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00119871 | Update on training status - see communications | [11 empty] | N |  | 00119871 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00120883 | Update on training status - see communications | [11 empty] | Y |  | 00120883 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Start timeline (2 weeks before study go-live date) | [11 empty] | N |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00121481 | Update on training status - see communications | [11 empty] | Y |  | 00121481 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00125493 | Update on training status - see communications | [11 empty] | Y |  | 00125493 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127612 | Update on training status - see communications | [11 empty] | Y |  | 00127612 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Start timeline (2 weeks before study go-live date) | [11 empty] | N |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Update on subject data collection status - see communications | [11 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Migration: General V2 - 00127778 | Update on training status - see communications | [11 empty] | Y |  | 00127778 |  |  |  | CTSU - Ambulatory and Chronic Disease
Open to Accrual - 235-SUGAR | Study Files Established | [10 empty] | 2017-03-09 | N |  | 00134503 |  |  |  | CTSU - Ambulatory and Chronic Disease
Report Date: